## 📊 Summary
Component PO Plan — Executive Summary
Production rate (monthly) | 101336: 150/mo 101759: 25/mo 101760: 25/mo 101711: 40/mo 101769: 20/mo 102237: 5/mo 101490: 1/mo 102240: 20/mo 101059: 150/mo 100986: 150/mo 102036: 100/mo 101557: 200/mo
Coverage target | 7 months
Reorder point | 3 months coverage remaining
Order qty rounding | Round up to nearest 50
Generated | 2026-03-02 22:24 UTC
Total components in scope | 95
🔴 ORDER NOW (overdue) | 7
🟠 Order within 14 days | 2
🟡 Plan ahead (order date upcoming) | 66
✅ Sufficient stock | 20
⚠ No supplier configured | 0
⚠ Lead time = 0 (needs review) | 6
💰 Estimated total PO value | $840,137
Supplier | Parts | To Order | Urgent | Est. Value
ICO Mold LLC | 28 | 24 | 6 | $48,352
ULINE, Sales ULINE | 1 | 1 | 1 | N/A
Alloy Concepts | 19 | 18 | 0 | $231,386
Custom Sheet Metal Products (CSTM) | 2 | 2 | 0 | $75,042
Atlas Gaskets | 4 | 4 | 0 | $5,781
Atlas Gaskets, Rebecca Lopez | 1 | 1 | 0 | $80
Globtek Inc. | 2 | 2 | 0 | $6,132
Alloy Concepts, Perry MacIssaac | 1 | 1 | 0 | $38,192
GEB General Electronics Battery Co | 1 | 1 | 0 | $1,872
Graphiscan | 1 | 1 | 0 | $911
Moticont | 1 | 1 | 0 | $234,773
Net Burner | 1 | 1 | 0 | $95,200
Xometry, Ethan Beum | 1 | 1 | 0 | $11,391
OSD Displays | 1 | 1 | 0 | $5,760
SMT Hautes Technologies | 11 | 3 | 0 | $31,760
TWP | 1 | 1 | 0 | $1,282
ICO Mold LLC, Brian Bay | 6 | 5 | 0 | $1,884
Minco | 1 | 1 | 0 | $16,140
NEL Technologies | 1 | 1 | 0 | $14,278
E-Sonic | 2 | 2 | 0 | $11,310
Lovepac | 1 | 1 | 0 | $4,896
OSD Displays, Christopher Geisler | 1 | 1 | 0 | $2,500
Bogen Magnetics GmbH Magnetics | 1 | 1 | 0 | $1,215
FrontierPC | 1 | 0 | 0 | N/A
The ZPS Store | 1 | 0 | 0 | N/A
Barcodes Inc. | 1 | 0 | 0 | N/A
SEKI | 2 | 0 | 0 | N/A
Xometry | 1 | 0 | 0 | N/A

## 📋 PO Plan
Component PO Plan — 6-Month Rolling Coverage (95 components)
Rate: 101336×150 101759×25 101760×25 101711×40 101769×20 102237×5 101490×1 102240×20 101059×150 100986×150 102036×100 101557×200 /mo ¦ Target: 7mo ¦ Reorder at: 3mo ¦ Generated: 2026-03-02 22:24 UTC
Ref | Component Name | Supplier | Sup Code | Lead Days | Min Qty | Stock Avail | Open Incoming | Total Avail | Monthly Req | Coverage Now(mo) | Reorder Point | Target Qty(7mo) | ORDER QTY | Coverage After | Latest Safe Order Date | Buffer (days) | Price Source | Est Value (USD) | Status
🔴 ORDER NOW — 7 components (lead time already exceeded)
101744 | [101744] tf C-100 HHU LOOVER PLATE - V | ICO Mold LLC |  | 42 |  | 63 | 0 | 63 | 50 | 1.3 | 150 | 350 | 300 | 7.3 | 2026-03-02 | -3 | P01432 (USD) | 3744 | 🔴 CRITICAL — stock out in 38d, lead 42d — ORDER TODAY
101745 | [101745] tf C-100 HHU FRONT CAP - Vita | ICO Mold LLC |  | 42 |  | 61 | 0 | 61 | 50 | 1.2 | 150 | 350 | 300 | 7.2 | 2026-03-02 | -4 | P01432 (USD) | 3780 | 🔴 CRITICAL — stock out in 37d, lead 42d — ORDER TODAY
101746 | [101746] tf C-100 HHU_NAME PLATE - Vit | ICO Mold LLC |  | 42 |  | 54 | 0 | 54 | 50 | 1.1 | 150 | 350 | 300 | 7.1 | 2026-03-02 | -9 | P01432 (USD) | 3744 | 🔴 CRITICAL — stock out in 32d, lead 42d — ORDER TODAY
101747 | [101747] tf C-100 CCU Enclosure Holder | ICO Mold LLC |  | 42 |  | 61 | 0 | 61 | 50 | 1.2 | 150 | 350 | 300 | 7.2 | 2026-03-02 | -4 | P01432 (USD) | 4290 | 🔴 CRITICAL — stock out in 37d, lead 42d — ORDER TODAY
101748 | [101748] tf C-100 CCU Enclosure front | ICO Mold LLC |  | 42 |  | 62 | 0 | 62 | 50 | 1.2 | 150 | 350 | 300 | 7.2 | 2026-03-02 | -4 | P01432 (USD) | 5778 | 🔴 CRITICAL — stock out in 37d, lead 42d — ORDER TODAY
101749 | [101749] tf C-100 HHU BACK SHELL - Vit | ICO Mold LLC |  | 42 |  | 59 | 0 | 59 | 50 | 1.2 | 150 | 350 | 300 | 7.2 | 2026-03-02 | -6 | P01432 (USD) | 7044 | 🔴 CRITICAL — stock out in 35d, lead 42d — ORDER TODAY
102020 | [102020] Wafer Seal Sticker 1.5in | ULINE, Sales ULINE |  | 1 |  | 0 | 0 | 0 | 200 | 0 | 600 | 1400 | 1400 | 7 | 2026-03-02 | -1 | pricelist |  | 🔴 CRITICAL — stock out in 0d, lead 1d — ORDER TODAY
🟠 ORDER WITHIN 14 DAYS — 2 components
100978 | [100978] tF C100 PFT Filter Interface | Alloy Concepts |  | 56 |  | 0 | 2 | 2 | 1 | 2 | 3 | 7 | 50 | 52 | 2026-03-06 | 4 | P01883 (CAD) | 4123.3 | 🟠 Order NOW — only 4d buffer
100359 | [100359] TremoFlo C-100 CU Metal Enclo | Custom Sheet Metal P | 100359 | 70 |  | 226 | 300 | 526 | 201 | 2.6 | 603 | 1407 | 900 | 7.1 | 2026-03-11 | 9 | P01840 (CAD) | 74687.76 | 🟠 Order NOW — only 9d buffer
🟡 PLAN AHEAD — 66 components (order date upcoming)
101683 | [101683] tf C2 - Pneumotach Mesh | Atlas Gaskets |  | 28 |  | 143 | 0 | 143 | 85 | 1.7 | 255 | 595 | 500 | 7.6 | 2026-03-25 | 23 | P01559 (USD) | 4725 | 🟡 Order by 2026-03-25 — 23d buffer (lead 28d)
101699 | [101699] tf C2 - Pneumotach Neck Foam | Atlas Gaskets, Rebec |  | 50 |  | 204 | 0 | 204 | 85 | 2.4 | 255 | 595 | 400 | 7.1 | 2026-03-25 | 23 | P00729 (USD) | 80 | 🟡 Order by 2026-03-25 — 23d buffer (lead 50d)
101694 | [101694] USB Cable Type C to A - 2 Fe | Globtek Inc. |  | 1 |  | 91 | 0 | 91 | 100 | 0.9 | 300 | 700 | 650 | 7.4 | 2026-03-28 | 26 | P00730 (USD) | 5486 | 🟡 Order by 2026-03-28 — 26d buffer (lead 1d)
101718 | [101718] tf C2 - Main Body CNC | Alloy Concepts, Perr |  | 56 |  | 228 | 5 | 233 | 85 | 2.7 | 255 | 595 | 400 | 7.4 | 2026-03-29 | 27 | P01635 (USD) | 38192 | 🟡 Order by 2026-03-29 — 27d buffer (lead 56d)
101719 | [101719] tf C2 Piston CNC | Alloy Concepts |  | 56 |  | 248 | 5 | 253 | 85 | 3 | 255 | 595 | 350 | 7.1 | 2026-04-05 | 34 | P01635 (USD) | 20461 | 🟡 Order by 2026-04-05 — 34d buffer (lead 56d)
101706 | [101706] tf C2 - Exhaust Mesh Frame | Custom Sheet Metal P |  | 70 |  | 337 | 0 | 337 | 85 | 4 | 255 | 595 | 300 | 7.5 | 2026-04-21 | 50 | P00754 (CAD) | 354.06 | 🟢 Order by 2026-04-21 — 50d buffer (lead 70d)
101750 | [101750] tf C-100 CCU Enclosure Top - | ICO Mold LLC |  | 42 |  | 162 | 0 | 162 | 50 | 3.2 | 150 | 350 | 200 | 7.2 | 2026-04-27 | 56 | P01432 (USD) | 4448 | 🟢 Order by 2026-04-27 — 56d buffer (lead 42d)
101658 | [101658] tf C2 Battery Pack | GEB General Electro |  | 42 |  | 79 | 200 | 279 | 85 | 3.3 | 255 | 595 | 350 | 7.4 | 2026-04-28 | 57 | P01790 (USD) | 1872.5 | 🟢 Order by 2026-04-28 — 57d buffer (lead 42d)
102128 | [102128] C2 USB Power Supply Box Sleev | Graphiscan |  | 0 |  | 197 | 0 | 197 | 100 | 2 | 300 | 700 | 550 | 7.5 | 2026-04-30 | 59 | P01554 (CAD) | 911.13 | ⚠ CHECK LEAD TIME — 🟢 Order by 2026-04-30 — 59d buffer (lead 0d)
101104 | [101104] Test Load Assy | Alloy Concepts |  | 60 |  | 153 | 450 | 603 | 150 | 4 | 450 | 1050 | 450 | 7 | 2026-05-03 | 62 | P01745 (CAD) | 22763.88 | 🟢 Order by 2026-05-03 — 62d buffer (lead 60d)
101675 | [101675] tf C2 - Battery Strap | Atlas Gaskets |  | 28 |  | 256 | 0 | 256 | 85 | 3 | 255 | 595 | 350 | 7.1 | 2026-05-04 | 63 | P00729 (USD) | 605.5 | 🟢 Order by 2026-05-04 — 63d buffer (lead 28d)
101278 | [101278] tf C100 Motor Assembly VCA | Moticont | LVCM-016-019-01 | 28 |  | 531 | 400 | 931 | 286 | 3.3 | 858 | 2002 | 1100 | 7.1 | 2026-05-12 | 71 | P01885 (USD) | 234773 | 🟢 Order by 2026-05-12 — 71d buffer (lead 28d)
100159 | [100159] NetBurner Ethernet Core Modul | Net Burner | MOD5234-200IR | 21 |  | 323 | 300 | 623 | 201 | 3.1 | 603 | 1407 | 800 | 7.1 | 2026-05-14 | 73 | P01841 (USD) | 95200 | 🟢 Order by 2026-05-14 — 73d buffer (lead 21d)
101755 | [101755] tf C-100 Filter interface Vit | Xometry, Ethan Beum |  | 1 |  | 125 | 0 | 125 | 50 | 2.5 | 150 | 350 | 250 | 7.5 | 2026-05-16 | 75 | P01405 (CAD) | 11391.3 | 🟢 Order by 2026-05-16 — 75d buffer (lead 1d)
100348 | [100348] TremoFlo C-100 Motor Piston M | Alloy Concepts | 100348 | 56 |  | 136 | 750 | 886 | 201 | 4.4 | 603 | 1407 | 550 | 7.1 | 2026-05-19 | 78 | P01745 (CAD) | 12707.81 | 🟢 Order by 2026-05-19 — 78d buffer (lead 56d)
101682 | [101682] tf C2 - Sensor Module Foam Ga | Atlas Gaskets |  | 28 |  | 298 | 0 | 298 | 85 | 3.5 | 255 | 595 | 300 | 7 | 2026-05-19 | 78 | P00729 (USD) | 177 | 🟢 Order by 2026-05-19 — 78d buffer (lead 28d)
101672 | [101672] tf C2 - Custom Display Assemb | OSD Displays |  | 60 |  | 298 | 0 | 298 | 65 | 4.6 | 195 | 455 | 200 | 7.7 | 2026-05-20 | 79 | P00326 (USD) | 5760 | 🟢 Order by 2026-05-20 — 79d buffer (lead 60d)
101106 | [101106] TremoFlo C100 Custom made cab | SMT Hautes Technolog | 101106 | 112 |  | 278 | 1002 | 1280 | 201 | 6.4 | 603 | 1407 | 150 | 7.1 | 2026-05-22 | 81 | P01838 (CAD) | 8519.28 | 🟢 Order by 2026-05-22 — 81d buffer (lead 112d)
101979 | [101979] Test Load Mesh 165X1400 | TWP |  | 0 |  | 407 | 0 | 407 | 150 | 2.7 | 450 | 1050 | 650 | 7 | 2026-05-23 | 82 | P01854 (CAD) | 1281.73 | ⚠ CHECK LEAD TIME — 🟢 Order by 2026-05-23 — 82d buffer (lead 0d)
101685 | [101685] tf C2 Pneumotach Main Part | ICO Mold LLC, Brian |  | 42 |  | 352 | 0 | 352 | 85 | 4.1 | 255 | 595 | 250 | 7.1 | 2026-05-25 | 84 | P00741 (USD) | 315 | 🟢 Order by 2026-05-25 — 84d buffer (lead 42d)
100346 | [100346] TremoFlo C-100 Pneumotach RTD | Minco | S100725PFYT24B | 42 |  | 443 | 400 | 843 | 201 | 4.2 | 603 | 1407 | 600 | 7.2 | 2026-05-26 | 85 | P01886 (USD) | 16140 | 🟢 Order by 2026-05-26 — 85d buffer (lead 42d)
100481 | [100481] TremoFlo C-100 Handheld Ring | SMT Hautes Technolog |  | 119 |  | 87 | 1299 | 1386 | 201 | 6.9 | 603 | 1407 | 50 | 7.1 | 2026-05-31 | 90 | P01746 (USD) | 4696 | 🟢 Order by 2026-05-31 — 90d buffer (lead 119d)
100345 | [100345] TremoFlo C-100 Pneumotach Hea | NEL Technologies | NEL-2018-1743-HA | 42 |  | 490 | 400 | 890 | 201 | 4.4 | 603 | 1407 | 550 | 7.2 | 2026-06-02 | 92 | P01886 (USD) | 14278 | 🟢 Order by 2026-06-02 — 92d buffer (lead 42d)
100326 | [100326] TremoFlo C-100 Motor Piston O | Alloy Concepts | 100326 | 56 |  | 234 | 750 | 984 | 201 | 4.9 | 603 | 1407 | 450 | 7.1 | 2026-06-03 | 93 | P01745 (CAD) | 3869.28 | 🟢 Order by 2026-06-03 — 93d buffer (lead 56d)
101681 | [101681] tf C2 Sensor Module Cover | ICO Mold LLC |  | 42 |  | 380 | 0 | 380 | 85 | 4.5 | 255 | 595 | 250 | 7.4 | 2026-06-04 | 94 | P00741 (USD) | 290 | 🟢 Order by 2026-06-04 — 94d buffer (lead 42d)
101541 | [101541] tF C-100 Pneumotach Heater Ri | Alloy Concepts | 101541 | 56 |  | 249 | 750 | 999 | 201 | 5 | 603 | 1407 | 450 | 7.2 | 2026-06-05 | 95 | P01745 (CAD) | 14860.35 | 🟢 Order by 2026-06-05 — 95d buffer (lead 56d)
100318 | [100318] TremoFlo C-100 Motor Bobbin | Alloy Concepts | 100318 | 56 |  | 111 | 900 | 1011 | 201 | 5 | 603 | 1407 | 400 | 7 | 2026-06-07 | 97 | P01745 (CAD) | 48045.76 | 🟢 Order by 2026-06-07 — 97d buffer (lead 56d)
100866 | [100866] THERMOSTAT 50 DEG NC TO-220 A | E-Sonic | 67L050 | 14 |  | 337 | 400 | 737 | 201 | 3.7 | 603 | 1407 | 700 | 7.1 | 2026-06-07 | 97 | P01595 (CAD) | 5105.59 | 🟢 Order by 2026-06-07 — 97d buffer (lead 14d)
101540 | [101540] tF C-100 Pneumotach Main Body | Alloy Concepts | 101540 | 56 |  | 118 | 928 | 1046 | 201 | 5.2 | 603 | 1407 | 400 | 7.2 | 2026-06-12 | 102 | P01745 (CAD) | 25682.44 | 🟢 Order by 2026-06-12 — 102d buffer (lead 56d)
101671 | [101671] tf C2 Shoe Mount Cover | ICO Mold LLC |  | 42 |  | 403 | 0 | 403 | 85 | 4.7 | 255 | 595 | 200 | 7.1 | 2026-06-12 | 102 | P00741 (USD) | 244 | 🟢 Order by 2026-06-12 — 102d buffer (lead 42d)
101680 | [101680] tf C2 Motor Rod | Alloy Concepts |  | 63 |  | 534 | 400 | 934 | 170 | 5.5 | 510 | 1190 | 300 | 7.3 | 2026-06-14 | 104 | P01381 (CAD) | 3208.47 | 🟢 Order by 2026-06-14 — 104d buffer (lead 63d)
100975 | [100975] tF C100 Pneumotach Inner Mesh | Alloy Concepts | 100975 | 56 |  | 169 | 900 | 1069 | 201 | 5.3 | 603 | 1407 | 350 | 7.1 | 2026-06-15 | 105 | P01745 (CAD) | 5680.25 | 🟢 Order by 2026-06-15 — 105d buffer (lead 56d)
100977 | [100977] tF C100 Pneumotach Knob | Alloy Concepts | 100977 | 56 |  | 450 | 634 | 1084 | 201 | 5.4 | 603 | 1407 | 350 | 7.1 | 2026-06-18 | 108 | P01745 (CAD) | 7725.03 | 🟢 Order by 2026-06-18 — 108d buffer (lead 56d)
100321 | [100321] TremoFlo C-100 Motor Shaft | Alloy Concepts |  | 56 |  | 576 | 1611 | 2187 | 402 | 5.4 | 1206 | 2814 | 650 | 7.1 | 2026-06-19 | 109 | P01745 (CAD) | 6494.28 | 🟢 Order by 2026-06-19 — 109d buffer (lead 56d)
100976 | [100976] tF C100 Pneumotach Outer Mesh | Alloy Concepts | 100976 | 56 |  | 197 | 900 | 1097 | 201 | 5.5 | 603 | 1407 | 350 | 7.2 | 2026-06-20 | 110 | P01745 (CAD) | 7314.55 | 🟢 Order by 2026-06-20 — 110d buffer (lead 56d)
100790 | [100790] tF C-100 HHU_STRAIN RELIEF In | ICO Mold LLC | 030-100790-00 | 42 |  | 383 | 1700 | 2083 | 402 | 5.2 | 1206 | 2814 | 750 | 7 | 2026-06-25 | 115 | P01844 (USD) | 832.5 | 🟢 Order by 2026-06-25 — 115d buffer (lead 42d)
101255 | [101255] tF C-100 Light Motor Back Pla | Alloy Concepts | 101255 | 56 |  | 457 | 696 | 1153 | 201 | 5.7 | 603 | 1407 | 300 | 7.2 | 2026-06-28 | 118 | P01745 (CAD) | 12130.2 | 🟢 Order by 2026-06-28 — 118d buffer (lead 56d)
101609 | [101609] Reference Load Shipper box wi | Lovepac |  | 0 |  | 206 | 960 | 1166 | 300 | 3.9 | 900 | 2100 | 950 | 7.1 | 2026-06-28 | 118 | P01871 (CAD) | 4895.54 | ⚠ CHECK LEAD TIME — 🟢 Order by 2026-06-28 — 118d buffer (lead 0d)
101669 | [101669] tf C2 USB-C Cap | ICO Mold LLC, Brian |  | 42 |  | 345 | 0 | 345 | 65 | 5.3 | 195 | 455 | 150 | 7.6 | 2026-06-29 | 119 | P00741 (USD) | 307.5 | 🟢 Order by 2026-06-29 — 119d buffer (lead 42d)
101670 | [101670] tf C2 Front Cap | ICO Mold LLC, Brian |  | 42 |  | 356 | 0 | 356 | 65 | 5.5 | 195 | 455 | 100 | 7 | 2026-07-04 | 124 | P00741 (USD) | 155 | 🟢 Order by 2026-07-04 — 124d buffer (lead 42d)
102242 | [102242] tf C2 Top Shell - VTG | ICO Mold LLC |  | 42 |  | 52 | 58 | 110 | 20 | 5.5 | 60 | 140 | 50 | 8 | 2026-07-05 | 125 | P01865 (USD) | 1545 | 🟢 Order by 2026-07-05 — 125d buffer (lead 42d)
102243 | [102243] tf C2 Front Cap – VTG | ICO Mold LLC |  | 42 |  | 52 | 58 | 110 | 20 | 5.5 | 60 | 140 | 50 | 8 | 2026-07-05 | 125 | P01865 (USD) | 1450 | 🟢 Order by 2026-07-05 — 125d buffer (lead 42d)
102244 | [102244] tf C2 USB-C Cap – VTG | ICO Mold LLC |  | 42 |  | 55 | 55 | 110 | 20 | 5.5 | 60 | 140 | 50 | 8 | 2026-07-05 | 125 | P01865 (USD) | 1050 | 🟢 Order by 2026-07-05 — 125d buffer (lead 42d)
100783 | [100783] tF C-100 HHU_LENS LIGHT PIPE | ICO Mold LLC | 100783 | 42 |  | 714 | 400 | 1114 | 201 | 5.5 | 603 | 1407 | 300 | 7 | 2026-07-06 | 126 | P01844 (USD) | 774 | 🟢 Order by 2026-07-06 — 126d buffer (lead 42d)
100328 | [100328] TremoFlo C-100 Motor Piston I | Alloy Concepts | 100328 | 56 |  | 379 | 842 | 1221 | 201 | 6.1 | 603 | 1407 | 200 | 7.1 | 2026-07-08 | 128 | P01745 (CAD) | 1508.58 | 🟢 Order by 2026-07-08 — 128d buffer (lead 56d)
101535 | [101535] PCBA tF C-100 Connector Board | SMT Hautes Technolog | 101535 | 70 |  | 44 | 1265 | 1309 | 201 | 6.5 | 603 | 1407 | 100 | 7 | 2026-07-08 | 128 | P01746 (USD) | 18545 | 🟢 Order by 2026-07-08 — 128d buffer (lead 70d)
100322 | [100322] TremoFlo C-100 Hall Sensor Br | Alloy Concepts | 100322 | 56 |  | 765 | 475 | 1240 | 201 | 6.2 | 603 | 1407 | 200 | 7.2 | 2026-07-11 | 131 | P01745 (CAD) | 3605.04 | 🟢 Order by 2026-07-11 — 131d buffer (lead 56d)
101254 | [101254] tF C-100 Light Piston | Alloy Concepts |  | 56 |  | 245 | 1005 | 1250 | 201 | 6.2 | 603 | 1407 | 200 | 7.2 | 2026-07-13 | 133 | P01745 (CAD) | 18761.18 | 🟢 Order by 2026-07-13 — 133d buffer (lead 56d)
100794 | [100794] tF C-100 CCU Enclosure Holder | ICO Mold LLC | 030-100794-00 | 42 |  | 410 | 464 | 874 | 151 | 5.8 | 453 | 1057 | 200 | 7.1 | 2026-07-14 | 134 | P01844 (USD) | 814 | 🟢 Order by 2026-07-14 — 134d buffer (lead 42d)
100793 | [100793] tF C-100 CCU Enclosure Top In | ICO Mold LLC | 030-100793-00 | 42 |  | 493 | 400 | 893 | 151 | 5.9 | 453 | 1057 | 200 | 7.2 | 2026-07-18 | 138 | P01844 (USD) | 2888 | 🟢 Order by 2026-07-18 — 138d buffer (lead 42d)
101393 | [101393] MOTOR THERMAL SWITCH [O53GAB1 | E-Sonic | O53GAB140A-125Y | 14 |  | 620 | 400 | 1020 | 201 | 5.1 | 603 | 1407 | 400 | 7.1 | 2026-07-20 | 140 | P01873 (CAD) | 6204.36 | 🟢 Order by 2026-07-20 — 140d buffer (lead 14d)
100797 | [100797] tF C-100 CCU Enclosure Interf | ICO Mold LLC | 100797 | 42 |  | 511 | 700 | 1211 | 201 | 6 | 603 | 1407 | 200 | 7 | 2026-07-21 | 141 | P01844 (USD) | 284 | 🟢 Order by 2026-07-21 — 141d buffer (lead 42d)
100785 | [100785] tF C-100 HHU_LEFT BUTTON Inj. | ICO Mold LLC | 030-100785-00 | 42 |  | 521 | 700 | 1221 | 201 | 6.1 | 603 | 1407 | 200 | 7.1 | 2026-07-22 | 142 | P01844 (USD) | 222 | 🟢 Order by 2026-07-22 — 142d buffer (lead 42d)
100786 | [100786] tF C100 HHU RIGHT BUTTON Inj. | ICO Mold LLC | 030-100786-00 | 42 |  | 543 | 700 | 1243 | 201 | 6.2 | 603 | 1407 | 200 | 7.2 | 2026-07-26 | 146 | P01844 (USD) | 222 | 🟢 Order by 2026-07-26 — 146d buffer (lead 42d)
100795 | [100795] tF C-100 CCU Enclosure BOTTOM | ICO Mold LLC | 030-100795-00 | 42 |  | 153 | 1100 | 1253 | 201 | 6.2 | 603 | 1407 | 200 | 7.2 | 2026-07-27 | 147 | P01844 (USD) | 1428 | 🟢 Order by 2026-07-27 — 147d buffer (lead 42d)
101700 | [101700] tf C2 Pneumotach chamber Back | ICO Mold LLC, Brian |  | 42 |  | 283 | 250 | 533 | 85 | 6.3 | 255 | 595 | 100 | 7.4 | 2026-07-28 | 148 | P01826 (USD) | 523 | 🟢 Order by 2026-07-28 — 148d buffer (lead 42d)
102245 | [102245] tf C2 Custom Display Assembly | OSD Displays, Christ |  | 1 |  | 0 | 100 | 100 | 20 | 5 | 60 | 140 | 50 | 7.5 | 2026-07-31 | 151 | P01866 (USD) | 2500 | 🟢 Order by 2026-07-31 — 151d buffer (lead 1d)
100781 | [100781] tF C-100 HHU Front Shell Inj. | ICO Mold LLC | 030-100781-00 | 42 |  | 197 | 1100 | 1297 | 201 | 6.5 | 603 | 1407 | 150 | 7.2 | 2026-08-03 | 154 | P01844 (USD) | 1575 | 🟢 Order by 2026-08-03 — 154d buffer (lead 42d)
100782 | [100782] tF C-100 HHU BACK SHELL Inj. | ICO Mold LLC | 030-100782-00 | 42 |  | 578 | 400 | 978 | 151 | 6.5 | 453 | 1057 | 100 | 7.1 | 2026-08-04 | 155 | P01844 (USD) | 1717 | 🟢 Order by 2026-08-04 — 155d buffer (lead 42d)
101668 | [101668] tf C2 Bottom Shell | ICO Mold LLC, Brian |  | 42 |  | 569 | 0 | 569 | 85 | 6.7 | 255 | 595 | 50 | 7.3 | 2026-08-10 | 161 | P01148 (USD) | 583 | 🟢 Order by 2026-08-10 — 161d buffer (lead 42d)
102114 | [102114] Test Load Assy for Reference | Alloy Concepts |  | 1 |  | 380 | 450 | 830 | 150 | 5.5 | 450 | 1050 | 250 | 7.2 | 2026-08-16 | 167 | P01745 (CAD) | 12445.02 | 🟢 Order by 2026-08-16 — 167d buffer (lead 1d)
100784 | [100784] tF C-100 HHU_LOOVER REAR PLAT | ICO Mold LLC | 030-100784-00 | 42 |  | 650 | 400 | 1050 | 151 | 7 | 453 | 1057 | 50 | 7.3 | 2026-08-18 | 169 | P01844 (USD) | 96 | 🟢 Order by 2026-08-18 — 169d buffer (lead 42d)
100791 | [100791] tF C-100 HHU_NAME PLATE Inj. | ICO Mold LLC | 030-100791-00 | 42 |  | 653 | 400 | 1053 | 151 | 7 | 453 | 1057 | 50 | 7.3 | 2026-08-19 | 170 | P01844 (USD) | 93 | 🟢 Order by 2026-08-19 — 170d buffer (lead 42d)
101707 | [101707] tf C2 - Exhaust Mesh Standard | Atlas Gaskets |  | 28 |  | 567 | 0 | 567 | 85 | 6.7 | 255 | 595 | 50 | 7.3 | 2026-08-24 | 175 | P01559 (USD) | 273.5 | 🟢 Order by 2026-08-24 — 175d buffer (lead 28d)
101498 | [101498] Magnetic strip 24mm | Bogen Magnetics GmbH |  | 1 |  | 1756 | 0 | 1756 | 286 | 6.1 | 858 | 2002 | 250 | 7 | 2026-09-03 | 185 | P01674 (USD) | 1215 | 🟢 Order by 2026-09-03 — 185d buffer (lead 1d)
101663 | [101663] tf C2 Power Supply | Globtek Inc. |  | 0 |  | 659 | 0 | 659 | 100 | 6.6 | 300 | 700 | 50 | 7.1 | 2026-09-18 | 200 | P00730 (USD) | 645.5 | ⚠ CHECK LEAD TIME — 🟢 Order by 2026-09-18 — 200d buffer (lead 0d)
✅ SUFFICIENT STOCK — 20 components (coverage > 7 months)
100477 | [100477] tremoFlo C-100 Mezzanine PCBA | SMT Hautes Technolog | 100477 | 70 |  | 79 | 1340 | 1419 | 201 | 7.1 | 603 | 1407 |  |  |  |  | P01746 (USD) |  | ✅ Sufficient
100479 | [100479] TremoFlo C-100 Handheld Main | SMT Hautes Technolog |  | 119 |  | 61 | 1438 | 1499 | 201 | 7.5 | 603 | 1407 |  |  |  |  | P01746 (USD) |  | ✅ Sufficient
100480 | [100480] TremoFlo C-100 Handheld Posit | SMT Hautes Technolog |  | 119 |  | 175 | 1481 | 1656 | 201 | 8.2 | 603 | 1407 |  |  |  |  | P01746 (USD) |  | ✅ Sufficient
100789 | [100789] tF C-100 HHU_FRONT CAP Inj. | ICO Mold LLC | 030-100789-00 | 42 |  | 702 | 400 | 1102 | 151 | 7.3 | 453 | 1057 |  |  |  |  | P01844 (USD) |  | ✅ Sufficient
100792 | [100792] tF C-100 CCU Enclosure front | ICO Mold LLC | 030-100792-00 | 42 |  | 196 | 1100 | 1296 | 151 | 8.6 | 453 | 1057 |  |  |  |  | P01844 (USD) |  | ✅ Sufficient
100796 | [100796] tF C-100 CCU Enclosure Power | ICO Mold LLC | 030-100796-00 | 42 |  | 1943 | 700 | 2643 | 201 | 13.1 | 603 | 1407 |  |  |  |  | P01844 (USD) |  | ✅ Sufficient
101385 | [101385] tF C-100 PFT Filter Interface | Alloy Concepts | 101385 | 56 |  | 357 | 800 | 1157 | 150 | 7.7 | 450 | 1050 |  |  |  |  | P01745 (CAD) |  | ✅ Sufficient
101405 | [101405] Zebra 5095 High Performance B | FrontierPC |  | 1 |  | 0 | 25 | 25 |  | ∞ | 0 | 0 |  |  |  |  | P01747 (CAD) |  | ✅ Sufficient
101520 | [101520] 2.5 x 4 in. polyester Label r | The ZPS Store |  | 0 |  | 0 | 6 | 6 |  | ∞ | 0 | 0 |  |  |  |  | P01610 (CAD) |  | ⚠ CHECK LEAD TIME — ✅ Sufficient
101532 | [101532] PCBA TFC100 NB-SBC | SMT Hautes Technolog | 101532 | 70 |  | 97 | 1404 | 1501 | 201 | 7.5 | 603 | 1407 |  |  |  |  | P01746 (USD) |  | ✅ Sufficient
101641 | [101641] 2 x 1 in Zebra label roll | Barcodes Inc. |  | 1 |  | 0 | 2 | 2 |  | ∞ | 0 | 0 |  |  |  |  | P01747 (CAD) |  | ✅ Sufficient
101667 | [101667] tf C2 Top Shell | ICO Mold LLC |  | 42 |  | 212 | 500 | 712 | 65 | 11 | 195 | 455 |  |  |  |  | P01826 (USD) |  | ✅ Sufficient
101677 | [101677] tf C2 Main Board PCBA | SMT Hautes Technolog |  | 180 |  | 273 | 772 | 1045 | 85 | 12.3 | 255 | 595 |  |  |  |  | P01894 (USD) |  | ✅ Sufficient
101678 | [101678] tf C2 Button Board PCBA | SMT Hautes Technolog |  | 180 |  | 582 | 743 | 1325 | 170 | 7.8 | 510 | 1190 |  |  |  |  | P01816 (USD) |  | ✅ Sufficient
101679 | [101679] tf C2 USB Board PCBA | SMT Hautes Technolog |  | 0 |  | 278 | 799 | 1077 | 85 | 12.7 | 255 | 595 |  |  |  |  | P01816 (USD) |  | ⚠ CHECK LEAD TIME — ✅ Sufficient
101687 | [101687] tf C2 Sensor Board PCBA | SMT Hautes Technolog |  | 180 |  | 327 | 789 | 1116 | 85 | 13.1 | 255 | 595 |  |  |  |  | P01816 (USD) |  | ✅ Sufficient
101701 | [101701] tf C2 Pneumotach chamber Fron | ICO Mold LLC, Brian |  | 42 |  | 213 | 250 | 463 | 60 | 7.7 | 180 | 420 |  |  |  |  | P01826 (USD) |  | ✅ Sufficient
101708 | [101708] Thermal fuse/switch 55C | SEKI |  | 28 |  | 741 | 0 | 741 | 85 | 8.7 | 255 | 595 |  |  |  |  | P00390 (USD) |  | ✅ Sufficient
101715 | [101715] Thermal switch mouting bracke | SEKI |  | 14 |  | 784 | 0 | 784 | 85 | 9.2 | 255 | 595 |  |  |  |  | P00390 (USD) |  | ✅ Sufficient
102152 | [102152] tf C2 Pneumotach chamber Fron | Xometry |  | 1 |  | 53 | 205 | 258 | 25 | 10.3 | 75 | 175 |  |  |  |  | P01814 (USD) |  | ✅ Sufficient

## 🏭 By Supplier
Component PO Plan — Grouped by Supplier
Rate: 101336×150 101759×25 101760×25 101711×40 101769×20 102237×5 101490×1 102240×20 101059×150 100986×150 102036×100 101557×200 /mo ¦ Target: 7mo ¦ Reorder at: 3mo ¦ Generated: 2026-03-02 22:24 UTC
Ref | Component Name | Supplier | Sup Code | Lead Days | Min Qty | Stock Avail | Open Incoming | Total Avail | Monthly Req | Coverage Now(mo) | Reorder Point | Target Qty(7mo) | ORDER QTY | Coverage After | Latest Safe Order Date | Buffer (days) | Price Source | Est Value (USD) | Status
🏭 ICO Mold LLC — 28 parts ¦ 24 to order ¦ Est. $48,352
101744 | [101744] tf C-100 HHU LOOVER PLATE - V | ICO Mold LLC |  | 42 |  | 63 | 0 | 63 | 50 | 1.3 | 150 | 350 | 300 | 7.3 | 2026-03-02 | -3 | P01432 (USD) | 3744 | 🔴 CRITICAL — stock out in 38d, lead 42d — ORDER TODAY
101745 | [101745] tf C-100 HHU FRONT CAP - Vita | ICO Mold LLC |  | 42 |  | 61 | 0 | 61 | 50 | 1.2 | 150 | 350 | 300 | 7.2 | 2026-03-02 | -4 | P01432 (USD) | 3780 | 🔴 CRITICAL — stock out in 37d, lead 42d — ORDER TODAY
101746 | [101746] tf C-100 HHU_NAME PLATE - Vit | ICO Mold LLC |  | 42 |  | 54 | 0 | 54 | 50 | 1.1 | 150 | 350 | 300 | 7.1 | 2026-03-02 | -9 | P01432 (USD) | 3744 | 🔴 CRITICAL — stock out in 32d, lead 42d — ORDER TODAY
101747 | [101747] tf C-100 CCU Enclosure Holder | ICO Mold LLC |  | 42 |  | 61 | 0 | 61 | 50 | 1.2 | 150 | 350 | 300 | 7.2 | 2026-03-02 | -4 | P01432 (USD) | 4290 | 🔴 CRITICAL — stock out in 37d, lead 42d — ORDER TODAY
101748 | [101748] tf C-100 CCU Enclosure front | ICO Mold LLC |  | 42 |  | 62 | 0 | 62 | 50 | 1.2 | 150 | 350 | 300 | 7.2 | 2026-03-02 | -4 | P01432 (USD) | 5778 | 🔴 CRITICAL — stock out in 37d, lead 42d — ORDER TODAY
101749 | [101749] tf C-100 HHU BACK SHELL - Vit | ICO Mold LLC |  | 42 |  | 59 | 0 | 59 | 50 | 1.2 | 150 | 350 | 300 | 7.2 | 2026-03-02 | -6 | P01432 (USD) | 7044 | 🔴 CRITICAL — stock out in 35d, lead 42d — ORDER TODAY
101750 | [101750] tf C-100 CCU Enclosure Top - | ICO Mold LLC |  | 42 |  | 162 | 0 | 162 | 50 | 3.2 | 150 | 350 | 200 | 7.2 | 2026-04-27 | 56 | P01432 (USD) | 4448 | 🟢 Order by 2026-04-27 — 56d buffer (lead 42d)
101681 | [101681] tf C2 Sensor Module Cover | ICO Mold LLC |  | 42 |  | 380 | 0 | 380 | 85 | 4.5 | 255 | 595 | 250 | 7.4 | 2026-06-04 | 94 | P00741 (USD) | 290 | 🟢 Order by 2026-06-04 — 94d buffer (lead 42d)
101671 | [101671] tf C2 Shoe Mount Cover | ICO Mold LLC |  | 42 |  | 403 | 0 | 403 | 85 | 4.7 | 255 | 595 | 200 | 7.1 | 2026-06-12 | 102 | P00741 (USD) | 244 | 🟢 Order by 2026-06-12 — 102d buffer (lead 42d)
100790 | [100790] tF C-100 HHU_STRAIN RELIEF In | ICO Mold LLC | 030-100790-00 | 42 |  | 383 | 1700 | 2083 | 402 | 5.2 | 1206 | 2814 | 750 | 7 | 2026-06-25 | 115 | P01844 (USD) | 832.5 | 🟢 Order by 2026-06-25 — 115d buffer (lead 42d)
102242 | [102242] tf C2 Top Shell - VTG | ICO Mold LLC |  | 42 |  | 52 | 58 | 110 | 20 | 5.5 | 60 | 140 | 50 | 8 | 2026-07-05 | 125 | P01865 (USD) | 1545 | 🟢 Order by 2026-07-05 — 125d buffer (lead 42d)
102243 | [102243] tf C2 Front Cap – VTG | ICO Mold LLC |  | 42 |  | 52 | 58 | 110 | 20 | 5.5 | 60 | 140 | 50 | 8 | 2026-07-05 | 125 | P01865 (USD) | 1450 | 🟢 Order by 2026-07-05 — 125d buffer (lead 42d)
102244 | [102244] tf C2 USB-C Cap – VTG | ICO Mold LLC |  | 42 |  | 55 | 55 | 110 | 20 | 5.5 | 60 | 140 | 50 | 8 | 2026-07-05 | 125 | P01865 (USD) | 1050 | 🟢 Order by 2026-07-05 — 125d buffer (lead 42d)
100783 | [100783] tF C-100 HHU_LENS LIGHT PIPE | ICO Mold LLC | 100783 | 42 |  | 714 | 400 | 1114 | 201 | 5.5 | 603 | 1407 | 300 | 7 | 2026-07-06 | 126 | P01844 (USD) | 774 | 🟢 Order by 2026-07-06 — 126d buffer (lead 42d)
100794 | [100794] tF C-100 CCU Enclosure Holder | ICO Mold LLC | 030-100794-00 | 42 |  | 410 | 464 | 874 | 151 | 5.8 | 453 | 1057 | 200 | 7.1 | 2026-07-14 | 134 | P01844 (USD) | 814 | 🟢 Order by 2026-07-14 — 134d buffer (lead 42d)
100793 | [100793] tF C-100 CCU Enclosure Top In | ICO Mold LLC | 030-100793-00 | 42 |  | 493 | 400 | 893 | 151 | 5.9 | 453 | 1057 | 200 | 7.2 | 2026-07-18 | 138 | P01844 (USD) | 2888 | 🟢 Order by 2026-07-18 — 138d buffer (lead 42d)
100797 | [100797] tF C-100 CCU Enclosure Interf | ICO Mold LLC | 100797 | 42 |  | 511 | 700 | 1211 | 201 | 6 | 603 | 1407 | 200 | 7 | 2026-07-21 | 141 | P01844 (USD) | 284 | 🟢 Order by 2026-07-21 — 141d buffer (lead 42d)
100785 | [100785] tF C-100 HHU_LEFT BUTTON Inj. | ICO Mold LLC | 030-100785-00 | 42 |  | 521 | 700 | 1221 | 201 | 6.1 | 603 | 1407 | 200 | 7.1 | 2026-07-22 | 142 | P01844 (USD) | 222 | 🟢 Order by 2026-07-22 — 142d buffer (lead 42d)
100786 | [100786] tF C100 HHU RIGHT BUTTON Inj. | ICO Mold LLC | 030-100786-00 | 42 |  | 543 | 700 | 1243 | 201 | 6.2 | 603 | 1407 | 200 | 7.2 | 2026-07-26 | 146 | P01844 (USD) | 222 | 🟢 Order by 2026-07-26 — 146d buffer (lead 42d)
100795 | [100795] tF C-100 CCU Enclosure BOTTOM | ICO Mold LLC | 030-100795-00 | 42 |  | 153 | 1100 | 1253 | 201 | 6.2 | 603 | 1407 | 200 | 7.2 | 2026-07-27 | 147 | P01844 (USD) | 1428 | 🟢 Order by 2026-07-27 — 147d buffer (lead 42d)
100781 | [100781] tF C-100 HHU Front Shell Inj. | ICO Mold LLC | 030-100781-00 | 42 |  | 197 | 1100 | 1297 | 201 | 6.5 | 603 | 1407 | 150 | 7.2 | 2026-08-03 | 154 | P01844 (USD) | 1575 | 🟢 Order by 2026-08-03 — 154d buffer (lead 42d)
100782 | [100782] tF C-100 HHU BACK SHELL Inj. | ICO Mold LLC | 030-100782-00 | 42 |  | 578 | 400 | 978 | 151 | 6.5 | 453 | 1057 | 100 | 7.1 | 2026-08-04 | 155 | P01844 (USD) | 1717 | 🟢 Order by 2026-08-04 — 155d buffer (lead 42d)
100784 | [100784] tF C-100 HHU_LOOVER REAR PLAT | ICO Mold LLC | 030-100784-00 | 42 |  | 650 | 400 | 1050 | 151 | 7 | 453 | 1057 | 50 | 7.3 | 2026-08-18 | 169 | P01844 (USD) | 96 | 🟢 Order by 2026-08-18 — 169d buffer (lead 42d)
100791 | [100791] tF C-100 HHU_NAME PLATE Inj. | ICO Mold LLC | 030-100791-00 | 42 |  | 653 | 400 | 1053 | 151 | 7 | 453 | 1057 | 50 | 7.3 | 2026-08-19 | 170 | P01844 (USD) | 93 | 🟢 Order by 2026-08-19 — 170d buffer (lead 42d)
100789 | [100789] tF C-100 HHU_FRONT CAP Inj. | ICO Mold LLC | 030-100789-00 | 42 |  | 702 | 400 | 1102 | 151 | 7.3 | 453 | 1057 |  |  |  |  | P01844 (USD) |  | ✅ Sufficient
100792 | [100792] tF C-100 CCU Enclosure front | ICO Mold LLC | 030-100792-00 | 42 |  | 196 | 1100 | 1296 | 151 | 8.6 | 453 | 1057 |  |  |  |  | P01844 (USD) |  | ✅ Sufficient
100796 | [100796] tF C-100 CCU Enclosure Power | ICO Mold LLC | 030-100796-00 | 42 |  | 1943 | 700 | 2643 | 201 | 13.1 | 603 | 1407 |  |  |  |  | P01844 (USD) |  | ✅ Sufficient
101667 | [101667] tf C2 Top Shell | ICO Mold LLC |  | 42 |  | 212 | 500 | 712 | 65 | 11 | 195 | 455 |  |  |  |  | P01826 (USD) |  | ✅ Sufficient
🏭 ULINE, Sales ULINE — 1 parts ¦ 1 to order ¦ Est. $0
102020 | [102020] Wafer Seal Sticker 1.5in | ULINE, Sales ULINE |  | 1 |  | 0 | 0 | 0 | 200 | 0 | 600 | 1400 | 1400 | 7 | 2026-03-02 | -1 | pricelist |  | 🔴 CRITICAL — stock out in 0d, lead 1d — ORDER TODAY
🏭 Alloy Concepts — 19 parts ¦ 18 to order ¦ Est. $231,386
100978 | [100978] tF C100 PFT Filter Interface | Alloy Concepts |  | 56 |  | 0 | 2 | 2 | 1 | 2 | 3 | 7 | 50 | 52 | 2026-03-06 | 4 | P01883 (CAD) | 4123.3 | 🟠 Order NOW — only 4d buffer
101719 | [101719] tf C2 Piston CNC | Alloy Concepts |  | 56 |  | 248 | 5 | 253 | 85 | 3 | 255 | 595 | 350 | 7.1 | 2026-04-05 | 34 | P01635 (USD) | 20461 | 🟡 Order by 2026-04-05 — 34d buffer (lead 56d)
101104 | [101104] Test Load Assy | Alloy Concepts |  | 60 |  | 153 | 450 | 603 | 150 | 4 | 450 | 1050 | 450 | 7 | 2026-05-03 | 62 | P01745 (CAD) | 22763.88 | 🟢 Order by 2026-05-03 — 62d buffer (lead 60d)
100348 | [100348] TremoFlo C-100 Motor Piston M | Alloy Concepts | 100348 | 56 |  | 136 | 750 | 886 | 201 | 4.4 | 603 | 1407 | 550 | 7.1 | 2026-05-19 | 78 | P01745 (CAD) | 12707.81 | 🟢 Order by 2026-05-19 — 78d buffer (lead 56d)
100326 | [100326] TremoFlo C-100 Motor Piston O | Alloy Concepts | 100326 | 56 |  | 234 | 750 | 984 | 201 | 4.9 | 603 | 1407 | 450 | 7.1 | 2026-06-03 | 93 | P01745 (CAD) | 3869.28 | 🟢 Order by 2026-06-03 — 93d buffer (lead 56d)
101541 | [101541] tF C-100 Pneumotach Heater Ri | Alloy Concepts | 101541 | 56 |  | 249 | 750 | 999 | 201 | 5 | 603 | 1407 | 450 | 7.2 | 2026-06-05 | 95 | P01745 (CAD) | 14860.35 | 🟢 Order by 2026-06-05 — 95d buffer (lead 56d)
100318 | [100318] TremoFlo C-100 Motor Bobbin | Alloy Concepts | 100318 | 56 |  | 111 | 900 | 1011 | 201 | 5 | 603 | 1407 | 400 | 7 | 2026-06-07 | 97 | P01745 (CAD) | 48045.76 | 🟢 Order by 2026-06-07 — 97d buffer (lead 56d)
101540 | [101540] tF C-100 Pneumotach Main Body | Alloy Concepts | 101540 | 56 |  | 118 | 928 | 1046 | 201 | 5.2 | 603 | 1407 | 400 | 7.2 | 2026-06-12 | 102 | P01745 (CAD) | 25682.44 | 🟢 Order by 2026-06-12 — 102d buffer (lead 56d)
101680 | [101680] tf C2 Motor Rod | Alloy Concepts |  | 63 |  | 534 | 400 | 934 | 170 | 5.5 | 510 | 1190 | 300 | 7.3 | 2026-06-14 | 104 | P01381 (CAD) | 3208.47 | 🟢 Order by 2026-06-14 — 104d buffer (lead 63d)
100975 | [100975] tF C100 Pneumotach Inner Mesh | Alloy Concepts | 100975 | 56 |  | 169 | 900 | 1069 | 201 | 5.3 | 603 | 1407 | 350 | 7.1 | 2026-06-15 | 105 | P01745 (CAD) | 5680.25 | 🟢 Order by 2026-06-15 — 105d buffer (lead 56d)
100977 | [100977] tF C100 Pneumotach Knob | Alloy Concepts | 100977 | 56 |  | 450 | 634 | 1084 | 201 | 5.4 | 603 | 1407 | 350 | 7.1 | 2026-06-18 | 108 | P01745 (CAD) | 7725.03 | 🟢 Order by 2026-06-18 — 108d buffer (lead 56d)
100321 | [100321] TremoFlo C-100 Motor Shaft | Alloy Concepts |  | 56 |  | 576 | 1611 | 2187 | 402 | 5.4 | 1206 | 2814 | 650 | 7.1 | 2026-06-19 | 109 | P01745 (CAD) | 6494.28 | 🟢 Order by 2026-06-19 — 109d buffer (lead 56d)
100976 | [100976] tF C100 Pneumotach Outer Mesh | Alloy Concepts | 100976 | 56 |  | 197 | 900 | 1097 | 201 | 5.5 | 603 | 1407 | 350 | 7.2 | 2026-06-20 | 110 | P01745 (CAD) | 7314.55 | 🟢 Order by 2026-06-20 — 110d buffer (lead 56d)
101255 | [101255] tF C-100 Light Motor Back Pla | Alloy Concepts | 101255 | 56 |  | 457 | 696 | 1153 | 201 | 5.7 | 603 | 1407 | 300 | 7.2 | 2026-06-28 | 118 | P01745 (CAD) | 12130.2 | 🟢 Order by 2026-06-28 — 118d buffer (lead 56d)
100328 | [100328] TremoFlo C-100 Motor Piston I | Alloy Concepts | 100328 | 56 |  | 379 | 842 | 1221 | 201 | 6.1 | 603 | 1407 | 200 | 7.1 | 2026-07-08 | 128 | P01745 (CAD) | 1508.58 | 🟢 Order by 2026-07-08 — 128d buffer (lead 56d)
100322 | [100322] TremoFlo C-100 Hall Sensor Br | Alloy Concepts | 100322 | 56 |  | 765 | 475 | 1240 | 201 | 6.2 | 603 | 1407 | 200 | 7.2 | 2026-07-11 | 131 | P01745 (CAD) | 3605.04 | 🟢 Order by 2026-07-11 — 131d buffer (lead 56d)
101254 | [101254] tF C-100 Light Piston | Alloy Concepts |  | 56 |  | 245 | 1005 | 1250 | 201 | 6.2 | 603 | 1407 | 200 | 7.2 | 2026-07-13 | 133 | P01745 (CAD) | 18761.18 | 🟢 Order by 2026-07-13 — 133d buffer (lead 56d)
102114 | [102114] Test Load Assy for Reference | Alloy Concepts |  | 1 |  | 380 | 450 | 830 | 150 | 5.5 | 450 | 1050 | 250 | 7.2 | 2026-08-16 | 167 | P01745 (CAD) | 12445.02 | 🟢 Order by 2026-08-16 — 167d buffer (lead 1d)
101385 | [101385] tF C-100 PFT Filter Interface | Alloy Concepts | 101385 | 56 |  | 357 | 800 | 1157 | 150 | 7.7 | 450 | 1050 |  |  |  |  | P01745 (CAD) |  | ✅ Sufficient
🏭 Custom Sheet Metal Products (CSTM) — 2 parts ¦ 2 to order ¦ Est. $75,042
100359 | [100359] TremoFlo C-100 CU Metal Enclo | Custom Sheet Metal P | 100359 | 70 |  | 226 | 300 | 526 | 201 | 2.6 | 603 | 1407 | 900 | 7.1 | 2026-03-11 | 9 | P01840 (CAD) | 74687.76 | 🟠 Order NOW — only 9d buffer
101706 | [101706] tf C2 - Exhaust Mesh Frame | Custom Sheet Metal P |  | 70 |  | 337 | 0 | 337 | 85 | 4 | 255 | 595 | 300 | 7.5 | 2026-04-21 | 50 | P00754 (CAD) | 354.06 | 🟢 Order by 2026-04-21 — 50d buffer (lead 70d)
🏭 Atlas Gaskets — 4 parts ¦ 4 to order ¦ Est. $5,781
101683 | [101683] tf C2 - Pneumotach Mesh | Atlas Gaskets |  | 28 |  | 143 | 0 | 143 | 85 | 1.7 | 255 | 595 | 500 | 7.6 | 2026-03-25 | 23 | P01559 (USD) | 4725 | 🟡 Order by 2026-03-25 — 23d buffer (lead 28d)
101675 | [101675] tf C2 - Battery Strap | Atlas Gaskets |  | 28 |  | 256 | 0 | 256 | 85 | 3 | 255 | 595 | 350 | 7.1 | 2026-05-04 | 63 | P00729 (USD) | 605.5 | 🟢 Order by 2026-05-04 — 63d buffer (lead 28d)
101682 | [101682] tf C2 - Sensor Module Foam Ga | Atlas Gaskets |  | 28 |  | 298 | 0 | 298 | 85 | 3.5 | 255 | 595 | 300 | 7 | 2026-05-19 | 78 | P00729 (USD) | 177 | 🟢 Order by 2026-05-19 — 78d buffer (lead 28d)
101707 | [101707] tf C2 - Exhaust Mesh Standard | Atlas Gaskets |  | 28 |  | 567 | 0 | 567 | 85 | 6.7 | 255 | 595 | 50 | 7.3 | 2026-08-24 | 175 | P01559 (USD) | 273.5 | 🟢 Order by 2026-08-24 — 175d buffer (lead 28d)
🏭 Atlas Gaskets, Rebecca Lopez — 1 parts ¦ 1 to order ¦ Est. $80
101699 | [101699] tf C2 - Pneumotach Neck Foam | Atlas Gaskets, Rebec |  | 50 |  | 204 | 0 | 204 | 85 | 2.4 | 255 | 595 | 400 | 7.1 | 2026-03-25 | 23 | P00729 (USD) | 80 | 🟡 Order by 2026-03-25 — 23d buffer (lead 50d)
🏭 Globtek Inc. — 2 parts ¦ 2 to order ¦ Est. $6,132
101694 | [101694] USB Cable Type C to A - 2 Fe | Globtek Inc. |  | 1 |  | 91 | 0 | 91 | 100 | 0.9 | 300 | 700 | 650 | 7.4 | 2026-03-28 | 26 | P00730 (USD) | 5486 | 🟡 Order by 2026-03-28 — 26d buffer (lead 1d)
101663 | [101663] tf C2 Power Supply | Globtek Inc. |  | 0 |  | 659 | 0 | 659 | 100 | 6.6 | 300 | 700 | 50 | 7.1 | 2026-09-18 | 200 | P00730 (USD) | 645.5 | ⚠ CHECK LEAD TIME — 🟢 Order by 2026-09-18 — 200d buffer (lead 0d)
🏭 Alloy Concepts, Perry MacIssaac — 1 parts ¦ 1 to order ¦ Est. $38,192
101718 | [101718] tf C2 - Main Body CNC | Alloy Concepts, Perr |  | 56 |  | 228 | 5 | 233 | 85 | 2.7 | 255 | 595 | 400 | 7.4 | 2026-03-29 | 27 | P01635 (USD) | 38192 | 🟡 Order by 2026-03-29 — 27d buffer (lead 56d)
🏭 GEB General Electronics Battery Co. Ltd — 1 parts ¦ 1 to order ¦ Est. $1,872
101658 | [101658] tf C2 Battery Pack | GEB General Electro |  | 42 |  | 79 | 200 | 279 | 85 | 3.3 | 255 | 595 | 350 | 7.4 | 2026-04-28 | 57 | P01790 (USD) | 1872.5 | 🟢 Order by 2026-04-28 — 57d buffer (lead 42d)
🏭 Graphiscan — 1 parts ¦ 1 to order ¦ Est. $911
102128 | [102128] C2 USB Power Supply Box Sleev | Graphiscan |  | 0 |  | 197 | 0 | 197 | 100 | 2 | 300 | 700 | 550 | 7.5 | 2026-04-30 | 59 | P01554 (CAD) | 911.13 | ⚠ CHECK LEAD TIME — 🟢 Order by 2026-04-30 — 59d buffer (lead 0d)
🏭 Moticont — 1 parts ¦ 1 to order ¦ Est. $234,773
101278 | [101278] tf C100 Motor Assembly VCA | Moticont | LVCM-016-019-01 | 28 |  | 531 | 400 | 931 | 286 | 3.3 | 858 | 2002 | 1100 | 7.1 | 2026-05-12 | 71 | P01885 (USD) | 234773 | 🟢 Order by 2026-05-12 — 71d buffer (lead 28d)
🏭 Net Burner — 1 parts ¦ 1 to order ¦ Est. $95,200
100159 | [100159] NetBurner Ethernet Core Modul | Net Burner | MOD5234-200IR | 21 |  | 323 | 300 | 623 | 201 | 3.1 | 603 | 1407 | 800 | 7.1 | 2026-05-14 | 73 | P01841 (USD) | 95200 | 🟢 Order by 2026-05-14 — 73d buffer (lead 21d)
🏭 Xometry, Ethan Beum — 1 parts ¦ 1 to order ¦ Est. $11,391
101755 | [101755] tf C-100 Filter interface Vit | Xometry, Ethan Beum |  | 1 |  | 125 | 0 | 125 | 50 | 2.5 | 150 | 350 | 250 | 7.5 | 2026-05-16 | 75 | P01405 (CAD) | 11391.3 | 🟢 Order by 2026-05-16 — 75d buffer (lead 1d)
🏭 OSD Displays — 1 parts ¦ 1 to order ¦ Est. $5,760
101672 | [101672] tf C2 - Custom Display Assemb | OSD Displays |  | 60 |  | 298 | 0 | 298 | 65 | 4.6 | 195 | 455 | 200 | 7.7 | 2026-05-20 | 79 | P00326 (USD) | 5760 | 🟢 Order by 2026-05-20 — 79d buffer (lead 60d)
🏭 SMT Hautes Technologies — 11 parts ¦ 3 to order ¦ Est. $31,760
101106 | [101106] TremoFlo C100 Custom made cab | SMT Hautes Technolog | 101106 | 112 |  | 278 | 1002 | 1280 | 201 | 6.4 | 603 | 1407 | 150 | 7.1 | 2026-05-22 | 81 | P01838 (CAD) | 8519.28 | 🟢 Order by 2026-05-22 — 81d buffer (lead 112d)
100481 | [100481] TremoFlo C-100 Handheld Ring | SMT Hautes Technolog |  | 119 |  | 87 | 1299 | 1386 | 201 | 6.9 | 603 | 1407 | 50 | 7.1 | 2026-05-31 | 90 | P01746 (USD) | 4696 | 🟢 Order by 2026-05-31 — 90d buffer (lead 119d)
101535 | [101535] PCBA tF C-100 Connector Board | SMT Hautes Technolog | 101535 | 70 |  | 44 | 1265 | 1309 | 201 | 6.5 | 603 | 1407 | 100 | 7 | 2026-07-08 | 128 | P01746 (USD) | 18545 | 🟢 Order by 2026-07-08 — 128d buffer (lead 70d)
100477 | [100477] tremoFlo C-100 Mezzanine PCBA | SMT Hautes Technolog | 100477 | 70 |  | 79 | 1340 | 1419 | 201 | 7.1 | 603 | 1407 |  |  |  |  | P01746 (USD) |  | ✅ Sufficient
100479 | [100479] TremoFlo C-100 Handheld Main | SMT Hautes Technolog |  | 119 |  | 61 | 1438 | 1499 | 201 | 7.5 | 603 | 1407 |  |  |  |  | P01746 (USD) |  | ✅ Sufficient
100480 | [100480] TremoFlo C-100 Handheld Posit | SMT Hautes Technolog |  | 119 |  | 175 | 1481 | 1656 | 201 | 8.2 | 603 | 1407 |  |  |  |  | P01746 (USD) |  | ✅ Sufficient
101532 | [101532] PCBA TFC100 NB-SBC | SMT Hautes Technolog | 101532 | 70 |  | 97 | 1404 | 1501 | 201 | 7.5 | 603 | 1407 |  |  |  |  | P01746 (USD) |  | ✅ Sufficient
101677 | [101677] tf C2 Main Board PCBA | SMT Hautes Technolog |  | 180 |  | 273 | 772 | 1045 | 85 | 12.3 | 255 | 595 |  |  |  |  | P01894 (USD) |  | ✅ Sufficient
101678 | [101678] tf C2 Button Board PCBA | SMT Hautes Technolog |  | 180 |  | 582 | 743 | 1325 | 170 | 7.8 | 510 | 1190 |  |  |  |  | P01816 (USD) |  | ✅ Sufficient
101679 | [101679] tf C2 USB Board PCBA | SMT Hautes Technolog |  | 0 |  | 278 | 799 | 1077 | 85 | 12.7 | 255 | 595 |  |  |  |  | P01816 (USD) |  | ⚠ CHECK LEAD TIME — ✅ Sufficient
101687 | [101687] tf C2 Sensor Board PCBA | SMT Hautes Technolog |  | 180 |  | 327 | 789 | 1116 | 85 | 13.1 | 255 | 595 |  |  |  |  | P01816 (USD) |  | ✅ Sufficient
🏭 TWP — 1 parts ¦ 1 to order ¦ Est. $1,282
101979 | [101979] Test Load Mesh 165X1400 | TWP |  | 0 |  | 407 | 0 | 407 | 150 | 2.7 | 450 | 1050 | 650 | 7 | 2026-05-23 | 82 | P01854 (CAD) | 1281.73 | ⚠ CHECK LEAD TIME — 🟢 Order by 2026-05-23 — 82d buffer (lead 0d)
🏭 ICO Mold LLC, Brian Bay — 6 parts ¦ 5 to order ¦ Est. $1,884
101685 | [101685] tf C2 Pneumotach Main Part | ICO Mold LLC, Brian |  | 42 |  | 352 | 0 | 352 | 85 | 4.1 | 255 | 595 | 250 | 7.1 | 2026-05-25 | 84 | P00741 (USD) | 315 | 🟢 Order by 2026-05-25 — 84d buffer (lead 42d)
101669 | [101669] tf C2 USB-C Cap | ICO Mold LLC, Brian |  | 42 |  | 345 | 0 | 345 | 65 | 5.3 | 195 | 455 | 150 | 7.6 | 2026-06-29 | 119 | P00741 (USD) | 307.5 | 🟢 Order by 2026-06-29 — 119d buffer (lead 42d)
101670 | [101670] tf C2 Front Cap | ICO Mold LLC, Brian |  | 42 |  | 356 | 0 | 356 | 65 | 5.5 | 195 | 455 | 100 | 7 | 2026-07-04 | 124 | P00741 (USD) | 155 | 🟢 Order by 2026-07-04 — 124d buffer (lead 42d)
101700 | [101700] tf C2 Pneumotach chamber Back | ICO Mold LLC, Brian |  | 42 |  | 283 | 250 | 533 | 85 | 6.3 | 255 | 595 | 100 | 7.4 | 2026-07-28 | 148 | P01826 (USD) | 523 | 🟢 Order by 2026-07-28 — 148d buffer (lead 42d)
101668 | [101668] tf C2 Bottom Shell | ICO Mold LLC, Brian |  | 42 |  | 569 | 0 | 569 | 85 | 6.7 | 255 | 595 | 50 | 7.3 | 2026-08-10 | 161 | P01148 (USD) | 583 | 🟢 Order by 2026-08-10 — 161d buffer (lead 42d)
101701 | [101701] tf C2 Pneumotach chamber Fron | ICO Mold LLC, Brian |  | 42 |  | 213 | 250 | 463 | 60 | 7.7 | 180 | 420 |  |  |  |  | P01826 (USD) |  | ✅ Sufficient
🏭 Minco — 1 parts ¦ 1 to order ¦ Est. $16,140
100346 | [100346] TremoFlo C-100 Pneumotach RTD | Minco | S100725PFYT24B | 42 |  | 443 | 400 | 843 | 201 | 4.2 | 603 | 1407 | 600 | 7.2 | 2026-05-26 | 85 | P01886 (USD) | 16140 | 🟢 Order by 2026-05-26 — 85d buffer (lead 42d)
🏭 NEL Technologies — 1 parts ¦ 1 to order ¦ Est. $14,278
100345 | [100345] TremoFlo C-100 Pneumotach Hea | NEL Technologies | NEL-2018-1743-HA | 42 |  | 490 | 400 | 890 | 201 | 4.4 | 603 | 1407 | 550 | 7.2 | 2026-06-02 | 92 | P01886 (USD) | 14278 | 🟢 Order by 2026-06-02 — 92d buffer (lead 42d)
🏭 E-Sonic — 2 parts ¦ 2 to order ¦ Est. $11,310
100866 | [100866] THERMOSTAT 50 DEG NC TO-220 A | E-Sonic | 67L050 | 14 |  | 337 | 400 | 737 | 201 | 3.7 | 603 | 1407 | 700 | 7.1 | 2026-06-07 | 97 | P01595 (CAD) | 5105.59 | 🟢 Order by 2026-06-07 — 97d buffer (lead 14d)
101393 | [101393] MOTOR THERMAL SWITCH [O53GAB1 | E-Sonic | O53GAB140A-125Y | 14 |  | 620 | 400 | 1020 | 201 | 5.1 | 603 | 1407 | 400 | 7.1 | 2026-07-20 | 140 | P01873 (CAD) | 6204.36 | 🟢 Order by 2026-07-20 — 140d buffer (lead 14d)
🏭 Lovepac — 1 parts ¦ 1 to order ¦ Est. $4,896
101609 | [101609] Reference Load Shipper box wi | Lovepac |  | 0 |  | 206 | 960 | 1166 | 300 | 3.9 | 900 | 2100 | 950 | 7.1 | 2026-06-28 | 118 | P01871 (CAD) | 4895.54 | ⚠ CHECK LEAD TIME — 🟢 Order by 2026-06-28 — 118d buffer (lead 0d)
🏭 OSD Displays, Christopher Geisler — 1 parts ¦ 1 to order ¦ Est. $2,500
102245 | [102245] tf C2 Custom Display Assembly | OSD Displays, Christ |  | 1 |  | 0 | 100 | 100 | 20 | 5 | 60 | 140 | 50 | 7.5 | 2026-07-31 | 151 | P01866 (USD) | 2500 | 🟢 Order by 2026-07-31 — 151d buffer (lead 1d)
🏭 Bogen Magnetics GmbH Magnetics — 1 parts ¦ 1 to order ¦ Est. $1,215
101498 | [101498] Magnetic strip 24mm | Bogen Magnetics GmbH |  | 1 |  | 1756 | 0 | 1756 | 286 | 6.1 | 858 | 2002 | 250 | 7 | 2026-09-03 | 185 | P01674 (USD) | 1215 | 🟢 Order by 2026-09-03 — 185d buffer (lead 1d)
🏭 FrontierPC — 1 parts ¦ 0 to order ¦ Est. $0
101405 | [101405] Zebra 5095 High Performance B | FrontierPC |  | 1 |  | 0 | 25 | 25 |  | ∞ | 0 | 0 |  |  |  |  | P01747 (CAD) |  | ✅ Sufficient
🏭 The ZPS Store — 1 parts ¦ 0 to order ¦ Est. $0
101520 | [101520] 2.5 x 4 in. polyester Label r | The ZPS Store |  | 0 |  | 0 | 6 | 6 |  | ∞ | 0 | 0 |  |  |  |  | P01610 (CAD) |  | ⚠ CHECK LEAD TIME — ✅ Sufficient
🏭 Barcodes Inc. — 1 parts ¦ 0 to order ¦ Est. $0
101641 | [101641] 2 x 1 in Zebra label roll | Barcodes Inc. |  | 1 |  | 0 | 2 | 2 |  | ∞ | 0 | 0 |  |  |  |  | P01747 (CAD) |  | ✅ Sufficient
🏭 SEKI — 2 parts ¦ 0 to order ¦ Est. $0
101708 | [101708] Thermal fuse/switch 55C | SEKI |  | 28 |  | 741 | 0 | 741 | 85 | 8.7 | 255 | 595 |  |  |  |  | P00390 (USD) |  | ✅ Sufficient
101715 | [101715] Thermal switch mouting bracke | SEKI |  | 14 |  | 784 | 0 | 784 | 85 | 9.2 | 255 | 595 |  |  |  |  | P00390 (USD) |  | ✅ Sufficient
🏭 Xometry — 1 parts ¦ 0 to order ¦ Est. $0
102152 | [102152] tf C2 Pneumotach chamber Fron | Xometry |  | 1 |  | 53 | 205 | 258 | 25 | 10.3 | 75 | 175 |  |  |  |  | P01814 (USD) |  | ✅ Sufficient

## 🔧 Buildable Units
Buildable Units — How Many Devices Can We Build Right Now?
Stock Only = physical stock now ¦ +Incoming = stock + all open PO receipts expected
Ref | Finished Product | Monthly Plan | Max Build (Stock Only) | Months Coverage | Max Build (+Incoming) | Months Coverage | Limiting Component (Stock Only) | Limiting Component (+Incoming)
101336 | tremoFlo C-100 Device ClearFlo compatibl | 150 | 44 | 0.3 mo | 526 | 3.5 mo | 101535 — [101535] PCBA tF C-100 Connector (44 avail / 1.000/unit = 44 units) | 100359 — [100359] TremoFlo C-100 CU Metal (526 avail / 1.000/unit = 526 units)
101711 | tremoflo C2 Device - clearflo | 40 | 79 | 2.0 mo | 143 | 3.6 mo | 101658 — [101658] tf C2 Battery Pack (79 avail / 1.000/unit = 79 units) | 101683 — [101683] tf C2 - Pneumotach Mesh (143 avail / 1.000/unit = 143 units)
101769 | tremoflo C2 Device - Bird - Purple | 20 | 79 | 4.0 mo | 143 | 7.2 mo | 101658 — [101658] tf C2 Battery Pack (79 avail / 1.000/unit = 79 units) | 101683 — [101683] tf C2 - Pneumotach Mesh (143 avail / 1.000/unit = 143 units)
102237 | tF C2 Device - Yellow - VTG 28554 | 5 | 53 | 10.6 mo | 143 | 28.6 mo | 102152 — [102152] tf C2 Pneumotach chambe (53 avail / 1.000/unit = 53 units) | 101683 — [101683] tf C2 - Pneumotach Mesh (143 avail / 1.000/unit = 143 units)
101490 | tremoFlo C-100 Device Suregard compatibl | 1 | 0 | 0.0 mo | 2 | 2.0 mo | 100978 — [100978] tF C100 PFT Filter Inte (0 avail / 1.000/unit = 0 units) | 100978 — [100978] tF C100 PFT Filter Inte (2 avail / 1.000/unit = 2 units)
101759 | tf C-100 Device Vitalograph - 28300 | 25 | 44 | 1.8 mo | 54 | 2.2 mo | 101535 — [101535] PCBA tF C-100 Connector (44 avail / 1.000/unit = 44 units) | 101746 — [101746] tf C-100 HHU_NAME PLATE (54 avail / 1.000/unit = 54 units)
101760 | tf C-100 Device Vitalograph - 28500 | 25 | 44 | 1.8 mo | 54 | 2.2 mo | 101535 — [101535] PCBA tF C-100 Connector (44 avail / 1.000/unit = 44 units) | 101746 — [101746] tf C-100 HHU_NAME PLATE (54 avail / 1.000/unit = 54 units)
102240 | tf C2 Device - Blue - VTG 28554 | 20 | 0 | 0.0 mo | 100 | 5.0 mo | 102245 — [102245] tf C2 Custom Display As (0 avail / 1.000/unit = 0 units) | 102245 — [102245] tf C2 Custom Display As (100 avail / 1.000/unit = 100 units)
101059 | tremoflo C-100 Calibrated Reference Load | 150 | 206 | 1.4 mo | 407 | 2.7 mo | 101609 — [101609] Reference Load Shipper (206 avail / 1.000/unit = 206 units) | 101979 — [101979] Test Load Mesh 165X1400 (407 avail / 1.000/unit = 407 units)
100986 | tremoflo C-100 Calibrated Reference Load | 150 | 153 | 1.0 mo | 603 | 4.0 mo | 101104 — [101104] Test Load Assy (153 avail / 1.000/unit = 153 units) | 101104 — [101104] Test Load Assy (603 avail / 1.000/unit = 603 units)
102036 | tremoflo C2 Airwave Oscillometry System | 100 | 0 | 0.0 mo | 0 | 0.0 mo | 102020 — [102020] Wafer Seal Sticker 1.5i (0 avail / 2.000/unit = 0 units) | 102020 — [102020] Wafer Seal Sticker 1.5i (0 avail / 2.000/unit = 0 units)
101336 — tremoFlo C-100 Device ClearFlo compati ¦ Monthly: 150 ¦ Max buildable (stock): 44 ¦ Max buildable (+incoming): 1309
Ref | Component | Qty/Unit | Stock | Incoming | Total | Build(Stock) | Build(+Inc)
101535 | [101535] PCBA tF C-100 Connector Board | 1 | 44 | 1265 | 1309 | 44 | 1309
100479 | [100479] TremoFlo C-100 Handheld Main | 1 | 61 | 1438 | 1499 | 61 | 1499
100477 | [100477] tremoFlo C-100 Mezzanine PCBA | 1 | 79 | 1340 | 1419 | 79 | 1419
100481 | [100481] TremoFlo C-100 Handheld Ring | 1 | 87 | 1299 | 1386 | 87 | 1386
101532 | [101532] PCBA TFC100 NB-SBC | 1 | 97 | 1404 | 1501 | 97 | 1501
100318 | [100318] TremoFlo C-100 Motor Bobbin | 1 | 111 | 900 | 1011 | 111 | 1011
101540 | [101540] tF C-100 Pneumotach Main Body | 1 | 118 | 928 | 1046 | 118 | 1046
100348 | [100348] TremoFlo C-100 Motor Piston M | 1 | 136 | 750 | 886 | 136 | 886
100795 | [100795] tF C-100 CCU Enclosure BOTTOM | 1 | 153 | 1100 | 1253 | 153 | 1253
100975 | [100975] tF C100 Pneumotach Inner Mesh | 1 | 169 | 900 | 1069 | 169 | 1069
100480 | [100480] TremoFlo C-100 Handheld Posit | 1 | 175 | 1481 | 1656 | 175 | 1656
100790 | [100790] tF C-100 HHU_STRAIN RELIEF In | 2 | 383 | 1700 | 2083 | 191 | 1041
100792 | [100792] tF C-100 CCU Enclosure front | 1 | 196 | 1100 | 1296 | 196 | 1296
100781 | [100781] tF C-100 HHU Front Shell Inj. | 1 | 197 | 1100 | 1297 | 197 | 1297
100976 | [100976] tF C100 Pneumotach Outer Mesh | 1 | 197 | 900 | 1097 | 197 | 1097
101711 — tremoflo C2 Device - clearflo ¦ Monthly: 40 ¦ Max buildable (stock): 79 ¦ Max buildable (+incoming): 279
Ref | Component | Qty/Unit | Stock | Incoming | Total | Build(Stock) | Build(+Inc)
101658 | [101658] tf C2 Battery Pack | 1 | 79 | 200 | 279 | 79 | 279
101683 | [101683] tf C2 - Pneumotach Mesh | 1 | 143 | 0 | 143 | 143 | 143
101699 | [101699] tf C2 - Pneumotach Neck Foam | 1 | 204 | 0 | 204 | 204 | 204
101667 | [101667] tf C2 Top Shell | 1 | 212 | 500 | 712 | 212 | 712
101701 | [101701] tf C2 Pneumotach chamber Fron | 1 | 213 | 250 | 463 | 213 | 463
101718 | [101718] tf C2 - Main Body CNC | 1 | 228 | 5 | 233 | 228 | 233
101719 | [101719] tf C2 Piston CNC | 1 | 248 | 5 | 253 | 248 | 253
101675 | [101675] tf C2 - Battery Strap | 1 | 256 | 0 | 256 | 256 | 256
101680 | [101680] tf C2 Motor Rod | 2 | 534 | 400 | 934 | 267 | 467
101677 | [101677] tf C2 Main Board PCBA | 1 | 273 | 772 | 1045 | 273 | 1045
101679 | [101679] tf C2 USB Board PCBA | 1 | 278 | 799 | 1077 | 278 | 1077
101700 | [101700] tf C2 Pneumotach chamber Back | 1 | 283 | 250 | 533 | 283 | 533
101678 | [101678] tf C2 Button Board PCBA | 2 | 582 | 743 | 1325 | 291 | 662
101672 | [101672] tf C2 - Custom Display Assemb | 1 | 298 | 0 | 298 | 298 | 298
101682 | [101682] tf C2 - Sensor Module Foam Ga | 1 | 298 | 0 | 298 | 298 | 298
101769 — tremoflo C2 Device - Bird - Purple ¦ Monthly: 20 ¦ Max buildable (stock): 79 ¦ Max buildable (+incoming): 279
Ref | Component | Qty/Unit | Stock | Incoming | Total | Build(Stock) | Build(+Inc)
101658 | [101658] tf C2 Battery Pack | 1 | 79 | 200 | 279 | 79 | 279
101683 | [101683] tf C2 - Pneumotach Mesh | 1 | 143 | 0 | 143 | 143 | 143
101699 | [101699] tf C2 - Pneumotach Neck Foam | 1 | 204 | 0 | 204 | 204 | 204
101667 | [101667] tf C2 Top Shell | 1 | 212 | 500 | 712 | 212 | 712
101701 | [101701] tf C2 Pneumotach chamber Fron | 1 | 213 | 250 | 463 | 213 | 463
101718 | [101718] tf C2 - Main Body CNC | 1 | 228 | 5 | 233 | 228 | 233
101719 | [101719] tf C2 Piston CNC | 1 | 248 | 5 | 253 | 248 | 253
101675 | [101675] tf C2 - Battery Strap | 1 | 256 | 0 | 256 | 256 | 256
101680 | [101680] tf C2 Motor Rod | 2 | 534 | 400 | 934 | 267 | 467
101677 | [101677] tf C2 Main Board PCBA | 1 | 273 | 772 | 1045 | 273 | 1045
101679 | [101679] tf C2 USB Board PCBA | 1 | 278 | 799 | 1077 | 278 | 1077
101700 | [101700] tf C2 Pneumotach chamber Back | 1 | 283 | 250 | 533 | 283 | 533
101678 | [101678] tf C2 Button Board PCBA | 2 | 582 | 743 | 1325 | 291 | 662
101672 | [101672] tf C2 - Custom Display Assemb | 1 | 298 | 0 | 298 | 298 | 298
101682 | [101682] tf C2 - Sensor Module Foam Ga | 1 | 298 | 0 | 298 | 298 | 298
102237 — tF C2 Device - Yellow - VTG 28554 ¦ Monthly: 5 ¦ Max buildable (stock): 53 ¦ Max buildable (+incoming): 258
Ref | Component | Qty/Unit | Stock | Incoming | Total | Build(Stock) | Build(+Inc)
102152 | [102152] tf C2 Pneumotach chamber Fron | 1 | 53 | 205 | 258 | 53 | 258
101658 | [101658] tf C2 Battery Pack | 1 | 79 | 200 | 279 | 79 | 279
101683 | [101683] tf C2 - Pneumotach Mesh | 1 | 143 | 0 | 143 | 143 | 143
101699 | [101699] tf C2 - Pneumotach Neck Foam | 1 | 204 | 0 | 204 | 204 | 204
101667 | [101667] tf C2 Top Shell | 1 | 212 | 500 | 712 | 212 | 712
101718 | [101718] tf C2 - Main Body CNC | 1 | 228 | 5 | 233 | 228 | 233
101719 | [101719] tf C2 Piston CNC | 1 | 248 | 5 | 253 | 248 | 253
101675 | [101675] tf C2 - Battery Strap | 1 | 256 | 0 | 256 | 256 | 256
101680 | [101680] tf C2 Motor Rod | 2 | 534 | 400 | 934 | 267 | 467
101677 | [101677] tf C2 Main Board PCBA | 1 | 273 | 772 | 1045 | 273 | 1045
101679 | [101679] tf C2 USB Board PCBA | 1 | 278 | 799 | 1077 | 278 | 1077
101700 | [101700] tf C2 Pneumotach chamber Back | 1 | 283 | 250 | 533 | 283 | 533
101678 | [101678] tf C2 Button Board PCBA | 2 | 582 | 743 | 1325 | 291 | 662
101682 | [101682] tf C2 - Sensor Module Foam Ga | 1 | 298 | 0 | 298 | 298 | 298
101672 | [101672] tf C2 - Custom Display Assemb | 1 | 298 | 0 | 298 | 298 | 298
101490 — tremoFlo C-100 Device Suregard compati ¦ Monthly: 1 ¦ Max buildable (stock): 0 ¦ Max buildable (+incoming): 2
Ref | Component | Qty/Unit | Stock | Incoming | Total | Build(Stock) | Build(+Inc)
100978 | [100978] tF C100 PFT Filter Interface | 1 | 0 | 2 | 2 | 0 | 2
101535 | [101535] PCBA tF C-100 Connector Board | 1 | 44 | 1265 | 1309 | 44 | 1309
100479 | [100479] TremoFlo C-100 Handheld Main | 1 | 61 | 1438 | 1499 | 61 | 1499
100477 | [100477] tremoFlo C-100 Mezzanine PCBA | 1 | 79 | 1340 | 1419 | 79 | 1419
100481 | [100481] TremoFlo C-100 Handheld Ring | 1 | 87 | 1299 | 1386 | 87 | 1386
101532 | [101532] PCBA TFC100 NB-SBC | 1 | 97 | 1404 | 1501 | 97 | 1501
100318 | [100318] TremoFlo C-100 Motor Bobbin | 1 | 111 | 900 | 1011 | 111 | 1011
101540 | [101540] tF C-100 Pneumotach Main Body | 1 | 118 | 928 | 1046 | 118 | 1046
100348 | [100348] TremoFlo C-100 Motor Piston M | 1 | 136 | 750 | 886 | 136 | 886
100795 | [100795] tF C-100 CCU Enclosure BOTTOM | 1 | 153 | 1100 | 1253 | 153 | 1253
100975 | [100975] tF C100 Pneumotach Inner Mesh | 1 | 169 | 900 | 1069 | 169 | 1069
100480 | [100480] TremoFlo C-100 Handheld Posit | 1 | 175 | 1481 | 1656 | 175 | 1656
100790 | [100790] tF C-100 HHU_STRAIN RELIEF In | 2 | 383 | 1700 | 2083 | 191 | 1041
100792 | [100792] tF C-100 CCU Enclosure front | 1 | 196 | 1100 | 1296 | 196 | 1296
100781 | [100781] tF C-100 HHU Front Shell Inj. | 1 | 197 | 1100 | 1297 | 197 | 1297
101759 — tf C-100 Device Vitalograph - 28300 ¦ Monthly: 25 ¦ Max buildable (stock): 44 ¦ Max buildable (+incoming): 1309
Ref | Component | Qty/Unit | Stock | Incoming | Total | Build(Stock) | Build(+Inc)
101535 | [101535] PCBA tF C-100 Connector Board | 1 | 44 | 1265 | 1309 | 44 | 1309
101746 | [101746] tf C-100 HHU_NAME PLATE - Vit | 1 | 54 | 0 | 54 | 54 | 54
101749 | [101749] tf C-100 HHU BACK SHELL - Vit | 1 | 59 | 0 | 59 | 59 | 59
101745 | [101745] tf C-100 HHU FRONT CAP - Vita | 1 | 61 | 0 | 61 | 61 | 61
101747 | [101747] tf C-100 CCU Enclosure Holder | 1 | 61 | 0 | 61 | 61 | 61
100479 | [100479] TremoFlo C-100 Handheld Main | 1 | 61 | 1438 | 1499 | 61 | 1499
101748 | [101748] tf C-100 CCU Enclosure front | 1 | 62 | 0 | 62 | 62 | 62
101744 | [101744] tf C-100 HHU LOOVER PLATE - V | 1 | 63 | 0 | 63 | 63 | 63
100477 | [100477] tremoFlo C-100 Mezzanine PCBA | 1 | 79 | 1340 | 1419 | 79 | 1419
100481 | [100481] TremoFlo C-100 Handheld Ring | 1 | 87 | 1299 | 1386 | 87 | 1386
101532 | [101532] PCBA TFC100 NB-SBC | 1 | 97 | 1404 | 1501 | 97 | 1501
100318 | [100318] TremoFlo C-100 Motor Bobbin | 1 | 111 | 900 | 1011 | 111 | 1011
101540 | [101540] tF C-100 Pneumotach Main Body | 1 | 118 | 928 | 1046 | 118 | 1046
101755 | [101755] tf C-100 Filter interface Vit | 1 | 125 | 0 | 125 | 125 | 125
100348 | [100348] TremoFlo C-100 Motor Piston M | 1 | 136 | 750 | 886 | 136 | 886
101760 — tf C-100 Device Vitalograph - 28500 ¦ Monthly: 25 ¦ Max buildable (stock): 44 ¦ Max buildable (+incoming): 1309
Ref | Component | Qty/Unit | Stock | Incoming | Total | Build(Stock) | Build(+Inc)
101535 | [101535] PCBA tF C-100 Connector Board | 1 | 44 | 1265 | 1309 | 44 | 1309
101746 | [101746] tf C-100 HHU_NAME PLATE - Vit | 1 | 54 | 0 | 54 | 54 | 54
101749 | [101749] tf C-100 HHU BACK SHELL - Vit | 1 | 59 | 0 | 59 | 59 | 59
101745 | [101745] tf C-100 HHU FRONT CAP - Vita | 1 | 61 | 0 | 61 | 61 | 61
101747 | [101747] tf C-100 CCU Enclosure Holder | 1 | 61 | 0 | 61 | 61 | 61
100479 | [100479] TremoFlo C-100 Handheld Main | 1 | 61 | 1438 | 1499 | 61 | 1499
101748 | [101748] tf C-100 CCU Enclosure front | 1 | 62 | 0 | 62 | 62 | 62
101744 | [101744] tf C-100 HHU LOOVER PLATE - V | 1 | 63 | 0 | 63 | 63 | 63
100477 | [100477] tremoFlo C-100 Mezzanine PCBA | 1 | 79 | 1340 | 1419 | 79 | 1419
100481 | [100481] TremoFlo C-100 Handheld Ring | 1 | 87 | 1299 | 1386 | 87 | 1386
101532 | [101532] PCBA TFC100 NB-SBC | 1 | 97 | 1404 | 1501 | 97 | 1501
100318 | [100318] TremoFlo C-100 Motor Bobbin | 1 | 111 | 900 | 1011 | 111 | 1011
101540 | [101540] tF C-100 Pneumotach Main Body | 1 | 118 | 928 | 1046 | 118 | 1046
101755 | [101755] tf C-100 Filter interface Vit | 1 | 125 | 0 | 125 | 125 | 125
100348 | [100348] TremoFlo C-100 Motor Piston M | 1 | 136 | 750 | 886 | 136 | 886
102240 — tf C2 Device - Blue - VTG 28554 ¦ Monthly: 20 ¦ Max buildable (stock): 0 ¦ Max buildable (+incoming): 100
Ref | Component | Qty/Unit | Stock | Incoming | Total | Build(Stock) | Build(+Inc)
102245 | [102245] tf C2 Custom Display Assembly | 1 | 0 | 100 | 100 | 0 | 100
102242 | [102242] tf C2 Top Shell - VTG | 1 | 52 | 58 | 110 | 52 | 110
102243 | [102243] tf C2 Front Cap – VTG | 1 | 52 | 58 | 110 | 52 | 110
102152 | [102152] tf C2 Pneumotach chamber Fron | 1 | 53 | 205 | 258 | 53 | 258
102244 | [102244] tf C2 USB-C Cap – VTG | 1 | 55 | 55 | 110 | 55 | 110
101658 | [101658] tf C2 Battery Pack | 1 | 79 | 200 | 279 | 79 | 279
101683 | [101683] tf C2 - Pneumotach Mesh | 1 | 143 | 0 | 143 | 143 | 143
101699 | [101699] tf C2 - Pneumotach Neck Foam | 1 | 204 | 0 | 204 | 204 | 204
101718 | [101718] tf C2 - Main Body CNC | 1 | 228 | 5 | 233 | 228 | 233
101719 | [101719] tf C2 Piston CNC | 1 | 248 | 5 | 253 | 248 | 253
101675 | [101675] tf C2 - Battery Strap | 1 | 256 | 0 | 256 | 256 | 256
101680 | [101680] tf C2 Motor Rod | 2 | 534 | 400 | 934 | 267 | 467
101677 | [101677] tf C2 Main Board PCBA | 1 | 273 | 772 | 1045 | 273 | 1045
101679 | [101679] tf C2 USB Board PCBA | 1 | 278 | 799 | 1077 | 278 | 1077
101700 | [101700] tf C2 Pneumotach chamber Back | 1 | 283 | 250 | 533 | 283 | 533
101059 — tremoflo C-100 Calibrated Reference Lo ¦ Monthly: 150 ¦ Max buildable (stock): 206 ¦ Max buildable (+incoming): 1166
Ref | Component | Qty/Unit | Stock | Incoming | Total | Build(Stock) | Build(+Inc)
101609 | [101609] Reference Load Shipper box wi | 1 | 206 | 960 | 1166 | 206 | 1166
102114 | [102114] Test Load Assy for Reference | 1 | 380 | 450 | 830 | 380 | 830
101979 | [101979] Test Load Mesh 165X1400 | 1 | 407 | 0 | 407 | 407 | 407
100986 — tremoflo C-100 Calibrated Reference Lo ¦ Monthly: 150 ¦ Max buildable (stock): 153 ¦ Max buildable (+incoming): 603
Ref | Component | Qty/Unit | Stock | Incoming | Total | Build(Stock) | Build(+Inc)
101104 | [101104] Test Load Assy | 1 | 153 | 450 | 603 | 153 | 603
101609 | [101609] Reference Load Shipper box wi | 1 | 206 | 960 | 1166 | 206 | 1166
102036 — tremoflo C2 Airwave Oscillometry Syste ¦ Monthly: 100 ¦ Max buildable (stock): 0 ¦ Max buildable (+incoming): 0
Ref | Component | Qty/Unit | Stock | Incoming | Total | Build(Stock) | Build(+Inc)
102020 | [102020] Wafer Seal Sticker 1.5in | 2 | 0 | 0 | 0 | 0 | 0
101694 | [101694] USB Cable Type C to A - 2 Fe | 1 | 91 | 0 | 91 | 91 | 91
102128 | [102128] C2 USB Power Supply Box Sleev | 1 | 197 | 0 | 197 | 197 | 197
101663 | [101663] tf C2 Power Supply | 1 | 659 | 0 | 659 | 659 | 659