## 📊 Summary
Component PO Plan — Executive Summary
Production rate (monthly) | 101485: 5/mo 101524: 0/mo 101761: 25/mo 101762: 0/mo 101770: 0/mo 101929: 0/mo 101963: 15/mo 101969: 0/mo 102002: 0/mo 102003: 0/mo 102005: 0/mo 102035: 0/mo 102036: 100/mo 102181: 25/mo 102585: 125/mo
Coverage target | 7 months
Reorder point | 3 months coverage remaining
Order qty rounding | Round up to nearest 50
Generated | 2026-03-02 22:47 UTC
Total components in scope | 76
🔴 ORDER NOW (overdue) | 10
🟠 Order within 14 days | 1
🟡 Plan ahead (order date upcoming) | 17
✅ Sufficient stock | 48
⚠ No supplier configured | 0
⚠ Lead time = 0 (needs review) | 3
💰 Estimated total PO value | $267,250
Supplier | Parts | To Order | Urgent | Est. Value
Alloy Concepts | 16 | 3 | 2 | $11,830
Lovepac | 3 | 3 | 1 | $7,392
ICO Mold LLC | 22 | 7 | 6 | $32,828
ULINE, Sales ULINE | 1 | 1 | 1 | N/A
Barcodes Inc. | 1 | 1 | 0 | $123,033
Globtek Inc. | 2 | 2 | 0 | $6,132
FrontierPC | 1 | 1 | 0 | $22,907
Graphiscan | 3 | 1 | 0 | $911
Sinpro Electronics | 1 | 1 | 0 | $10,100
Infinite Cables | 5 | 3 | 0 | $4,262
Xometry, Ethan Beum | 2 | 2 | 0 | $17,435
Laiju Bag | 1 | 1 | 0 | $760
Quail Electronics | 1 | 1 | 0 | $340
Radicom | 1 | 1 | 0 | $29,321
Net Burner | 1 | 0 | 0 | N/A
NEL Technologies | 1 | 0 | 0 | N/A
Minco | 1 | 0 | 0 | N/A
Custom Sheet Metal Products (CSTM) | 1 | 0 | 0 | N/A
SMT Hautes Technologies | 7 | 0 | 0 | N/A
E-Sonic | 2 | 0 | 0 | N/A
Moticont | 1 | 0 | 0 | N/A
Bogen Magnetics GmbH Magnetics | 1 | 0 | 0 | N/A
The ZPS Store | 1 | 0 | 0 | N/A

## 📋 PO Plan
Component PO Plan — 6-Month Rolling Coverage (76 components)
Rate: 101485×5 101524×0 101761×25 101762×0 101770×0 101929×0 101963×15 101969×0 102002×0 102003×0 102005×0 102035×0 102036×100 102181×25 102585×125 /mo ¦ Target: 7mo ¦ Reorder at: 3mo ¦ Generated: 2026-03-02 22:47 UTC
Ref | Component Name | Supplier | Sup Code | Lead Days | Min Qty | Stock Avail | Open Incoming | Total Avail | Monthly Req | Coverage Now(mo) | Reorder Point | Target Qty(7mo) | ORDER QTY | Coverage After | Latest Safe Order Date | Buffer (days) | Price Source | Est Value (USD) | Status
🔴 ORDER NOW — 10 components (lead time already exceeded)
100978 | [100978] tF C100 PFT Filter Interface | Alloy Concepts |  | 56 |  | 0 | 2 | 2 | 5 | 0.4 | 15 | 35 | 50 | 10.4 | 2026-03-02 | -43 | P01883 (CAD) | 4123.3 | 🔴 CRITICAL — stock out in 12d, lead 56d — ORDER TODAY
101109 | [101109] Test Load Adaptor - Suregard | Alloy Concepts |  | 56 |  | 9 | 0 | 9 | 5 | 1.8 | 15 | 35 | 50 | 11.8 | 2026-03-02 | -1 | P00220 (CAD) | 1109.81 | 🔴 CRITICAL — stock out in 54d, lead 56d — ORDER TODAY
101610 | [101610] tF Power Supply & Cord Box - | Lovepac |  | 42 |  | 0 | 0 | 0 | 145 | 0 | 435 | 1015 | 1050 | 7.2 | 2026-03-02 | -42 | pricelist | 1291.5 | 🔴 CRITICAL — stock out in 0d, lead 42d — ORDER TODAY
101744 | [101744] tf C-100 HHU LOOVER PLATE - V | ICO Mold LLC |  | 42 |  | 63 | 0 | 63 | 50 | 1.3 | 150 | 350 | 300 | 7.3 | 2026-03-02 | -3 | P01432 (USD) | 3744 | 🔴 CRITICAL — stock out in 38d, lead 42d — ORDER TODAY
101745 | [101745] tf C-100 HHU FRONT CAP - Vita | ICO Mold LLC |  | 42 |  | 61 | 0 | 61 | 50 | 1.2 | 150 | 350 | 300 | 7.2 | 2026-03-02 | -4 | P01432 (USD) | 3780 | 🔴 CRITICAL — stock out in 37d, lead 42d — ORDER TODAY
101746 | [101746] tf C-100 HHU_NAME PLATE - Vit | ICO Mold LLC |  | 42 |  | 54 | 0 | 54 | 50 | 1.1 | 150 | 350 | 300 | 7.1 | 2026-03-02 | -9 | P01432 (USD) | 3744 | 🔴 CRITICAL — stock out in 32d, lead 42d — ORDER TODAY
101747 | [101747] tf C-100 CCU Enclosure Holder | ICO Mold LLC |  | 42 |  | 61 | 0 | 61 | 50 | 1.2 | 150 | 350 | 300 | 7.2 | 2026-03-02 | -4 | P01432 (USD) | 4290 | 🔴 CRITICAL — stock out in 37d, lead 42d — ORDER TODAY
101748 | [101748] tf C-100 CCU Enclosure front | ICO Mold LLC |  | 42 |  | 62 | 0 | 62 | 50 | 1.2 | 150 | 350 | 300 | 7.2 | 2026-03-02 | -4 | P01432 (USD) | 5778 | 🔴 CRITICAL — stock out in 37d, lead 42d — ORDER TODAY
101749 | [101749] tf C-100 HHU BACK SHELL - Vit | ICO Mold LLC |  | 42 |  | 59 | 0 | 59 | 50 | 1.2 | 150 | 350 | 300 | 7.2 | 2026-03-02 | -6 | P01432 (USD) | 7044 | 🔴 CRITICAL — stock out in 35d, lead 42d — ORDER TODAY
102020 | [102020] Wafer Seal Sticker 1.5in | ULINE, Sales ULINE |  | 1 |  | 0 | 0 | 0 | 200 | 0 | 600 | 1400 | 1400 | 7 | 2026-03-02 | -1 | pricelist |  | 🔴 CRITICAL — stock out in 0d, lead 1d — ORDER TODAY
🟠 ORDER WITHIN 14 DAYS — 1 components
101641 | [101641] 2 x 1 in Zebra label roll | Barcodes Inc. |  | 1 |  | 0 | 2 | 2 | 20 | 0.1 | 60 | 140 | 150 | 7.6 | 2026-03-04 | 2 | P01747 (CAD) | 123032.55 | 🟠 Order NOW — only 2d buffer
🟡 PLAN AHEAD — 17 components (order date upcoming)
101694 | [101694] USB Cable Type C to A - 2 Fe | Globtek Inc. |  | 1 |  | 91 | 0 | 91 | 100 | 0.9 | 300 | 700 | 650 | 7.4 | 2026-03-28 | 26 | P00730 (USD) | 5486 | 🟡 Order by 2026-03-28 — 26d buffer (lead 1d)
101405 | [101405] Zebra 5095 High Performance B | FrontierPC |  | 1 |  | 0 | 25 | 25 | 20 | 1.2 | 60 | 140 | 150 | 8.8 | 2026-04-08 | 37 | P01747 (CAD) | 22906.83 | 🟡 Order by 2026-04-08 — 37d buffer (lead 1d)
101750 | [101750] tf C-100 CCU Enclosure Top - | ICO Mold LLC |  | 42 |  | 162 | 0 | 162 | 50 | 3.2 | 150 | 350 | 200 | 7.2 | 2026-04-27 | 56 | P01432 (USD) | 4448 | 🟢 Order by 2026-04-27 — 56d buffer (lead 42d)
102128 | [102128] C2 USB Power Supply Box Sleev | Graphiscan |  | 0 |  | 197 | 0 | 197 | 100 | 2 | 300 | 700 | 550 | 7.5 | 2026-04-30 | 59 | P01554 (CAD) | 911.13 | ⚠ CHECK LEAD TIME — 🟢 Order by 2026-04-30 — 59d buffer (lead 0d)
101557 | [101557] Medical Grade Power Supply fo | Sinpro Electronics |  | 84 |  | 494 | 500 | 994 | 195 | 5.1 | 585 | 1365 | 400 | 7.1 | 2026-05-12 | 71 | P01845 (USD) | 10100 | 🟢 Order by 2026-05-12 — 71d buffer (lead 84d)
101322 | [101322] CABLE, ETHERNET CAT5E, WHITE, | Infinite Cables | CAT5E-07WH | 7 |  | 524 | 0 | 524 | 195 | 2.7 | 585 | 1365 | 850 | 7 | 2026-05-15 | 74 | P01629 (CAD) | 2000.05 | 🟢 Order by 2026-05-15 — 74d buffer (lead 7d)
101753 | [101753] tf C-100 Test Load adapter Vi | Xometry, Ethan Beum |  | 1 |  | 124 | 0 | 124 | 50 | 2.5 | 150 | 350 | 250 | 7.5 | 2026-05-15 | 74 | P01405 (CAD) | 6043.82 | 🟢 Order by 2026-05-15 — 74d buffer (lead 1d)
101755 | [101755] tf C-100 Filter interface Vit | Xometry, Ethan Beum |  | 1 |  | 125 | 0 | 125 | 50 | 2.5 | 150 | 350 | 250 | 7.5 | 2026-05-16 | 75 | P01405 (CAD) | 11391.3 | 🟢 Order by 2026-05-16 — 75d buffer (lead 1d)
102195 | [102195] tf C100 Dust Cover | Laiju Bag |  | 1 |  | 46 | 0 | 46 | 15 | 3.1 | 45 | 105 | 100 | 9.7 | 2026-06-02 | 92 | P01422 (USD) | 760 | 🟢 Order by 2026-06-02 — 92d buffer (lead 1d)
101604 | [101604] Power Cord 2.0M Black, IS 653 | Quail Electronics | 9840.079 | 28 |  | 61 | 0 | 61 | 15 | 4.1 | 45 | 105 | 50 | 7.4 | 2026-06-05 | 95 | P00878 (CAD) | 339.76 | 🟢 Order by 2026-06-05 — 95d buffer (lead 28d)
102584 | [102584] USB to Ethernet Adapter (incl | Radicom |  | 28 |  | 156 | 353 | 509 | 125 | 4.1 | 375 | 875 | 400 | 7.3 | 2026-06-05 | 95 | P01880 (CAD) | 29321.2 | 🟢 Order by 2026-06-05 — 95d buffer (lead 28d)
101595 | [101595] tF C100 Test Load Adapter - C | Alloy Concepts |  | 56 |  | 249 | 459 | 708 | 140 | 5.1 | 420 | 980 | 300 | 7.2 | 2026-06-07 | 97 | P01828 (CAD) | 6597.27 | 🟢 Order by 2026-06-07 — 97d buffer (lead 56d)
101793 | [101793] tf Shipper Box - Vitalograph | Lovepac |  | 42 |  | 121 | 0 | 121 | 25 | 4.8 | 75 | 175 | 100 | 8.8 | 2026-06-15 | 105 | P01613 (CAD) | 2731.27 | 🟢 Order by 2026-06-15 — 105d buffer (lead 42d)
101612 | [101612] tF C-100 Shipper Box Carton o | Lovepac |  | 42 |  | 265 | 610 | 875 | 145 | 6 | 435 | 1015 | 150 | 7.1 | 2026-07-21 | 141 | P01842 (CAD) | 3369 | 🟢 Order by 2026-07-21 — 141d buffer (lead 42d)
101113 | [101113] Power Cord, Type I (AS/NZS 31 | Infinite Cables |  | 7 |  | 26 | 0 | 26 | 5 | 5.2 | 15 | 35 | 50 | 15.2 | 2026-07-31 | 151 | P01538 (CAD) | 207.81 | 🟢 Order by 2026-07-31 — 151d buffer (lead 7d)
101073 | [101073] Medical Grade Power Cord PWL- | Infinite Cables |  | 7 |  | 279 | 560 | 839 | 150 | 5.6 | 450 | 1050 | 250 | 7.3 | 2026-08-12 | 163 | P01888 (CAD) | 2054.32 | 🟢 Order by 2026-08-12 — 163d buffer (lead 7d)
101663 | [101663] tf C2 Power Supply | Globtek Inc. |  | 0 |  | 659 | 0 | 659 | 100 | 6.6 | 300 | 700 | 50 | 7.1 | 2026-09-18 | 200 | P00730 (USD) | 645.5 | ⚠ CHECK LEAD TIME — 🟢 Order by 2026-09-18 — 200d buffer (lead 0d)
✅ SUFFICIENT STOCK — 48 components (coverage > 7 months)
100159 | [100159] NetBurner Ethernet Core Modul | Net Burner | MOD5234-200IR | 21 |  | 323 | 300 | 623 | 55 | 11.3 | 165 | 385 |  |  |  |  | P01841 (USD) |  | ✅ Sufficient
100318 | [100318] TremoFlo C-100 Motor Bobbin | Alloy Concepts | 100318 | 56 |  | 111 | 900 | 1011 | 55 | 18.4 | 165 | 385 |  |  |  |  | P01745 (CAD) |  | ✅ Sufficient
100321 | [100321] TremoFlo C-100 Motor Shaft | Alloy Concepts |  | 56 |  | 576 | 1611 | 2187 | 110 | 19.9 | 330 | 770 |  |  |  |  | P01745 (CAD) |  | ✅ Sufficient
100322 | [100322] TremoFlo C-100 Hall Sensor Br | Alloy Concepts | 100322 | 56 |  | 765 | 475 | 1240 | 55 | 22.5 | 165 | 385 |  |  |  |  | P01745 (CAD) |  | ✅ Sufficient
100326 | [100326] TremoFlo C-100 Motor Piston O | Alloy Concepts | 100326 | 56 |  | 234 | 750 | 984 | 55 | 17.9 | 165 | 385 |  |  |  |  | P01745 (CAD) |  | ✅ Sufficient
100328 | [100328] TremoFlo C-100 Motor Piston I | Alloy Concepts | 100328 | 56 |  | 379 | 842 | 1221 | 55 | 22.2 | 165 | 385 |  |  |  |  | P01745 (CAD) |  | ✅ Sufficient
100345 | [100345] TremoFlo C-100 Pneumotach Hea | NEL Technologies | NEL-2018-1743-HA | 42 |  | 490 | 400 | 890 | 55 | 16.2 | 165 | 385 |  |  |  |  | P01886 (USD) |  | ✅ Sufficient
100346 | [100346] TremoFlo C-100 Pneumotach RTD | Minco | S100725PFYT24B | 42 |  | 443 | 400 | 843 | 55 | 15.3 | 165 | 385 |  |  |  |  | P01886 (USD) |  | ✅ Sufficient
100348 | [100348] TremoFlo C-100 Motor Piston M | Alloy Concepts | 100348 | 56 |  | 136 | 750 | 886 | 55 | 16.1 | 165 | 385 |  |  |  |  | P01745 (CAD) |  | ✅ Sufficient
100359 | [100359] TremoFlo C-100 CU Metal Enclo | Custom Sheet Metal P | 100359 | 70 |  | 226 | 300 | 526 | 55 | 9.6 | 165 | 385 |  |  |  |  | P01840 (CAD) |  | ✅ Sufficient
100477 | [100477] tremoFlo C-100 Mezzanine PCBA | SMT Hautes Technolog | 100477 | 70 |  | 79 | 1340 | 1419 | 55 | 25.8 | 165 | 385 |  |  |  |  | P01746 (USD) |  | ✅ Sufficient
100479 | [100479] TremoFlo C-100 Handheld Main | SMT Hautes Technolog |  | 119 |  | 61 | 1438 | 1499 | 55 | 27.3 | 165 | 385 |  |  |  |  | P01746 (USD) |  | ✅ Sufficient
100480 | [100480] TremoFlo C-100 Handheld Posit | SMT Hautes Technolog |  | 119 |  | 175 | 1481 | 1656 | 55 | 30.1 | 165 | 385 |  |  |  |  | P01746 (USD) |  | ✅ Sufficient
100481 | [100481] TremoFlo C-100 Handheld Ring | SMT Hautes Technolog |  | 119 |  | 87 | 1299 | 1386 | 55 | 25.2 | 165 | 385 |  |  |  |  | P01746 (USD) |  | ✅ Sufficient
100781 | [100781] tF C-100 HHU Front Shell Inj. | ICO Mold LLC | 030-100781-00 | 42 |  | 197 | 1100 | 1297 | 55 | 23.6 | 165 | 385 |  |  |  |  | P01844 (USD) |  | ✅ Sufficient
100782 | [100782] tF C-100 HHU BACK SHELL Inj. | ICO Mold LLC | 030-100782-00 | 42 |  | 578 | 400 | 978 | 5 | ∞ | 15 | 35 |  |  |  |  | P01844 (USD) |  | ✅ Sufficient
100783 | [100783] tF C-100 HHU_LENS LIGHT PIPE | ICO Mold LLC | 100783 | 42 |  | 714 | 400 | 1114 | 55 | 20.3 | 165 | 385 |  |  |  |  | P01844 (USD) |  | ✅ Sufficient
100784 | [100784] tF C-100 HHU_LOOVER REAR PLAT | ICO Mold LLC | 030-100784-00 | 42 |  | 650 | 400 | 1050 | 5 | ∞ | 15 | 35 |  |  |  |  | P01844 (USD) |  | ✅ Sufficient
100785 | [100785] tF C-100 HHU_LEFT BUTTON Inj. | ICO Mold LLC | 030-100785-00 | 42 |  | 521 | 700 | 1221 | 55 | 22.2 | 165 | 385 |  |  |  |  | P01844 (USD) |  | ✅ Sufficient
100786 | [100786] tF C100 HHU RIGHT BUTTON Inj. | ICO Mold LLC | 030-100786-00 | 42 |  | 543 | 700 | 1243 | 55 | 22.6 | 165 | 385 |  |  |  |  | P01844 (USD) |  | ✅ Sufficient
100789 | [100789] tF C-100 HHU_FRONT CAP Inj. | ICO Mold LLC | 030-100789-00 | 42 |  | 702 | 400 | 1102 | 5 | ∞ | 15 | 35 |  |  |  |  | P01844 (USD) |  | ✅ Sufficient
100790 | [100790] tF C-100 HHU_STRAIN RELIEF In | ICO Mold LLC | 030-100790-00 | 42 |  | 383 | 1700 | 2083 | 110 | 18.9 | 330 | 770 |  |  |  |  | P01844 (USD) |  | ✅ Sufficient
100791 | [100791] tF C-100 HHU_NAME PLATE Inj. | ICO Mold LLC | 030-100791-00 | 42 |  | 653 | 400 | 1053 | 5 | ∞ | 15 | 35 |  |  |  |  | P01844 (USD) |  | ✅ Sufficient
100792 | [100792] tF C-100 CCU Enclosure front | ICO Mold LLC | 030-100792-00 | 42 |  | 196 | 1100 | 1296 | 5 | ∞ | 15 | 35 |  |  |  |  | P01844 (USD) |  | ✅ Sufficient
100793 | [100793] tF C-100 CCU Enclosure Top In | ICO Mold LLC | 030-100793-00 | 42 |  | 493 | 400 | 893 | 5 | ∞ | 15 | 35 |  |  |  |  | P01844 (USD) |  | ✅ Sufficient
100794 | [100794] tF C-100 CCU Enclosure Holder | ICO Mold LLC | 030-100794-00 | 42 |  | 410 | 464 | 874 | 5 | ∞ | 15 | 35 |  |  |  |  | P01844 (USD) |  | ✅ Sufficient
100795 | [100795] tF C-100 CCU Enclosure BOTTOM | ICO Mold LLC | 030-100795-00 | 42 |  | 153 | 1100 | 1253 | 55 | 22.8 | 165 | 385 |  |  |  |  | P01844 (USD) |  | ✅ Sufficient
100796 | [100796] tF C-100 CCU Enclosure Power | ICO Mold LLC | 030-100796-00 | 42 |  | 1943 | 700 | 2643 | 55 | 48.1 | 165 | 385 |  |  |  |  | P01844 (USD) |  | ✅ Sufficient
100797 | [100797] tF C-100 CCU Enclosure Interf | ICO Mold LLC | 100797 | 42 |  | 511 | 700 | 1211 | 55 | 22 | 165 | 385 |  |  |  |  | P01844 (USD) |  | ✅ Sufficient
100866 | [100866] THERMOSTAT 50 DEG NC TO-220 A | E-Sonic | 67L050 | 14 |  | 337 | 400 | 737 | 55 | 13.4 | 165 | 385 |  |  |  |  | P01595 (CAD) |  | ✅ Sufficient
100975 | [100975] tF C100 Pneumotach Inner Mesh | Alloy Concepts | 100975 | 56 |  | 169 | 900 | 1069 | 55 | 19.4 | 165 | 385 |  |  |  |  | P01745 (CAD) |  | ✅ Sufficient
100976 | [100976] tF C100 Pneumotach Outer Mesh | Alloy Concepts | 100976 | 56 |  | 197 | 900 | 1097 | 55 | 19.9 | 165 | 385 |  |  |  |  | P01745 (CAD) |  | ✅ Sufficient
100977 | [100977] tF C100 Pneumotach Knob | Alloy Concepts | 100977 | 56 |  | 450 | 634 | 1084 | 55 | 19.7 | 165 | 385 |  |  |  |  | P01745 (CAD) |  | ✅ Sufficient
101106 | [101106] TremoFlo C100 Custom made cab | SMT Hautes Technolog | 101106 | 112 |  | 278 | 1002 | 1280 | 55 | 23.3 | 165 | 385 |  |  |  |  | P01838 (CAD) |  | ✅ Sufficient
101110 | [101110] Power Cord, Type E/F (CEE 7/7 | Infinite Cables |  | 7 |  | 515 | 560 | 1075 | 125 | 8.6 | 375 | 875 |  |  |  |  | P01888 (CAD) |  | ✅ Sufficient
101111 | [101111] Power Cord 2.5M, 1.0mm^2 H05V | Infinite Cables |  | 7 |  | 11 | 0 | 11 |  | ∞ | 0 | 0 |  |  |  |  | P01303 (CAD) |  | ✅ Sufficient
101254 | [101254] tF C-100 Light Piston | Alloy Concepts |  | 56 |  | 245 | 1005 | 1250 | 55 | 22.7 | 165 | 385 |  |  |  |  | P01745 (CAD) |  | ✅ Sufficient
101255 | [101255] tF C-100 Light Motor Back Pla | Alloy Concepts | 101255 | 56 |  | 457 | 696 | 1153 | 55 | 21 | 165 | 385 |  |  |  |  | P01745 (CAD) |  | ✅ Sufficient
101278 | [101278] tf C100 Motor Assembly VCA | Moticont | LVCM-016-019-01 | 28 |  | 531 | 400 | 931 | 55 | 16.9 | 165 | 385 |  |  |  |  | P01885 (USD) |  | ✅ Sufficient
101393 | [101393] MOTOR THERMAL SWITCH [O53GAB1 | E-Sonic | O53GAB140A-125Y | 14 |  | 620 | 400 | 1020 | 55 | 18.5 | 165 | 385 |  |  |  |  | P01873 (CAD) |  | ✅ Sufficient
101498 | [101498] Magnetic strip 24mm | Bogen Magnetics GmbH |  | 1 |  | 1756 | 0 | 1756 | 55 | 31.9 | 165 | 385 |  |  |  |  | P01674 (USD) |  | ✅ Sufficient
101520 | [101520] 2.5 x 4 in. polyester Label r | The ZPS Store |  | 0 |  | 0 | 6 | 6 |  | ∞ | 0 | 0 |  |  |  |  | P01610 (CAD) |  | ⚠ CHECK LEAD TIME — ✅ Sufficient
101532 | [101532] PCBA TFC100 NB-SBC | SMT Hautes Technolog | 101532 | 70 |  | 97 | 1404 | 1501 | 55 | 27.3 | 165 | 385 |  |  |  |  | P01746 (USD) |  | ✅ Sufficient
101535 | [101535] PCBA tF C-100 Connector Board | SMT Hautes Technolog | 101535 | 70 |  | 44 | 1265 | 1309 | 55 | 23.8 | 165 | 385 |  |  |  |  | P01746 (USD) |  | ✅ Sufficient
101540 | [101540] tF C-100 Pneumotach Main Body | Alloy Concepts | 101540 | 56 |  | 118 | 928 | 1046 | 55 | 19 | 165 | 385 |  |  |  |  | P01745 (CAD) |  | ✅ Sufficient
101541 | [101541] tF C-100 Pneumotach Heater Ri | Alloy Concepts | 101541 | 56 |  | 249 | 750 | 999 | 55 | 18.2 | 165 | 385 |  |  |  |  | P01745 (CAD) |  | ✅ Sufficient
101648 | [101648] tremoFlo C-100 User Manual, E | Graphiscan |  | 28 |  | 139 | 10 | 149 | 20 | 7.5 | 60 | 140 |  |  |  |  | P01859 (CAD) |  | ✅ Sufficient
101653 | [101653] tremoFlo C-100 User Manual, U | Graphiscan |  | 28 |  | 240 | 0 | 240 |  | ∞ | 0 | 0 |  |  |  |  | P01859 (CAD) |  | ✅ Sufficient

## 🏭 By Supplier
Component PO Plan — Grouped by Supplier
Rate: 101485×5 101524×0 101761×25 101762×0 101770×0 101929×0 101963×15 101969×0 102002×0 102003×0 102005×0 102035×0 102036×100 102181×25 102585×125 /mo ¦ Target: 7mo ¦ Reorder at: 3mo ¦ Generated: 2026-03-02 22:47 UTC
Ref | Component Name | Supplier | Sup Code | Lead Days | Min Qty | Stock Avail | Open Incoming | Total Avail | Monthly Req | Coverage Now(mo) | Reorder Point | Target Qty(7mo) | ORDER QTY | Coverage After | Latest Safe Order Date | Buffer (days) | Price Source | Est Value (USD) | Status
🏭 Alloy Concepts — 16 parts ¦ 3 to order ¦ Est. $11,830
100978 | [100978] tF C100 PFT Filter Interface | Alloy Concepts |  | 56 |  | 0 | 2 | 2 | 5 | 0.4 | 15 | 35 | 50 | 10.4 | 2026-03-02 | -43 | P01883 (CAD) | 4123.3 | 🔴 CRITICAL — stock out in 12d, lead 56d — ORDER TODAY
101109 | [101109] Test Load Adaptor - Suregard | Alloy Concepts |  | 56 |  | 9 | 0 | 9 | 5 | 1.8 | 15 | 35 | 50 | 11.8 | 2026-03-02 | -1 | P00220 (CAD) | 1109.81 | 🔴 CRITICAL — stock out in 54d, lead 56d — ORDER TODAY
101595 | [101595] tF C100 Test Load Adapter - C | Alloy Concepts |  | 56 |  | 249 | 459 | 708 | 140 | 5.1 | 420 | 980 | 300 | 7.2 | 2026-06-07 | 97 | P01828 (CAD) | 6597.27 | 🟢 Order by 2026-06-07 — 97d buffer (lead 56d)
100318 | [100318] TremoFlo C-100 Motor Bobbin | Alloy Concepts | 100318 | 56 |  | 111 | 900 | 1011 | 55 | 18.4 | 165 | 385 |  |  |  |  | P01745 (CAD) |  | ✅ Sufficient
100321 | [100321] TremoFlo C-100 Motor Shaft | Alloy Concepts |  | 56 |  | 576 | 1611 | 2187 | 110 | 19.9 | 330 | 770 |  |  |  |  | P01745 (CAD) |  | ✅ Sufficient
100322 | [100322] TremoFlo C-100 Hall Sensor Br | Alloy Concepts | 100322 | 56 |  | 765 | 475 | 1240 | 55 | 22.5 | 165 | 385 |  |  |  |  | P01745 (CAD) |  | ✅ Sufficient
100326 | [100326] TremoFlo C-100 Motor Piston O | Alloy Concepts | 100326 | 56 |  | 234 | 750 | 984 | 55 | 17.9 | 165 | 385 |  |  |  |  | P01745 (CAD) |  | ✅ Sufficient
100328 | [100328] TremoFlo C-100 Motor Piston I | Alloy Concepts | 100328 | 56 |  | 379 | 842 | 1221 | 55 | 22.2 | 165 | 385 |  |  |  |  | P01745 (CAD) |  | ✅ Sufficient
100348 | [100348] TremoFlo C-100 Motor Piston M | Alloy Concepts | 100348 | 56 |  | 136 | 750 | 886 | 55 | 16.1 | 165 | 385 |  |  |  |  | P01745 (CAD) |  | ✅ Sufficient
100975 | [100975] tF C100 Pneumotach Inner Mesh | Alloy Concepts | 100975 | 56 |  | 169 | 900 | 1069 | 55 | 19.4 | 165 | 385 |  |  |  |  | P01745 (CAD) |  | ✅ Sufficient
100976 | [100976] tF C100 Pneumotach Outer Mesh | Alloy Concepts | 100976 | 56 |  | 197 | 900 | 1097 | 55 | 19.9 | 165 | 385 |  |  |  |  | P01745 (CAD) |  | ✅ Sufficient
100977 | [100977] tF C100 Pneumotach Knob | Alloy Concepts | 100977 | 56 |  | 450 | 634 | 1084 | 55 | 19.7 | 165 | 385 |  |  |  |  | P01745 (CAD) |  | ✅ Sufficient
101254 | [101254] tF C-100 Light Piston | Alloy Concepts |  | 56 |  | 245 | 1005 | 1250 | 55 | 22.7 | 165 | 385 |  |  |  |  | P01745 (CAD) |  | ✅ Sufficient
101255 | [101255] tF C-100 Light Motor Back Pla | Alloy Concepts | 101255 | 56 |  | 457 | 696 | 1153 | 55 | 21 | 165 | 385 |  |  |  |  | P01745 (CAD) |  | ✅ Sufficient
101540 | [101540] tF C-100 Pneumotach Main Body | Alloy Concepts | 101540 | 56 |  | 118 | 928 | 1046 | 55 | 19 | 165 | 385 |  |  |  |  | P01745 (CAD) |  | ✅ Sufficient
101541 | [101541] tF C-100 Pneumotach Heater Ri | Alloy Concepts | 101541 | 56 |  | 249 | 750 | 999 | 55 | 18.2 | 165 | 385 |  |  |  |  | P01745 (CAD) |  | ✅ Sufficient
🏭 Lovepac — 3 parts ¦ 3 to order ¦ Est. $7,392
101610 | [101610] tF Power Supply & Cord Box - | Lovepac |  | 42 |  | 0 | 0 | 0 | 145 | 0 | 435 | 1015 | 1050 | 7.2 | 2026-03-02 | -42 | pricelist | 1291.5 | 🔴 CRITICAL — stock out in 0d, lead 42d — ORDER TODAY
101793 | [101793] tf Shipper Box - Vitalograph | Lovepac |  | 42 |  | 121 | 0 | 121 | 25 | 4.8 | 75 | 175 | 100 | 8.8 | 2026-06-15 | 105 | P01613 (CAD) | 2731.27 | 🟢 Order by 2026-06-15 — 105d buffer (lead 42d)
101612 | [101612] tF C-100 Shipper Box Carton o | Lovepac |  | 42 |  | 265 | 610 | 875 | 145 | 6 | 435 | 1015 | 150 | 7.1 | 2026-07-21 | 141 | P01842 (CAD) | 3369 | 🟢 Order by 2026-07-21 — 141d buffer (lead 42d)
🏭 ICO Mold LLC — 22 parts ¦ 7 to order ¦ Est. $32,828
101744 | [101744] tf C-100 HHU LOOVER PLATE - V | ICO Mold LLC |  | 42 |  | 63 | 0 | 63 | 50 | 1.3 | 150 | 350 | 300 | 7.3 | 2026-03-02 | -3 | P01432 (USD) | 3744 | 🔴 CRITICAL — stock out in 38d, lead 42d — ORDER TODAY
101745 | [101745] tf C-100 HHU FRONT CAP - Vita | ICO Mold LLC |  | 42 |  | 61 | 0 | 61 | 50 | 1.2 | 150 | 350 | 300 | 7.2 | 2026-03-02 | -4 | P01432 (USD) | 3780 | 🔴 CRITICAL — stock out in 37d, lead 42d — ORDER TODAY
101746 | [101746] tf C-100 HHU_NAME PLATE - Vit | ICO Mold LLC |  | 42 |  | 54 | 0 | 54 | 50 | 1.1 | 150 | 350 | 300 | 7.1 | 2026-03-02 | -9 | P01432 (USD) | 3744 | 🔴 CRITICAL — stock out in 32d, lead 42d — ORDER TODAY
101747 | [101747] tf C-100 CCU Enclosure Holder | ICO Mold LLC |  | 42 |  | 61 | 0 | 61 | 50 | 1.2 | 150 | 350 | 300 | 7.2 | 2026-03-02 | -4 | P01432 (USD) | 4290 | 🔴 CRITICAL — stock out in 37d, lead 42d — ORDER TODAY
101748 | [101748] tf C-100 CCU Enclosure front | ICO Mold LLC |  | 42 |  | 62 | 0 | 62 | 50 | 1.2 | 150 | 350 | 300 | 7.2 | 2026-03-02 | -4 | P01432 (USD) | 5778 | 🔴 CRITICAL — stock out in 37d, lead 42d — ORDER TODAY
101749 | [101749] tf C-100 HHU BACK SHELL - Vit | ICO Mold LLC |  | 42 |  | 59 | 0 | 59 | 50 | 1.2 | 150 | 350 | 300 | 7.2 | 2026-03-02 | -6 | P01432 (USD) | 7044 | 🔴 CRITICAL — stock out in 35d, lead 42d — ORDER TODAY
101750 | [101750] tf C-100 CCU Enclosure Top - | ICO Mold LLC |  | 42 |  | 162 | 0 | 162 | 50 | 3.2 | 150 | 350 | 200 | 7.2 | 2026-04-27 | 56 | P01432 (USD) | 4448 | 🟢 Order by 2026-04-27 — 56d buffer (lead 42d)
100781 | [100781] tF C-100 HHU Front Shell Inj. | ICO Mold LLC | 030-100781-00 | 42 |  | 197 | 1100 | 1297 | 55 | 23.6 | 165 | 385 |  |  |  |  | P01844 (USD) |  | ✅ Sufficient
100782 | [100782] tF C-100 HHU BACK SHELL Inj. | ICO Mold LLC | 030-100782-00 | 42 |  | 578 | 400 | 978 | 5 | ∞ | 15 | 35 |  |  |  |  | P01844 (USD) |  | ✅ Sufficient
100783 | [100783] tF C-100 HHU_LENS LIGHT PIPE | ICO Mold LLC | 100783 | 42 |  | 714 | 400 | 1114 | 55 | 20.3 | 165 | 385 |  |  |  |  | P01844 (USD) |  | ✅ Sufficient
100784 | [100784] tF C-100 HHU_LOOVER REAR PLAT | ICO Mold LLC | 030-100784-00 | 42 |  | 650 | 400 | 1050 | 5 | ∞ | 15 | 35 |  |  |  |  | P01844 (USD) |  | ✅ Sufficient
100785 | [100785] tF C-100 HHU_LEFT BUTTON Inj. | ICO Mold LLC | 030-100785-00 | 42 |  | 521 | 700 | 1221 | 55 | 22.2 | 165 | 385 |  |  |  |  | P01844 (USD) |  | ✅ Sufficient
100786 | [100786] tF C100 HHU RIGHT BUTTON Inj. | ICO Mold LLC | 030-100786-00 | 42 |  | 543 | 700 | 1243 | 55 | 22.6 | 165 | 385 |  |  |  |  | P01844 (USD) |  | ✅ Sufficient
100789 | [100789] tF C-100 HHU_FRONT CAP Inj. | ICO Mold LLC | 030-100789-00 | 42 |  | 702 | 400 | 1102 | 5 | ∞ | 15 | 35 |  |  |  |  | P01844 (USD) |  | ✅ Sufficient
100790 | [100790] tF C-100 HHU_STRAIN RELIEF In | ICO Mold LLC | 030-100790-00 | 42 |  | 383 | 1700 | 2083 | 110 | 18.9 | 330 | 770 |  |  |  |  | P01844 (USD) |  | ✅ Sufficient
100791 | [100791] tF C-100 HHU_NAME PLATE Inj. | ICO Mold LLC | 030-100791-00 | 42 |  | 653 | 400 | 1053 | 5 | ∞ | 15 | 35 |  |  |  |  | P01844 (USD) |  | ✅ Sufficient
100792 | [100792] tF C-100 CCU Enclosure front | ICO Mold LLC | 030-100792-00 | 42 |  | 196 | 1100 | 1296 | 5 | ∞ | 15 | 35 |  |  |  |  | P01844 (USD) |  | ✅ Sufficient
100793 | [100793] tF C-100 CCU Enclosure Top In | ICO Mold LLC | 030-100793-00 | 42 |  | 493 | 400 | 893 | 5 | ∞ | 15 | 35 |  |  |  |  | P01844 (USD) |  | ✅ Sufficient
100794 | [100794] tF C-100 CCU Enclosure Holder | ICO Mold LLC | 030-100794-00 | 42 |  | 410 | 464 | 874 | 5 | ∞ | 15 | 35 |  |  |  |  | P01844 (USD) |  | ✅ Sufficient
100795 | [100795] tF C-100 CCU Enclosure BOTTOM | ICO Mold LLC | 030-100795-00 | 42 |  | 153 | 1100 | 1253 | 55 | 22.8 | 165 | 385 |  |  |  |  | P01844 (USD) |  | ✅ Sufficient
100796 | [100796] tF C-100 CCU Enclosure Power | ICO Mold LLC | 030-100796-00 | 42 |  | 1943 | 700 | 2643 | 55 | 48.1 | 165 | 385 |  |  |  |  | P01844 (USD) |  | ✅ Sufficient
100797 | [100797] tF C-100 CCU Enclosure Interf | ICO Mold LLC | 100797 | 42 |  | 511 | 700 | 1211 | 55 | 22 | 165 | 385 |  |  |  |  | P01844 (USD) |  | ✅ Sufficient
🏭 ULINE, Sales ULINE — 1 parts ¦ 1 to order ¦ Est. $0
102020 | [102020] Wafer Seal Sticker 1.5in | ULINE, Sales ULINE |  | 1 |  | 0 | 0 | 0 | 200 | 0 | 600 | 1400 | 1400 | 7 | 2026-03-02 | -1 | pricelist |  | 🔴 CRITICAL — stock out in 0d, lead 1d — ORDER TODAY
🏭 Barcodes Inc. — 1 parts ¦ 1 to order ¦ Est. $123,033
101641 | [101641] 2 x 1 in Zebra label roll | Barcodes Inc. |  | 1 |  | 0 | 2 | 2 | 20 | 0.1 | 60 | 140 | 150 | 7.6 | 2026-03-04 | 2 | P01747 (CAD) | 123032.55 | 🟠 Order NOW — only 2d buffer
🏭 Globtek Inc. — 2 parts ¦ 2 to order ¦ Est. $6,132
101694 | [101694] USB Cable Type C to A - 2 Fe | Globtek Inc. |  | 1 |  | 91 | 0 | 91 | 100 | 0.9 | 300 | 700 | 650 | 7.4 | 2026-03-28 | 26 | P00730 (USD) | 5486 | 🟡 Order by 2026-03-28 — 26d buffer (lead 1d)
101663 | [101663] tf C2 Power Supply | Globtek Inc. |  | 0 |  | 659 | 0 | 659 | 100 | 6.6 | 300 | 700 | 50 | 7.1 | 2026-09-18 | 200 | P00730 (USD) | 645.5 | ⚠ CHECK LEAD TIME — 🟢 Order by 2026-09-18 — 200d buffer (lead 0d)
🏭 FrontierPC — 1 parts ¦ 1 to order ¦ Est. $22,907
101405 | [101405] Zebra 5095 High Performance B | FrontierPC |  | 1 |  | 0 | 25 | 25 | 20 | 1.2 | 60 | 140 | 150 | 8.8 | 2026-04-08 | 37 | P01747 (CAD) | 22906.83 | 🟡 Order by 2026-04-08 — 37d buffer (lead 1d)
🏭 Graphiscan — 3 parts ¦ 1 to order ¦ Est. $911
102128 | [102128] C2 USB Power Supply Box Sleev | Graphiscan |  | 0 |  | 197 | 0 | 197 | 100 | 2 | 300 | 700 | 550 | 7.5 | 2026-04-30 | 59 | P01554 (CAD) | 911.13 | ⚠ CHECK LEAD TIME — 🟢 Order by 2026-04-30 — 59d buffer (lead 0d)
101648 | [101648] tremoFlo C-100 User Manual, E | Graphiscan |  | 28 |  | 139 | 10 | 149 | 20 | 7.5 | 60 | 140 |  |  |  |  | P01859 (CAD) |  | ✅ Sufficient
101653 | [101653] tremoFlo C-100 User Manual, U | Graphiscan |  | 28 |  | 240 | 0 | 240 |  | ∞ | 0 | 0 |  |  |  |  | P01859 (CAD) |  | ✅ Sufficient
🏭 Sinpro Electronics — 1 parts ¦ 1 to order ¦ Est. $10,100
101557 | [101557] Medical Grade Power Supply fo | Sinpro Electronics |  | 84 |  | 494 | 500 | 994 | 195 | 5.1 | 585 | 1365 | 400 | 7.1 | 2026-05-12 | 71 | P01845 (USD) | 10100 | 🟢 Order by 2026-05-12 — 71d buffer (lead 84d)
🏭 Infinite Cables — 5 parts ¦ 3 to order ¦ Est. $4,262
101322 | [101322] CABLE, ETHERNET CAT5E, WHITE, | Infinite Cables | CAT5E-07WH | 7 |  | 524 | 0 | 524 | 195 | 2.7 | 585 | 1365 | 850 | 7 | 2026-05-15 | 74 | P01629 (CAD) | 2000.05 | 🟢 Order by 2026-05-15 — 74d buffer (lead 7d)
101113 | [101113] Power Cord, Type I (AS/NZS 31 | Infinite Cables |  | 7 |  | 26 | 0 | 26 | 5 | 5.2 | 15 | 35 | 50 | 15.2 | 2026-07-31 | 151 | P01538 (CAD) | 207.81 | 🟢 Order by 2026-07-31 — 151d buffer (lead 7d)
101073 | [101073] Medical Grade Power Cord PWL- | Infinite Cables |  | 7 |  | 279 | 560 | 839 | 150 | 5.6 | 450 | 1050 | 250 | 7.3 | 2026-08-12 | 163 | P01888 (CAD) | 2054.32 | 🟢 Order by 2026-08-12 — 163d buffer (lead 7d)
101110 | [101110] Power Cord, Type E/F (CEE 7/7 | Infinite Cables |  | 7 |  | 515 | 560 | 1075 | 125 | 8.6 | 375 | 875 |  |  |  |  | P01888 (CAD) |  | ✅ Sufficient
101111 | [101111] Power Cord 2.5M, 1.0mm^2 H05V | Infinite Cables |  | 7 |  | 11 | 0 | 11 |  | ∞ | 0 | 0 |  |  |  |  | P01303 (CAD) |  | ✅ Sufficient
🏭 Xometry, Ethan Beum — 2 parts ¦ 2 to order ¦ Est. $17,435
101753 | [101753] tf C-100 Test Load adapter Vi | Xometry, Ethan Beum |  | 1 |  | 124 | 0 | 124 | 50 | 2.5 | 150 | 350 | 250 | 7.5 | 2026-05-15 | 74 | P01405 (CAD) | 6043.82 | 🟢 Order by 2026-05-15 — 74d buffer (lead 1d)
101755 | [101755] tf C-100 Filter interface Vit | Xometry, Ethan Beum |  | 1 |  | 125 | 0 | 125 | 50 | 2.5 | 150 | 350 | 250 | 7.5 | 2026-05-16 | 75 | P01405 (CAD) | 11391.3 | 🟢 Order by 2026-05-16 — 75d buffer (lead 1d)
🏭 Laiju Bag — 1 parts ¦ 1 to order ¦ Est. $760
102195 | [102195] tf C100 Dust Cover | Laiju Bag |  | 1 |  | 46 | 0 | 46 | 15 | 3.1 | 45 | 105 | 100 | 9.7 | 2026-06-02 | 92 | P01422 (USD) | 760 | 🟢 Order by 2026-06-02 — 92d buffer (lead 1d)
🏭 Quail Electronics — 1 parts ¦ 1 to order ¦ Est. $340
101604 | [101604] Power Cord 2.0M Black, IS 653 | Quail Electronics | 9840.079 | 28 |  | 61 | 0 | 61 | 15 | 4.1 | 45 | 105 | 50 | 7.4 | 2026-06-05 | 95 | P00878 (CAD) | 339.76 | 🟢 Order by 2026-06-05 — 95d buffer (lead 28d)
🏭 Radicom — 1 parts ¦ 1 to order ¦ Est. $29,321
102584 | [102584] USB to Ethernet Adapter (incl | Radicom |  | 28 |  | 156 | 353 | 509 | 125 | 4.1 | 375 | 875 | 400 | 7.3 | 2026-06-05 | 95 | P01880 (CAD) | 29321.2 | 🟢 Order by 2026-06-05 — 95d buffer (lead 28d)
🏭 Net Burner — 1 parts ¦ 0 to order ¦ Est. $0
100159 | [100159] NetBurner Ethernet Core Modul | Net Burner | MOD5234-200IR | 21 |  | 323 | 300 | 623 | 55 | 11.3 | 165 | 385 |  |  |  |  | P01841 (USD) |  | ✅ Sufficient
🏭 NEL Technologies — 1 parts ¦ 0 to order ¦ Est. $0
100345 | [100345] TremoFlo C-100 Pneumotach Hea | NEL Technologies | NEL-2018-1743-HA | 42 |  | 490 | 400 | 890 | 55 | 16.2 | 165 | 385 |  |  |  |  | P01886 (USD) |  | ✅ Sufficient
🏭 Minco — 1 parts ¦ 0 to order ¦ Est. $0
100346 | [100346] TremoFlo C-100 Pneumotach RTD | Minco | S100725PFYT24B | 42 |  | 443 | 400 | 843 | 55 | 15.3 | 165 | 385 |  |  |  |  | P01886 (USD) |  | ✅ Sufficient
🏭 Custom Sheet Metal Products (CSTM) — 1 parts ¦ 0 to order ¦ Est. $0
100359 | [100359] TremoFlo C-100 CU Metal Enclo | Custom Sheet Metal P | 100359 | 70 |  | 226 | 300 | 526 | 55 | 9.6 | 165 | 385 |  |  |  |  | P01840 (CAD) |  | ✅ Sufficient
🏭 SMT Hautes Technologies — 7 parts ¦ 0 to order ¦ Est. $0
100477 | [100477] tremoFlo C-100 Mezzanine PCBA | SMT Hautes Technolog | 100477 | 70 |  | 79 | 1340 | 1419 | 55 | 25.8 | 165 | 385 |  |  |  |  | P01746 (USD) |  | ✅ Sufficient
100479 | [100479] TremoFlo C-100 Handheld Main | SMT Hautes Technolog |  | 119 |  | 61 | 1438 | 1499 | 55 | 27.3 | 165 | 385 |  |  |  |  | P01746 (USD) |  | ✅ Sufficient
100480 | [100480] TremoFlo C-100 Handheld Posit | SMT Hautes Technolog |  | 119 |  | 175 | 1481 | 1656 | 55 | 30.1 | 165 | 385 |  |  |  |  | P01746 (USD) |  | ✅ Sufficient
100481 | [100481] TremoFlo C-100 Handheld Ring | SMT Hautes Technolog |  | 119 |  | 87 | 1299 | 1386 | 55 | 25.2 | 165 | 385 |  |  |  |  | P01746 (USD) |  | ✅ Sufficient
101106 | [101106] TremoFlo C100 Custom made cab | SMT Hautes Technolog | 101106 | 112 |  | 278 | 1002 | 1280 | 55 | 23.3 | 165 | 385 |  |  |  |  | P01838 (CAD) |  | ✅ Sufficient
101532 | [101532] PCBA TFC100 NB-SBC | SMT Hautes Technolog | 101532 | 70 |  | 97 | 1404 | 1501 | 55 | 27.3 | 165 | 385 |  |  |  |  | P01746 (USD) |  | ✅ Sufficient
101535 | [101535] PCBA tF C-100 Connector Board | SMT Hautes Technolog | 101535 | 70 |  | 44 | 1265 | 1309 | 55 | 23.8 | 165 | 385 |  |  |  |  | P01746 (USD) |  | ✅ Sufficient
🏭 E-Sonic — 2 parts ¦ 0 to order ¦ Est. $0
100866 | [100866] THERMOSTAT 50 DEG NC TO-220 A | E-Sonic | 67L050 | 14 |  | 337 | 400 | 737 | 55 | 13.4 | 165 | 385 |  |  |  |  | P01595 (CAD) |  | ✅ Sufficient
101393 | [101393] MOTOR THERMAL SWITCH [O53GAB1 | E-Sonic | O53GAB140A-125Y | 14 |  | 620 | 400 | 1020 | 55 | 18.5 | 165 | 385 |  |  |  |  | P01873 (CAD) |  | ✅ Sufficient
🏭 Moticont — 1 parts ¦ 0 to order ¦ Est. $0
101278 | [101278] tf C100 Motor Assembly VCA | Moticont | LVCM-016-019-01 | 28 |  | 531 | 400 | 931 | 55 | 16.9 | 165 | 385 |  |  |  |  | P01885 (USD) |  | ✅ Sufficient
🏭 Bogen Magnetics GmbH Magnetics — 1 parts ¦ 0 to order ¦ Est. $0
101498 | [101498] Magnetic strip 24mm | Bogen Magnetics GmbH |  | 1 |  | 1756 | 0 | 1756 | 55 | 31.9 | 165 | 385 |  |  |  |  | P01674 (USD) |  | ✅ Sufficient
🏭 The ZPS Store — 1 parts ¦ 0 to order ¦ Est. $0
101520 | [101520] 2.5 x 4 in. polyester Label r | The ZPS Store |  | 0 |  | 0 | 6 | 6 |  | ∞ | 0 | 0 |  |  |  |  | P01610 (CAD) |  | ⚠ CHECK LEAD TIME — ✅ Sufficient

## 🔧 Buildable Units
Buildable Units — How Many Devices Can We Build Right Now?
Stock Only = physical stock now ¦ +Incoming = stock + all open PO receipts expected
Ref | Finished Product | Monthly Plan | Max Build (Stock Only) | Months Coverage | Max Build (+Incoming) | Months Coverage | Limiting Component (Stock Only) | Limiting Component (+Incoming)
101485 | tremoflo C-100 Airwave Oscillometry Syst | 5 | 0 | 0.0 mo | 0 | 0.0 mo | 101405 — [101405] Zebra 5095 High Perform (0 avail / 1.000/unit = 0 units) | 101610 — [101610] tF Power Supply & Cord (0 avail / 1.000/unit = 0 units)
101524 | tremoflo C-100 Airwave Oscillometry Syst | 0 | 0 | ∞ mo | 0 | ∞ mo | 101610 — [101610] tF Power Supply & Cord (0 avail / 1.000/unit = 0 units) | 101610 — [101610] tF Power Supply & Cord (0 avail / 1.000/unit = 0 units)
101761 | tf C-100 Kit Vitalograph - Clinical Tria | 25 | 44 | 1.8 mo | 54 | 2.2 mo | 101535 — [101535] PCBA tF C-100 Connector (44 avail / 1.000/unit = 44 units) | 101746 — [101746] tf C-100 HHU_NAME PLATE (54 avail / 1.000/unit = 54 units)
101762 | tf C-100 Kit Vitalograph - Healthcare Ed | 0 | 0 | ∞ mo | 2 | ∞ mo | 101405 — [101405] Zebra 5095 High Perform (0 avail / 1.000/unit = 0 units) | 101641 — [101641] 2 x 1 in Zebra label ro (2 avail / 1.000/unit = 2 units)
101963 | tremoflo C-100 Airwave Oscillometry Syst | 15 | 0 | 0.0 mo | 0 | 0.0 mo | 101405 — [101405] Zebra 5095 High Perform (0 avail / 1.000/unit = 0 units) | 101610 — [101610] tF Power Supply & Cord (0 avail / 1.000/unit = 0 units)
101969 | tremoflo C-100 Airwave Oscillometry Syst | 0 | 0 | ∞ mo | 0 | ∞ mo | 101405 — [101405] Zebra 5095 High Perform (0 avail / 1.000/unit = 0 units) | 101610 — [101610] tF Power Supply & Cord (0 avail / 1.000/unit = 0 units)
102002 | tremoflo C-100 Airwave Oscillometry Syst | 0 | 0 | ∞ mo | 0 | ∞ mo | 101405 — [101405] Zebra 5095 High Perform (0 avail / 1.000/unit = 0 units) | 101610 — [101610] tF Power Supply & Cord (0 avail / 1.000/unit = 0 units)
102003 | tremoflo C-100 Airwave Oscillometry Syst | 0 | 0 | ∞ mo | 0 | ∞ mo | 101405 — [101405] Zebra 5095 High Perform (0 avail / 1.000/unit = 0 units) | 101610 — [101610] tF Power Supply & Cord (0 avail / 1.000/unit = 0 units)
102005 | tremoflo C-100 Airwave Oscillometry Syst | 0 | 0 | ∞ mo | 0 | ∞ mo | 101405 — [101405] Zebra 5095 High Perform (0 avail / 1.000/unit = 0 units) | 101610 — [101610] tF Power Supply & Cord (0 avail / 1.000/unit = 0 units)
102036 | tremoflo C2 Airwave Oscillometry System | 100 | 0 | 0.0 mo | 0 | 0.0 mo | 102020 — [102020] Wafer Seal Sticker 1.5i (0 avail / 2.000/unit = 0 units) | 102020 — [102020] Wafer Seal Sticker 1.5i (0 avail / 2.000/unit = 0 units)
102181 | tf C-100 Kit Vitalograph - Healthcare US | 25 | 44 | 1.8 mo | 54 | 2.2 mo | 101535 — [101535] PCBA tF C-100 Connector (44 avail / 1.000/unit = 44 units) | 101746 — [101746] tf C-100 HHU_NAME PLATE (54 avail / 1.000/unit = 54 units)
102585 | tremoflo C-100 Airwave Oscillometry Syst | 125 | 0 | 0.0 mo | 0 | 0.0 mo | 101610 — [101610] tF Power Supply & Cord (0 avail / 1.000/unit = 0 units) | 101610 — [101610] tF Power Supply & Cord (0 avail / 1.000/unit = 0 units)
101485 — tremoflo C-100 Airwave Oscillometry Sy ¦ Monthly: 5 ¦ Max buildable (stock): 0 ¦ Max buildable (+incoming): 25
Ref | Component | Qty/Unit | Stock | Incoming | Total | Build(Stock) | Build(+Inc)
101405 | [101405] Zebra 5095 High Performance B | 1 | 0 | 25 | 25 | 0 | 25
100978 | [100978] tF C100 PFT Filter Interface | 1 | 0 | 2 | 2 | 0 | 2
101641 | [101641] 2 x 1 in Zebra label roll | 1 | 0 | 2 | 2 | 0 | 2
101610 | [101610] tF Power Supply & Cord Box - | 1 | 0 | 0 | 0 | 0 | 0
101109 | [101109] Test Load Adaptor - Suregard | 1 | 9 | 0 | 9 | 9 | 9
101113 | [101113] Power Cord, Type I (AS/NZS 31 | 1 | 26 | 0 | 26 | 26 | 26
101535 | [101535] PCBA tF C-100 Connector Board | 1 | 44 | 1265 | 1309 | 44 | 1309
100479 | [100479] TremoFlo C-100 Handheld Main | 1 | 61 | 1438 | 1499 | 61 | 1499
100477 | [100477] tremoFlo C-100 Mezzanine PCBA | 1 | 79 | 1340 | 1419 | 79 | 1419
100481 | [100481] TremoFlo C-100 Handheld Ring | 1 | 87 | 1299 | 1386 | 87 | 1386
101532 | [101532] PCBA TFC100 NB-SBC | 1 | 97 | 1404 | 1501 | 97 | 1501
100318 | [100318] TremoFlo C-100 Motor Bobbin | 1 | 111 | 900 | 1011 | 111 | 1011
101540 | [101540] tF C-100 Pneumotach Main Body | 1 | 118 | 928 | 1046 | 118 | 1046
100348 | [100348] TremoFlo C-100 Motor Piston M | 1 | 136 | 750 | 886 | 136 | 886
101648 | [101648] tremoFlo C-100 User Manual, E | 1 | 139 | 10 | 149 | 139 | 149
101524 — tremoflo C-100 Airwave Oscillometry Sy ¦ Monthly: 0 ¦ Max buildable (stock): 0 ¦ Max buildable (+incoming): 0
Ref | Component | Qty/Unit | Stock | Incoming | Total | Build(Stock) | Build(+Inc)
101610 | [101610] tF Power Supply & Cord Box - | 1 | 0 | 0 | 0 | 0 | 0
101653 | [101653] tremoFlo C-100 User Manual, U | 1 | 240 | 0 | 240 | 240 | 240
101595 | [101595] tF C100 Test Load Adapter - C | 1 | 249 | 459 | 708 | 249 | 708
101612 | [101612] tF C-100 Shipper Box Carton o | 1 | 265 | 610 | 875 | 265 | 875
101073 | [101073] Medical Grade Power Cord PWL- | 1 | 279 | 560 | 839 | 279 | 839
101557 | [101557] Medical Grade Power Supply fo | 1 | 494 | 500 | 994 | 494 | 994
101322 | [101322] CABLE, ETHERNET CAT5E, WHITE, | 1 | 524 | 0 | 524 | 524 | 524
101761 — tf C-100 Kit Vitalograph - Clinical Tr ¦ Monthly: 25 ¦ Max buildable (stock): 44 ¦ Max buildable (+incoming): 1309
Ref | Component | Qty/Unit | Stock | Incoming | Total | Build(Stock) | Build(+Inc)
101535 | [101535] PCBA tF C-100 Connector Board | 1 | 44 | 1265 | 1309 | 44 | 1309
101746 | [101746] tf C-100 HHU_NAME PLATE - Vit | 1 | 54 | 0 | 54 | 54 | 54
101749 | [101749] tf C-100 HHU BACK SHELL - Vit | 1 | 59 | 0 | 59 | 59 | 59
101745 | [101745] tf C-100 HHU FRONT CAP - Vita | 1 | 61 | 0 | 61 | 61 | 61
101747 | [101747] tf C-100 CCU Enclosure Holder | 1 | 61 | 0 | 61 | 61 | 61
100479 | [100479] TremoFlo C-100 Handheld Main | 1 | 61 | 1438 | 1499 | 61 | 1499
101748 | [101748] tf C-100 CCU Enclosure front | 1 | 62 | 0 | 62 | 62 | 62
101744 | [101744] tf C-100 HHU LOOVER PLATE - V | 1 | 63 | 0 | 63 | 63 | 63
100477 | [100477] tremoFlo C-100 Mezzanine PCBA | 1 | 79 | 1340 | 1419 | 79 | 1419
100481 | [100481] TremoFlo C-100 Handheld Ring | 1 | 87 | 1299 | 1386 | 87 | 1386
101532 | [101532] PCBA TFC100 NB-SBC | 1 | 97 | 1404 | 1501 | 97 | 1501
100318 | [100318] TremoFlo C-100 Motor Bobbin | 1 | 111 | 900 | 1011 | 111 | 1011
101540 | [101540] tF C-100 Pneumotach Main Body | 1 | 118 | 928 | 1046 | 118 | 1046
101793 | [101793] tf Shipper Box - Vitalograph | 1 | 121 | 0 | 121 | 121 | 121
101753 | [101753] tf C-100 Test Load adapter Vi | 1 | 124 | 0 | 124 | 124 | 124
101762 — tf C-100 Kit Vitalograph - Healthcare ¦ Monthly: 0 ¦ Max buildable (stock): 0 ¦ Max buildable (+incoming): 25
Ref | Component | Qty/Unit | Stock | Incoming | Total | Build(Stock) | Build(+Inc)
101405 | [101405] Zebra 5095 High Performance B | 1 | 0 | 25 | 25 | 0 | 25
101641 | [101641] 2 x 1 in Zebra label roll | 1 | 0 | 2 | 2 | 0 | 2
101535 | [101535] PCBA tF C-100 Connector Board | 1 | 44 | 1265 | 1309 | 44 | 1309
101746 | [101746] tf C-100 HHU_NAME PLATE - Vit | 1 | 54 | 0 | 54 | 54 | 54
101749 | [101749] tf C-100 HHU BACK SHELL - Vit | 1 | 59 | 0 | 59 | 59 | 59
101745 | [101745] tf C-100 HHU FRONT CAP - Vita | 1 | 61 | 0 | 61 | 61 | 61
101747 | [101747] tf C-100 CCU Enclosure Holder | 1 | 61 | 0 | 61 | 61 | 61
100479 | [100479] TremoFlo C-100 Handheld Main | 1 | 61 | 1438 | 1499 | 61 | 1499
101748 | [101748] tf C-100 CCU Enclosure front | 1 | 62 | 0 | 62 | 62 | 62
101744 | [101744] tf C-100 HHU LOOVER PLATE - V | 1 | 63 | 0 | 63 | 63 | 63
100477 | [100477] tremoFlo C-100 Mezzanine PCBA | 1 | 79 | 1340 | 1419 | 79 | 1419
100481 | [100481] TremoFlo C-100 Handheld Ring | 1 | 87 | 1299 | 1386 | 87 | 1386
101532 | [101532] PCBA TFC100 NB-SBC | 1 | 97 | 1404 | 1501 | 97 | 1501
100318 | [100318] TremoFlo C-100 Motor Bobbin | 1 | 111 | 900 | 1011 | 111 | 1011
101540 | [101540] tF C-100 Pneumotach Main Body | 1 | 118 | 928 | 1046 | 118 | 1046
101963 — tremoflo C-100 Airwave Oscillometry Sy ¦ Monthly: 15 ¦ Max buildable (stock): 0 ¦ Max buildable (+incoming): 25
Ref | Component | Qty/Unit | Stock | Incoming | Total | Build(Stock) | Build(+Inc)
101405 | [101405] Zebra 5095 High Performance B | 1 | 0 | 25 | 25 | 0 | 25
101641 | [101641] 2 x 1 in Zebra label roll | 1 | 0 | 2 | 2 | 0 | 2
101610 | [101610] tF Power Supply & Cord Box - | 1 | 0 | 0 | 0 | 0 | 0
102195 | [102195] tf C100 Dust Cover | 1 | 46 | 0 | 46 | 46 | 46
101604 | [101604] Power Cord 2.0M Black, IS 653 | 1 | 61 | 0 | 61 | 61 | 61
101648 | [101648] tremoFlo C-100 User Manual, E | 1 | 139 | 10 | 149 | 139 | 149
101595 | [101595] tF C100 Test Load Adapter - C | 1 | 249 | 459 | 708 | 249 | 708
101612 | [101612] tF C-100 Shipper Box Carton o | 1 | 265 | 610 | 875 | 265 | 875
101557 | [101557] Medical Grade Power Supply fo | 1 | 494 | 500 | 994 | 494 | 994
101322 | [101322] CABLE, ETHERNET CAT5E, WHITE, | 1 | 524 | 0 | 524 | 524 | 524
101969 — tremoflo C-100 Airwave Oscillometry Sy ¦ Monthly: 0 ¦ Max buildable (stock): 0 ¦ Max buildable (+incoming): 25
Ref | Component | Qty/Unit | Stock | Incoming | Total | Build(Stock) | Build(+Inc)
101405 | [101405] Zebra 5095 High Performance B | 1 | 0 | 25 | 25 | 0 | 25
101641 | [101641] 2 x 1 in Zebra label roll | 1 | 0 | 2 | 2 | 0 | 2
101610 | [101610] tF Power Supply & Cord Box - | 1 | 0 | 0 | 0 | 0 | 0
101648 | [101648] tremoFlo C-100 User Manual, E | 1 | 139 | 10 | 149 | 139 | 149
101595 | [101595] tF C100 Test Load Adapter - C | 1 | 249 | 459 | 708 | 249 | 708
101612 | [101612] tF C-100 Shipper Box Carton o | 1 | 265 | 610 | 875 | 265 | 875
101073 | [101073] Medical Grade Power Cord PWL- | 1 | 279 | 560 | 839 | 279 | 839
101557 | [101557] Medical Grade Power Supply fo | 1 | 494 | 500 | 994 | 494 | 994
101322 | [101322] CABLE, ETHERNET CAT5E, WHITE, | 1 | 524 | 0 | 524 | 524 | 524
102002 — tremoflo C-100 Airwave Oscillometry Sy ¦ Monthly: 0 ¦ Max buildable (stock): 0 ¦ Max buildable (+incoming): 25
Ref | Component | Qty/Unit | Stock | Incoming | Total | Build(Stock) | Build(+Inc)
101405 | [101405] Zebra 5095 High Performance B | 1 | 0 | 25 | 25 | 0 | 25
101641 | [101641] 2 x 1 in Zebra label roll | 1 | 0 | 2 | 2 | 0 | 2
101610 | [101610] tF Power Supply & Cord Box - | 1 | 0 | 0 | 0 | 0 | 0
101111 | [101111] Power Cord 2.5M, 1.0mm^2 H05V | 1 | 11 | 0 | 11 | 11 | 11
101648 | [101648] tremoFlo C-100 User Manual, E | 1 | 139 | 10 | 149 | 139 | 149
101595 | [101595] tF C100 Test Load Adapter - C | 1 | 249 | 459 | 708 | 249 | 708
101612 | [101612] tF C-100 Shipper Box Carton o | 1 | 265 | 610 | 875 | 265 | 875
101557 | [101557] Medical Grade Power Supply fo | 1 | 494 | 500 | 994 | 494 | 994
101322 | [101322] CABLE, ETHERNET CAT5E, WHITE, | 1 | 524 | 0 | 524 | 524 | 524
102003 — tremoflo C-100 Airwave Oscillometry Sy ¦ Monthly: 0 ¦ Max buildable (stock): 0 ¦ Max buildable (+incoming): 25
Ref | Component | Qty/Unit | Stock | Incoming | Total | Build(Stock) | Build(+Inc)
101405 | [101405] Zebra 5095 High Performance B | 1 | 0 | 25 | 25 | 0 | 25
101641 | [101641] 2 x 1 in Zebra label roll | 1 | 0 | 2 | 2 | 0 | 2
101610 | [101610] tF Power Supply & Cord Box - | 1 | 0 | 0 | 0 | 0 | 0
101648 | [101648] tremoFlo C-100 User Manual, E | 1 | 139 | 10 | 149 | 139 | 149
101595 | [101595] tF C100 Test Load Adapter - C | 1 | 249 | 459 | 708 | 249 | 708
101612 | [101612] tF C-100 Shipper Box Carton o | 1 | 265 | 610 | 875 | 265 | 875
101557 | [101557] Medical Grade Power Supply fo | 1 | 494 | 500 | 994 | 494 | 994
101110 | [101110] Power Cord, Type E/F (CEE 7/7 | 1 | 515 | 560 | 1075 | 515 | 1075
101322 | [101322] CABLE, ETHERNET CAT5E, WHITE, | 1 | 524 | 0 | 524 | 524 | 524
102005 — tremoflo C-100 Airwave Oscillometry Sy ¦ Monthly: 0 ¦ Max buildable (stock): 0 ¦ Max buildable (+incoming): 25
Ref | Component | Qty/Unit | Stock | Incoming | Total | Build(Stock) | Build(+Inc)
101405 | [101405] Zebra 5095 High Performance B | 1 | 0 | 25 | 25 | 0 | 25
101641 | [101641] 2 x 1 in Zebra label roll | 1 | 0 | 2 | 2 | 0 | 2
101610 | [101610] tF Power Supply & Cord Box - | 1 | 0 | 0 | 0 | 0 | 0
101648 | [101648] tremoFlo C-100 User Manual, E | 1 | 139 | 10 | 149 | 139 | 149
101595 | [101595] tF C100 Test Load Adapter - C | 1 | 249 | 459 | 708 | 249 | 708
101612 | [101612] tF C-100 Shipper Box Carton o | 1 | 265 | 610 | 875 | 265 | 875
101557 | [101557] Medical Grade Power Supply fo | 1 | 494 | 500 | 994 | 494 | 994
101110 | [101110] Power Cord, Type E/F (CEE 7/7 | 1 | 515 | 560 | 1075 | 515 | 1075
101322 | [101322] CABLE, ETHERNET CAT5E, WHITE, | 1 | 524 | 0 | 524 | 524 | 524
102036 — tremoflo C2 Airwave Oscillometry Syste ¦ Monthly: 100 ¦ Max buildable (stock): 0 ¦ Max buildable (+incoming): 0
Ref | Component | Qty/Unit | Stock | Incoming | Total | Build(Stock) | Build(+Inc)
102020 | [102020] Wafer Seal Sticker 1.5in | 2 | 0 | 0 | 0 | 0 | 0
101694 | [101694] USB Cable Type C to A - 2 Fe | 1 | 91 | 0 | 91 | 91 | 91
102128 | [102128] C2 USB Power Supply Box Sleev | 1 | 197 | 0 | 197 | 197 | 197
101663 | [101663] tf C2 Power Supply | 1 | 659 | 0 | 659 | 659 | 659
102181 — tf C-100 Kit Vitalograph - Healthcare ¦ Monthly: 25 ¦ Max buildable (stock): 44 ¦ Max buildable (+incoming): 1309
Ref | Component | Qty/Unit | Stock | Incoming | Total | Build(Stock) | Build(+Inc)
101535 | [101535] PCBA tF C-100 Connector Board | 1 | 44 | 1265 | 1309 | 44 | 1309
101746 | [101746] tf C-100 HHU_NAME PLATE - Vit | 1 | 54 | 0 | 54 | 54 | 54
101749 | [101749] tf C-100 HHU BACK SHELL - Vit | 1 | 59 | 0 | 59 | 59 | 59
101745 | [101745] tf C-100 HHU FRONT CAP - Vita | 1 | 61 | 0 | 61 | 61 | 61
101747 | [101747] tf C-100 CCU Enclosure Holder | 1 | 61 | 0 | 61 | 61 | 61
100479 | [100479] TremoFlo C-100 Handheld Main | 1 | 61 | 1438 | 1499 | 61 | 1499
101748 | [101748] tf C-100 CCU Enclosure front | 1 | 62 | 0 | 62 | 62 | 62
101744 | [101744] tf C-100 HHU LOOVER PLATE - V | 1 | 63 | 0 | 63 | 63 | 63
100477 | [100477] tremoFlo C-100 Mezzanine PCBA | 1 | 79 | 1340 | 1419 | 79 | 1419
100481 | [100481] TremoFlo C-100 Handheld Ring | 1 | 87 | 1299 | 1386 | 87 | 1386
101532 | [101532] PCBA TFC100 NB-SBC | 1 | 97 | 1404 | 1501 | 97 | 1501
100318 | [100318] TremoFlo C-100 Motor Bobbin | 1 | 111 | 900 | 1011 | 111 | 1011
101540 | [101540] tF C-100 Pneumotach Main Body | 1 | 118 | 928 | 1046 | 118 | 1046
101753 | [101753] tf C-100 Test Load adapter Vi | 1 | 124 | 0 | 124 | 124 | 124
101755 | [101755] tf C-100 Filter interface Vit | 1 | 125 | 0 | 125 | 125 | 125
102585 — tremoflo C-100 Airwave Oscillometry Sy ¦ Monthly: 125 ¦ Max buildable (stock): 0 ¦ Max buildable (+incoming): 0
Ref | Component | Qty/Unit | Stock | Incoming | Total | Build(Stock) | Build(+Inc)
101610 | [101610] tF Power Supply & Cord Box - | 1 | 0 | 0 | 0 | 0 | 0
102584 | [102584] USB to Ethernet Adapter (incl | 1 | 156 | 353 | 509 | 156 | 509
101595 | [101595] tF C100 Test Load Adapter - C | 1 | 249 | 459 | 708 | 249 | 708
101612 | [101612] tF C-100 Shipper Box Carton o | 1 | 265 | 610 | 875 | 265 | 875
101073 | [101073] Medical Grade Power Cord PWL- | 1 | 279 | 560 | 839 | 279 | 839
101557 | [101557] Medical Grade Power Supply fo | 1 | 494 | 500 | 994 | 494 | 994
101110 | [101110] Power Cord, Type E/F (CEE 7/7 | 1 | 515 | 560 | 1075 | 515 | 1075
101322 | [101322] CABLE, ETHERNET CAT5E, WHITE, | 1 | 524 | 0 | 524 | 524 | 524