## 📊 Summary
Component PO Plan — Executive Summary
Production rate (monthly) | 101485: 5/mo 101524: 10/mo 101761: 25/mo 101762: 25/mo 101769: 5/mo 101711: 40/mo 102239: 5/mo 102240: 5/mo 101963: 15/mo 101969: 1/mo 102002: 1/mo 102003: 10/mo 102005: 1/mo 102036: 100/mo 102181: 25/mo 102585: 125/mo
Coverage target | 7 months
Reorder point | 3 months coverage remaining
Order qty rounding | Round up to nearest 50
Generated | 2026-03-02 23:24 UTC
Total components in scope | 112
🔴 ORDER NOW (overdue) | 13
🟠 Order within 14 days | 1
🟡 Plan ahead (order date upcoming) | 68
✅ Sufficient stock | 30
⚠ No supplier configured | 0
⚠ Lead time = 0 (needs review) | 5
💰 Estimated total PO value | $1,402,040
Supplier | Parts | To Order | Urgent | Est. Value
Custom Sheet Metal Products (CSTM) | 2 | 2 | 1 | $99,643
Alloy Concepts | 22 | 20 | 4 | $401,773
Lovepac | 4 | 3 | 1 | $12,068
ICO Mold LLC | 28 | 21 | 6 | $79,070
ULINE, Sales ULINE | 1 | 1 | 1 | N/A
Globtek Inc. | 2 | 2 | 0 | $6,132
Sinpro Electronics | 1 | 1 | 0 | $18,938
SMT Hautes Technologies | 11 | 7 | 0 | $239,916
Xometry, Ethan Beum | 2 | 2 | 0 | $29,105
Atlas Gaskets | 4 | 3 | 0 | $2,681
Net Burner | 1 | 1 | 0 | $130,900
Infinite Cables | 5 | 3 | 0 | $5,497
Graphiscan | 3 | 2 | 0 | $2,212
Atlas Gaskets, Rebecca Lopez | 1 | 1 | 0 | $40
Minco | 1 | 1 | 0 | $24,210
Moticont | 1 | 1 | 0 | $256,116
NEL Technologies | 1 | 1 | 0 | $22,066
Alloy Concepts, Perry MacIssaac | 1 | 1 | 0 | $19,096
E-Sonic | 2 | 2 | 0 | $18,151
Laiju Bag | 1 | 1 | 0 | $760
Quail Electronics | 1 | 1 | 0 | $340
Radicom | 1 | 1 | 0 | $29,321
GEB General Electronics Battery Co | 1 | 1 | 0 | $802
OSD Displays | 1 | 1 | 0 | $1,440
ICO Mold LLC, Brian Bay | 6 | 1 | 0 | $63
Bogen Magnetics GmbH Magnetics | 1 | 1 | 0 | $1,701
FrontierPC | 1 | 0 | 0 | N/A
The ZPS Store | 1 | 0 | 0 | N/A
Barcodes Inc. | 1 | 0 | 0 | N/A
SEKI | 2 | 0 | 0 | N/A
Xometry | 1 | 0 | 0 | N/A
OSD Displays, Christopher Geisler | 1 | 0 | 0 | N/A

## 📋 PO Plan
Component PO Plan — 6-Month Rolling Coverage (112 components)
Rate: 101485×5 101524×10 101761×25 101762×25 101769×5 101711×40 102239×5 102240×5 101963×15 101969×1 102002×1 102003×10 102005×1 102036×100 102181×25 102585×125 /mo ¦ Target: 7mo ¦ Reorder at: 3mo ¦ Generated: 2026-03-02 23:24 UTC
Ref | Component Name | Supplier | Sup Code | Lead Days | Min Qty | Stock Avail | Open Incoming | Total Avail | Monthly Req | Coverage Now(mo) | Reorder Point | Target Qty(7mo) | ORDER QTY | Coverage After | Latest Safe Order Date | Buffer (days) | Price Source | Est Value (USD) | Status
🔴 ORDER NOW — 13 components (lead time already exceeded)
100359 | [100359] TremoFlo C-100 CU Metal Enclo | Custom Sheet Metal P | 100359 | 70 |  | 226 | 300 | 526 | 243 | 2.2 | 729 | 1701 | 1200 | 7.1 | 2026-03-02 | -4 | P01840 (CAD) | 99583.68 | 🔴 CRITICAL — stock out in 65d, lead 70d — ORDER TODAY
100641 | [100641] tF C100 Test Load Body | Alloy Concepts |  | 56 |  | 23 | 0 | 23 | 125 | 0.2 | 375 | 875 | 900 | 7.4 | 2026-03-02 | -50 | P01034 (CAD) | 23420.34 | 🔴 CRITICAL — stock out in 5d, lead 56d — ORDER TODAY
100642 | [100642] tF C100 Test Load Spacer | Alloy Concepts |  | 56 |  | 0 | 0 | 0 | 250 | 0 | 750 | 1750 | 1750 | 7 | 2026-03-02 | -56 | P01034 (CAD) | 19665.45 | 🔴 CRITICAL — stock out in 0d, lead 56d — ORDER TODAY
100978 | [100978] tF C100 PFT Filter Interface | Alloy Concepts |  | 56 |  | 0 | 2 | 2 | 5 | 0.4 | 15 | 35 | 50 | 10.4 | 2026-03-02 | -43 | P01883 (CAD) | 4123.3 | 🔴 CRITICAL — stock out in 12d, lead 56d — ORDER TODAY
101109 | [101109] Test Load Adaptor - Suregard | Alloy Concepts |  | 56 |  | 9 | 0 | 9 | 5 | 1.8 | 15 | 35 | 50 | 11.8 | 2026-03-02 | -1 | P00220 (CAD) | 1109.81 | 🔴 CRITICAL — stock out in 54d, lead 56d — ORDER TODAY
101610 | [101610] tF Power Supply & Cord Box - | Lovepac |  | 42 |  | 0 | 0 | 0 | 168 | 0 | 504 | 1176 | 1200 | 7.1 | 2026-03-02 | -42 | pricelist | 1476 | 🔴 CRITICAL — stock out in 0d, lead 42d — ORDER TODAY
101744 | [101744] tf C-100 HHU LOOVER PLATE - V | ICO Mold LLC |  | 42 |  | 63 | 0 | 63 | 75 | 0.8 | 225 | 525 | 500 | 7.5 | 2026-03-02 | -16 | P01432 (USD) | 6240 | 🔴 CRITICAL — stock out in 25d, lead 42d — ORDER TODAY
101745 | [101745] tf C-100 HHU FRONT CAP - Vita | ICO Mold LLC |  | 42 |  | 61 | 0 | 61 | 75 | 0.8 | 225 | 525 | 500 | 7.5 | 2026-03-02 | -17 | P01432 (USD) | 6300 | 🔴 CRITICAL — stock out in 24d, lead 42d — ORDER TODAY
101746 | [101746] tf C-100 HHU_NAME PLATE - Vit | ICO Mold LLC |  | 42 |  | 54 | 0 | 54 | 75 | 0.7 | 225 | 525 | 500 | 7.4 | 2026-03-02 | -20 | P01432 (USD) | 6240 | 🔴 CRITICAL — stock out in 21d, lead 42d — ORDER TODAY
101747 | [101747] tf C-100 CCU Enclosure Holder | ICO Mold LLC |  | 42 |  | 61 | 0 | 61 | 75 | 0.8 | 225 | 525 | 500 | 7.5 | 2026-03-02 | -17 | P01432 (USD) | 7150 | 🔴 CRITICAL — stock out in 24d, lead 42d — ORDER TODAY
101748 | [101748] tf C-100 CCU Enclosure front | ICO Mold LLC |  | 42 |  | 62 | 0 | 62 | 75 | 0.8 | 225 | 525 | 500 | 7.5 | 2026-03-02 | -16 | P01432 (USD) | 9630 | 🔴 CRITICAL — stock out in 25d, lead 42d — ORDER TODAY
101749 | [101749] tf C-100 HHU BACK SHELL - Vit | ICO Mold LLC |  | 42 |  | 59 | 0 | 59 | 75 | 0.8 | 225 | 525 | 500 | 7.5 | 2026-03-02 | -18 | P01432 (USD) | 11740 | 🔴 CRITICAL — stock out in 23d, lead 42d — ORDER TODAY
102020 | [102020] Wafer Seal Sticker 1.5in | ULINE, Sales ULINE |  | 1 |  | 0 | 0 | 0 | 200 | 0 | 600 | 1400 | 1400 | 7 | 2026-03-02 | -1 | pricelist |  | 🔴 CRITICAL — stock out in 0d, lead 1d — ORDER TODAY
🟠 ORDER WITHIN 14 DAYS — 1 components
100643 | [100643] tF C100 Test Load Cap | Alloy Concepts |  | 5 |  | 23 | 0 | 23 | 125 | 0.2 | 375 | 875 | 900 | 7.4 | 2026-03-02 | 0 | P01034 (CAD) | 22015.08 | 🟠 Order NOW — only 0d buffer
🟡 PLAN AHEAD — 68 components (order date upcoming)
101750 | [101750] tf C-100 CCU Enclosure Top - | ICO Mold LLC |  | 42 |  | 162 | 0 | 162 | 75 | 2.2 | 225 | 525 | 400 | 7.5 | 2026-03-25 | 23 | P01432 (USD) | 8896 | 🟡 Order by 2026-03-25 — 23d buffer (lead 42d)
101694 | [101694] USB Cable Type C to A - 2 Fe | Globtek Inc. |  | 1 |  | 91 | 0 | 91 | 100 | 0.9 | 300 | 700 | 650 | 7.4 | 2026-03-28 | 26 | P00730 (USD) | 5486 | 🟡 Order by 2026-03-28 — 26d buffer (lead 1d)
101557 | [101557] Medical Grade Power Supply fo | Sinpro Electronics |  | 84 |  | 494 | 500 | 994 | 243 | 4.1 | 729 | 1701 | 750 | 7.2 | 2026-04-11 | 40 | P01845 (USD) | 18937.5 | 🟡 Order by 2026-04-11 — 40d buffer (lead 84d)
101106 | [101106] TremoFlo C100 Custom made cab | SMT Hautes Technolog | 101106 | 112 |  | 278 | 1002 | 1280 | 243 | 5.3 | 729 | 1701 | 450 | 7.1 | 2026-04-19 | 48 | P01838 (CAD) | 25557.84 | 🟢 Order by 2026-04-19 — 48d buffer (lead 112d)
101753 | [101753] tf C-100 Test Load adapter Vi | Xometry, Ethan Beum |  | 1 |  | 124 | 0 | 124 | 75 | 1.7 | 225 | 525 | 450 | 7.7 | 2026-04-20 | 49 | P01405 (CAD) | 10878.89 | 🟢 Order by 2026-04-20 — 49d buffer (lead 1d)
101755 | [101755] tf C-100 Filter interface Vit | Xometry, Ethan Beum |  | 1 |  | 125 | 0 | 125 | 75 | 1.7 | 225 | 525 | 400 | 7 | 2026-04-20 | 49 | P01405 (CAD) | 18226.08 | 🟢 Order by 2026-04-20 — 49d buffer (lead 1d)
101683 | [101683] tf C2 - Pneumotach Mesh | Atlas Gaskets |  | 28 |  | 143 | 0 | 143 | 55 | 2.6 | 165 | 385 | 250 | 7.1 | 2026-04-22 | 51 | P01559 (USD) | 2362.5 | 🟢 Order by 2026-04-22 — 51d buffer (lead 28d)
100348 | [100348] TremoFlo C-100 Motor Piston M | Alloy Concepts | 100348 | 56 |  | 136 | 750 | 886 | 243 | 3.6 | 729 | 1701 | 850 | 7.1 | 2026-04-25 | 54 | P01745 (CAD) | 19639.33 | 🟢 Order by 2026-04-25 — 54d buffer (lead 56d)
100481 | [100481] TremoFlo C-100 Handheld Ring | SMT Hautes Technolog |  | 119 |  | 87 | 1299 | 1386 | 243 | 5.7 | 729 | 1701 | 350 | 7.1 | 2026-04-25 | 54 | P01746 (USD) | 32872 | 🟢 Order by 2026-04-25 — 54d buffer (lead 119d)
100159 | [100159] NetBurner Ethernet Core Modul | Net Burner | MOD5234-200IR | 21 |  | 323 | 300 | 623 | 243 | 2.6 | 729 | 1701 | 1100 | 7.1 | 2026-04-28 | 57 | P01841 (USD) | 130900 | 🟢 Order by 2026-04-28 — 57d buffer (lead 21d)
101322 | [101322] CABLE, ETHERNET CAT5E, WHITE, | Infinite Cables | CAT5E-07WH | 7 |  | 524 | 0 | 524 | 243 | 2.2 | 729 | 1701 | 1200 | 7.1 | 2026-04-29 | 58 | P01629 (CAD) | 2823.6 | 🟢 Order by 2026-04-29 — 58d buffer (lead 7d)
102128 | [102128] C2 USB Power Supply Box Sleev | Graphiscan |  | 0 |  | 197 | 0 | 197 | 100 | 2 | 300 | 700 | 550 | 7.5 | 2026-04-30 | 59 | P01554 (CAD) | 911.13 | ⚠ CHECK LEAD TIME — 🟢 Order by 2026-04-30 — 59d buffer (lead 0d)
101699 | [101699] tf C2 - Pneumotach Neck Foam | Atlas Gaskets, Rebec |  | 50 |  | 204 | 0 | 204 | 55 | 3.7 | 165 | 385 | 200 | 7.3 | 2026-05-03 | 62 | P00729 (USD) | 40 | 🟢 Order by 2026-05-03 — 62d buffer (lead 50d)
100346 | [100346] TremoFlo C-100 Pneumotach RTD | Minco | S100725PFYT24B | 42 |  | 443 | 400 | 843 | 243 | 3.5 | 729 | 1701 | 900 | 7.2 | 2026-05-04 | 63 | P01886 (USD) | 24210 | 🟢 Order by 2026-05-04 — 63d buffer (lead 42d)
100326 | [100326] TremoFlo C-100 Motor Piston O | Alloy Concepts | 100326 | 56 |  | 234 | 750 | 984 | 243 | 4 | 729 | 1701 | 750 | 7.1 | 2026-05-08 | 67 | P01745 (CAD) | 6448.8 | 🟢 Order by 2026-05-08 — 67d buffer (lead 56d)
101278 | [101278] tf C100 Motor Assembly VCA | Moticont | LVCM-016-019-01 | 28 |  | 531 | 400 | 931 | 298 | 3.1 | 894 | 2086 | 1200 | 7.2 | 2026-05-08 | 67 | P01885 (USD) | 256116 | 🟢 Order by 2026-05-08 — 67d buffer (lead 28d)
100479 | [100479] TremoFlo C-100 Handheld Main | SMT Hautes Technolog |  | 119 |  | 61 | 1438 | 1499 | 243 | 6.2 | 729 | 1701 | 250 | 7.2 | 2026-05-09 | 68 | P01746 (USD) | 23480 | 🟢 Order by 2026-05-09 — 68d buffer (lead 119d)
100345 | [100345] TremoFlo C-100 Pneumotach Hea | NEL Technologies | NEL-2018-1743-HA | 42 |  | 490 | 400 | 890 | 243 | 3.7 | 729 | 1701 | 850 | 7.2 | 2026-05-10 | 69 | P01886 (USD) | 22066 | 🟢 Order by 2026-05-10 — 69d buffer (lead 42d)
101541 | [101541] tF C-100 Pneumotach Heater Ri | Alloy Concepts | 101541 | 56 |  | 249 | 750 | 999 | 243 | 4.1 | 729 | 1701 | 750 | 7.2 | 2026-05-10 | 69 | P01745 (CAD) | 24767.25 | 🟢 Order by 2026-05-10 — 69d buffer (lead 56d)
100318 | [100318] TremoFlo C-100 Motor Bobbin | Alloy Concepts | 100318 | 56 |  | 111 | 900 | 1011 | 243 | 4.2 | 729 | 1701 | 700 | 7 | 2026-05-11 | 70 | P01745 (CAD) | 84080.08 | 🟢 Order by 2026-05-11 — 70d buffer (lead 56d)
101718 | [101718] tf C2 - Main Body CNC | Alloy Concepts, Perr |  | 56 |  | 228 | 5 | 233 | 55 | 4.2 | 165 | 385 | 200 | 7.9 | 2026-05-13 | 72 | P01635 (USD) | 19096 | 🟢 Order by 2026-05-13 — 72d buffer (lead 56d)
101540 | [101540] tF C-100 Pneumotach Main Body | Alloy Concepts | 101540 | 56 |  | 118 | 928 | 1046 | 243 | 4.3 | 729 | 1701 | 700 | 7.2 | 2026-05-16 | 75 | P01745 (CAD) | 44944.27 | 🟢 Order by 2026-05-16 — 75d buffer (lead 56d)
101595 | [101595] tF C100 Test Load Adapter - C | Alloy Concepts |  | 56 |  | 249 | 459 | 708 | 163 | 4.3 | 489 | 1141 | 450 | 7.1 | 2026-05-17 | 76 | P01828 (CAD) | 9895.91 | 🟢 Order by 2026-05-17 — 76d buffer (lead 56d)
100975 | [100975] tF C100 Pneumotach Inner Mesh | Alloy Concepts | 100975 | 56 |  | 169 | 900 | 1069 | 243 | 4.4 | 729 | 1701 | 650 | 7.1 | 2026-05-18 | 77 | P01745 (CAD) | 10549.04 | 🟢 Order by 2026-05-18 — 77d buffer (lead 56d)
100866 | [100866] THERMOSTAT 50 DEG NC TO-220 A | E-Sonic | 67L050 | 14 |  | 337 | 400 | 737 | 243 | 3 | 729 | 1701 | 1000 | 7.1 | 2026-05-19 | 78 | P01595 (CAD) | 7293.7 | 🟢 Order by 2026-05-19 — 78d buffer (lead 14d)
100977 | [100977] tF C100 Pneumotach Knob | Alloy Concepts | 100977 | 56 |  | 450 | 634 | 1084 | 243 | 4.5 | 729 | 1701 | 650 | 7.1 | 2026-05-20 | 79 | P01745 (CAD) | 14346.48 | 🟢 Order by 2026-05-20 — 79d buffer (lead 56d)
100321 | [100321] TremoFlo C-100 Motor Shaft | Alloy Concepts |  | 56 |  | 576 | 1611 | 2187 | 486 | 4.5 | 1458 | 3402 | 1250 | 7.1 | 2026-05-21 | 80 | P01745 (CAD) | 12489 | 🟢 Order by 2026-05-21 — 80d buffer (lead 56d)
100976 | [100976] tF C100 Pneumotach Outer Mesh | Alloy Concepts | 100976 | 56 |  | 197 | 900 | 1097 | 243 | 4.5 | 729 | 1701 | 650 | 7.2 | 2026-05-22 | 81 | P01745 (CAD) | 13584.16 | 🟢 Order by 2026-05-22 — 81d buffer (lead 56d)
101719 | [101719] tf C2 Piston CNC | Alloy Concepts |  | 56 |  | 248 | 5 | 253 | 55 | 4.6 | 165 | 385 | 150 | 7.3 | 2026-05-25 | 84 | P01635 (USD) | 8769 | 🟢 Order by 2026-05-25 — 84d buffer (lead 56d)
100480 | [100480] TremoFlo C-100 Handheld Posit | SMT Hautes Technolog |  | 119 |  | 175 | 1481 | 1656 | 243 | 6.8 | 729 | 1701 | 50 | 7 | 2026-05-29 | 88 | P01746 (USD) | 4696 | 🟢 Order by 2026-05-29 — 88d buffer (lead 119d)
100790 | [100790] tF C-100 HHU_STRAIN RELIEF In | ICO Mold LLC | 030-100790-00 | 42 |  | 383 | 1700 | 2083 | 486 | 4.3 | 1458 | 3402 | 1350 | 7.1 | 2026-05-29 | 88 | P01844 (USD) | 1498.5 | 🟢 Order by 2026-05-29 — 88d buffer (lead 42d)
101255 | [101255] tF C-100 Light Motor Back Pla | Alloy Concepts | 101255 | 56 |  | 457 | 696 | 1153 | 243 | 4.7 | 729 | 1701 | 550 | 7 | 2026-05-29 | 88 | P01745 (CAD) | 22238.7 | 🟢 Order by 2026-05-29 — 88d buffer (lead 56d)
102195 | [102195] tf C100 Dust Cover | Laiju Bag |  | 1 |  | 46 | 0 | 46 | 15 | 3.1 | 45 | 105 | 100 | 9.7 | 2026-06-02 | 92 | P01422 (USD) | 760 | 🟢 Order by 2026-06-02 — 92d buffer (lead 1d)
101535 | [101535] PCBA tF C-100 Connector Board | SMT Hautes Technolog | 101535 | 70 |  | 44 | 1265 | 1309 | 243 | 5.4 | 729 | 1701 | 400 | 7 | 2026-06-03 | 93 | P01746 (USD) | 74180 | 🟢 Order by 2026-06-03 — 93d buffer (lead 70d)
101604 | [101604] Power Cord 2.0M Black, IS 653 | Quail Electronics | 9840.079 | 28 |  | 61 | 0 | 61 | 15 | 4.1 | 45 | 105 | 50 | 7.4 | 2026-06-05 | 95 | P00878 (CAD) | 339.76 | 🟢 Order by 2026-06-05 — 95d buffer (lead 28d)
102584 | [102584] USB to Ethernet Adapter (incl | Radicom |  | 28 |  | 156 | 353 | 509 | 125 | 4.1 | 375 | 875 | 400 | 7.3 | 2026-06-05 | 95 | P01880 (CAD) | 29321.2 | 🟢 Order by 2026-06-05 — 95d buffer (lead 28d)
100328 | [100328] TremoFlo C-100 Motor Piston I | Alloy Concepts | 100328 | 56 |  | 379 | 842 | 1221 | 243 | 5 | 729 | 1701 | 500 | 7.1 | 2026-06-06 | 96 | P01745 (CAD) | 3771.45 | 🟢 Order by 2026-06-06 — 96d buffer (lead 56d)
100783 | [100783] tF C-100 HHU_LENS LIGHT PIPE | ICO Mold LLC | 100783 | 42 |  | 714 | 400 | 1114 | 243 | 4.6 | 729 | 1701 | 600 | 7.1 | 2026-06-07 | 97 | P01844 (USD) | 1548 | 🟢 Order by 2026-06-07 — 97d buffer (lead 42d)
100322 | [100322] TremoFlo C-100 Hall Sensor Br | Alloy Concepts | 100322 | 56 |  | 765 | 475 | 1240 | 243 | 5.1 | 729 | 1701 | 500 | 7.2 | 2026-06-09 | 99 | P01745 (CAD) | 9012.6 | 🟢 Order by 2026-06-09 — 99d buffer (lead 56d)
101254 | [101254] tF C-100 Light Piston | Alloy Concepts |  | 56 |  | 245 | 1005 | 1250 | 243 | 5.1 | 729 | 1701 | 500 | 7.2 | 2026-06-10 | 100 | P01745 (CAD) | 46902.95 | 🟢 Order by 2026-06-10 — 100d buffer (lead 56d)
101793 | [101793] tf Shipper Box - Vitalograph | Lovepac |  | 42 |  | 121 | 0 | 121 | 25 | 4.8 | 75 | 175 | 100 | 8.8 | 2026-06-15 | 105 | P01613 (CAD) | 2731.27 | 🟢 Order by 2026-06-15 — 105d buffer (lead 42d)
100477 | [100477] tremoFlo C-100 Mezzanine PCBA | SMT Hautes Technolog | 100477 | 70 |  | 79 | 1340 | 1419 | 243 | 5.8 | 729 | 1701 | 300 | 7.1 | 2026-06-17 | 107 | P01746 (USD) | 30450 | 🟢 Order by 2026-06-17 — 107d buffer (lead 70d)
100797 | [100797] tF C-100 CCU Enclosure Interf | ICO Mold LLC | 100797 | 42 |  | 511 | 700 | 1211 | 243 | 5 | 729 | 1701 | 500 | 7 | 2026-06-19 | 109 | P01844 (USD) | 710 | 🟢 Order by 2026-06-19 — 109d buffer (lead 42d)
101648 | [101648] tremoFlo C-100 User Manual, E | Graphiscan |  | 28 |  | 139 | 10 | 149 | 33 | 4.5 | 99 | 231 | 100 | 7.5 | 2026-06-19 | 109 | P01859 (CAD) | 1301.13 | 🟢 Order by 2026-06-19 — 109d buffer (lead 28d)
100785 | [100785] tF C-100 HHU_LEFT BUTTON Inj. | ICO Mold LLC | 030-100785-00 | 42 |  | 521 | 700 | 1221 | 243 | 5 | 729 | 1701 | 500 | 7.1 | 2026-06-20 | 110 | P01844 (USD) | 555 | 🟢 Order by 2026-06-20 — 110d buffer (lead 42d)
101658 | [101658] tf C2 Battery Pack | GEB General Electro |  | 42 |  | 79 | 200 | 279 | 55 | 5.1 | 165 | 385 | 150 | 7.8 | 2026-06-22 | 112 | P01790 (USD) | 802.5 | 🟢 Order by 2026-06-22 — 112d buffer (lead 42d)
100786 | [100786] tF C100 HHU RIGHT BUTTON Inj. | ICO Mold LLC | 030-100786-00 | 42 |  | 543 | 700 | 1243 | 243 | 5.1 | 729 | 1701 | 500 | 7.2 | 2026-06-23 | 113 | P01844 (USD) | 555 | 🟢 Order by 2026-06-23 — 113d buffer (lead 42d)
101393 | [101393] MOTOR THERMAL SWITCH [O53GAB1 | E-Sonic | O53GAB140A-125Y | 14 |  | 620 | 400 | 1020 | 243 | 4.2 | 729 | 1701 | 700 | 7.1 | 2026-06-23 | 113 | P01873 (CAD) | 10857.63 | 🟢 Order by 2026-06-23 — 113d buffer (lead 14d)
101675 | [101675] tf C2 - Battery Strap | Atlas Gaskets |  | 28 |  | 256 | 0 | 256 | 55 | 4.7 | 165 | 385 | 150 | 7.4 | 2026-06-23 | 113 | P00729 (USD) | 259.5 | 🟢 Order by 2026-06-23 — 113d buffer (lead 28d)
100795 | [100795] tF C-100 CCU Enclosure BOTTOM | ICO Mold LLC | 030-100795-00 | 42 |  | 153 | 1100 | 1253 | 243 | 5.2 | 729 | 1701 | 450 | 7 | 2026-06-24 | 114 | P01844 (USD) | 3213 | 🟢 Order by 2026-06-24 — 114d buffer (lead 42d)
100794 | [100794] tF C-100 CCU Enclosure Holder | ICO Mold LLC | 030-100794-00 | 42 |  | 410 | 464 | 874 | 168 | 5.2 | 504 | 1176 | 350 | 7.3 | 2026-06-26 | 116 | P01844 (USD) | 1424.5 | 🟢 Order by 2026-06-26 — 116d buffer (lead 42d)
101612 | [101612] tF C-100 Shipper Box Carton o | Lovepac |  | 42 |  | 265 | 610 | 875 | 168 | 5.2 | 504 | 1176 | 350 | 7.3 | 2026-06-26 | 116 | P01842 (CAD) | 7861 | 🟢 Order by 2026-06-26 — 116d buffer (lead 42d)
101706 | [101706] tf C2 - Exhaust Mesh Frame | Custom Sheet Metal P |  | 70 |  | 337 | 0 | 337 | 55 | 6.1 | 165 | 385 | 50 | 7 | 2026-06-26 | 116 | P00754 (CAD) | 59.01 | 🟢 Order by 2026-06-26 — 116d buffer (lead 70d)
101532 | [101532] PCBA TFC100 NB-SBC | SMT Hautes Technolog | 101532 | 70 |  | 97 | 1404 | 1501 | 243 | 6.2 | 729 | 1701 | 200 | 7 | 2026-06-28 | 118 | P01746 (USD) | 48680 | 🟢 Order by 2026-06-28 — 118d buffer (lead 70d)
100793 | [100793] tF C-100 CCU Enclosure Top In | ICO Mold LLC | 030-100793-00 | 42 |  | 493 | 400 | 893 | 168 | 5.3 | 504 | 1176 | 300 | 7.1 | 2026-06-29 | 119 | P01844 (USD) | 4332 | 🟢 Order by 2026-06-29 — 119d buffer (lead 42d)
100781 | [100781] tF C-100 HHU Front Shell Inj. | ICO Mold LLC | 030-100781-00 | 42 |  | 197 | 1100 | 1297 | 243 | 5.3 | 729 | 1701 | 450 | 7.2 | 2026-06-30 | 120 | P01844 (USD) | 4725 | 🟢 Order by 2026-06-30 — 120d buffer (lead 42d)
100782 | [100782] tF C-100 HHU BACK SHELL Inj. | ICO Mold LLC | 030-100782-00 | 42 |  | 578 | 400 | 978 | 168 | 5.8 | 504 | 1176 | 200 | 7 | 2026-07-15 | 135 | P01844 (USD) | 3434 | 🟢 Order by 2026-07-15 — 135d buffer (lead 42d)
101682 | [101682] tf C2 - Sensor Module Foam Ga | Atlas Gaskets |  | 28 |  | 298 | 0 | 298 | 55 | 5.4 | 165 | 385 | 100 | 7.2 | 2026-07-16 | 136 | P00729 (USD) | 59 | 🟢 Order by 2026-07-16 — 136d buffer (lead 28d)
101672 | [101672] tf C2 - Custom Display Assemb | OSD Displays |  | 60 |  | 298 | 0 | 298 | 45 | 6.6 | 135 | 315 | 50 | 7.7 | 2026-07-21 | 141 | P00326 (USD) | 1440 | 🟢 Order by 2026-07-21 — 141d buffer (lead 60d)
100784 | [100784] tF C-100 HHU_LOOVER REAR PLAT | ICO Mold LLC | 030-100784-00 | 42 |  | 650 | 400 | 1050 | 168 | 6.2 | 504 | 1176 | 150 | 7.1 | 2026-07-28 | 148 | P01844 (USD) | 288 | 🟢 Order by 2026-07-28 — 148d buffer (lead 42d)
100791 | [100791] tF C-100 HHU_NAME PLATE Inj. | ICO Mold LLC | 030-100791-00 | 42 |  | 653 | 400 | 1053 | 168 | 6.3 | 504 | 1176 | 150 | 7.2 | 2026-07-28 | 148 | P01844 (USD) | 279 | 🟢 Order by 2026-07-28 — 148d buffer (lead 42d)
101073 | [101073] Medical Grade Power Cord PWL- | Infinite Cables |  | 7 |  | 279 | 560 | 839 | 161 | 5.2 | 483 | 1127 | 300 | 7.1 | 2026-07-31 | 151 | P01888 (CAD) | 2465.19 | 🟢 Order by 2026-07-31 — 151d buffer (lead 7d)
101113 | [101113] Power Cord, Type I (AS/NZS 31 | Infinite Cables |  | 7 |  | 26 | 0 | 26 | 5 | 5.2 | 15 | 35 | 50 | 15.2 | 2026-07-31 | 151 | P01538 (CAD) | 207.81 | 🟢 Order by 2026-07-31 — 151d buffer (lead 7d)
101685 | [101685] tf C2 Pneumotach Main Part | ICO Mold LLC, Brian |  | 42 |  | 352 | 0 | 352 | 55 | 6.4 | 165 | 385 | 50 | 7.3 | 2026-08-01 | 152 | P00741 (USD) | 63 | 🟢 Order by 2026-08-01 — 152d buffer (lead 42d)
100789 | [100789] tF C-100 HHU_FRONT CAP Inj. | ICO Mold LLC | 030-100789-00 | 42 |  | 702 | 400 | 1102 | 168 | 6.6 | 504 | 1176 | 100 | 7.2 | 2026-08-06 | 157 | P01844 (USD) | 254 | 🟢 Order by 2026-08-06 — 157d buffer (lead 42d)
101681 | [101681] tf C2 Sensor Module Cover | ICO Mold LLC |  | 42 |  | 380 | 0 | 380 | 55 | 6.9 | 165 | 385 | 50 | 7.8 | 2026-08-17 | 168 | P00741 (USD) | 58 | 🟢 Order by 2026-08-17 — 168d buffer (lead 42d)
101498 | [101498] Magnetic strip 24mm | Bogen Magnetics GmbH |  | 1 |  | 1756 | 0 | 1756 | 298 | 5.9 | 894 | 2086 | 350 | 7.1 | 2026-08-27 | 178 | P01674 (USD) | 1701 | 🟢 Order by 2026-08-27 — 178d buffer (lead 1d)
101663 | [101663] tf C2 Power Supply | Globtek Inc. |  | 0 |  | 659 | 0 | 659 | 100 | 6.6 | 300 | 700 | 50 | 7.1 | 2026-09-18 | 200 | P00730 (USD) | 645.5 | ⚠ CHECK LEAD TIME — 🟢 Order by 2026-09-18 — 200d buffer (lead 0d)
✅ SUFFICIENT STOCK — 30 components (coverage > 7 months)
100792 | [100792] tF C-100 CCU Enclosure front | ICO Mold LLC | 030-100792-00 | 42 |  | 196 | 1100 | 1296 | 168 | 7.7 | 504 | 1176 |  |  |  |  | P01844 (USD) |  | ✅ Sufficient
100796 | [100796] tF C-100 CCU Enclosure Power | ICO Mold LLC | 030-100796-00 | 42 |  | 1943 | 700 | 2643 | 243 | 10.9 | 729 | 1701 |  |  |  |  | P01844 (USD) |  | ✅ Sufficient
101110 | [101110] Power Cord, Type E/F (CEE 7/7 | Infinite Cables |  | 7 |  | 515 | 560 | 1075 | 136 | 7.9 | 408 | 952 |  |  |  |  | P01888 (CAD) |  | ✅ Sufficient
101111 | [101111] Power Cord 2.5M, 1.0mm^2 H05V | Infinite Cables |  | 7 |  | 11 | 0 | 11 | 1 | 11 | 3 | 7 |  |  |  |  | P01303 (CAD) |  | ✅ Sufficient
101385 | [101385] tF C-100 PFT Filter Interface | Alloy Concepts | 101385 | 56 |  | 357 | 800 | 1157 | 163 | 7.1 | 489 | 1141 |  |  |  |  | P01745 (CAD) |  | ✅ Sufficient
101405 | [101405] Zebra 5095 High Performance B | FrontierPC |  | 1 |  | 0 | 25 | 25 |  | ∞ | 0 | 0 |  |  |  |  | P01747 (CAD) |  | ✅ Sufficient
101520 | [101520] 2.5 x 4 in. polyester Label r | The ZPS Store |  | 0 |  | 0 | 6 | 6 |  | ∞ | 0 | 0 |  |  |  |  | P01610 (CAD) |  | ⚠ CHECK LEAD TIME — ✅ Sufficient
101609 | [101609] Reference Load Shipper box wi | Lovepac |  | 0 |  | 206 | 960 | 1166 | 125 | 9.3 | 375 | 875 |  |  |  |  | P01871 (CAD) |  | ⚠ CHECK LEAD TIME — ✅ Sufficient
101641 | [101641] 2 x 1 in Zebra label roll | Barcodes Inc. |  | 1 |  | 0 | 2 | 2 |  | ∞ | 0 | 0 |  |  |  |  | P01747 (CAD) |  | ✅ Sufficient
101653 | [101653] tremoFlo C-100 User Manual, U | Graphiscan |  | 28 |  | 240 | 0 | 240 | 10 | 24 | 30 | 70 |  |  |  |  | P01859 (CAD) |  | ✅ Sufficient
101667 | [101667] tf C2 Top Shell | ICO Mold LLC |  | 42 |  | 212 | 500 | 712 | 45 | 15.8 | 135 | 315 |  |  |  |  | P01826 (USD) |  | ✅ Sufficient
101668 | [101668] tf C2 Bottom Shell | ICO Mold LLC, Brian |  | 42 |  | 569 | 0 | 569 | 55 | 10.3 | 165 | 385 |  |  |  |  | P01148 (USD) |  | ✅ Sufficient
101669 | [101669] tf C2 USB-C Cap | ICO Mold LLC, Brian |  | 42 |  | 345 | 0 | 345 | 45 | 7.7 | 135 | 315 |  |  |  |  | P00741 (USD) |  | ✅ Sufficient
101670 | [101670] tf C2 Front Cap | ICO Mold LLC, Brian |  | 42 |  | 356 | 0 | 356 | 45 | 7.9 | 135 | 315 |  |  |  |  | P00741 (USD) |  | ✅ Sufficient
101671 | [101671] tf C2 Shoe Mount Cover | ICO Mold LLC |  | 42 |  | 403 | 0 | 403 | 55 | 7.3 | 165 | 385 |  |  |  |  | P00741 (USD) |  | ✅ Sufficient
101677 | [101677] tf C2 Main Board PCBA | SMT Hautes Technolog |  | 180 |  | 273 | 772 | 1045 | 55 | 19 | 165 | 385 |  |  |  |  | P01894 (USD) |  | ✅ Sufficient
101678 | [101678] tf C2 Button Board PCBA | SMT Hautes Technolog |  | 180 |  | 582 | 743 | 1325 | 110 | 12 | 330 | 770 |  |  |  |  | P01816 (USD) |  | ✅ Sufficient
101679 | [101679] tf C2 USB Board PCBA | SMT Hautes Technolog |  | 0 |  | 278 | 799 | 1077 | 55 | 19.6 | 165 | 385 |  |  |  |  | P01816 (USD) |  | ⚠ CHECK LEAD TIME — ✅ Sufficient
101680 | [101680] tf C2 Motor Rod | Alloy Concepts |  | 63 |  | 534 | 400 | 934 | 110 | 8.5 | 330 | 770 |  |  |  |  | P01381 (CAD) |  | ✅ Sufficient
101687 | [101687] tf C2 Sensor Board PCBA | SMT Hautes Technolog |  | 180 |  | 327 | 789 | 1116 | 55 | 20.3 | 165 | 385 |  |  |  |  | P01816 (USD) |  | ✅ Sufficient
101700 | [101700] tf C2 Pneumotach chamber Back | ICO Mold LLC, Brian |  | 42 |  | 283 | 250 | 533 | 55 | 9.7 | 165 | 385 |  |  |  |  | P01826 (USD) |  | ✅ Sufficient
101701 | [101701] tf C2 Pneumotach chamber Fron | ICO Mold LLC, Brian |  | 42 |  | 213 | 250 | 463 | 45 | 10.3 | 135 | 315 |  |  |  |  | P01826 (USD) |  | ✅ Sufficient
101707 | [101707] tf C2 - Exhaust Mesh Standard | Atlas Gaskets |  | 28 |  | 567 | 0 | 567 | 55 | 10.3 | 165 | 385 |  |  |  |  | P01559 (USD) |  | ✅ Sufficient
101708 | [101708] Thermal fuse/switch 55C | SEKI |  | 28 |  | 741 | 0 | 741 | 55 | 13.5 | 165 | 385 |  |  |  |  | P00390 (USD) |  | ✅ Sufficient
101715 | [101715] Thermal switch mouting bracke | SEKI |  | 14 |  | 784 | 0 | 784 | 55 | 14.3 | 165 | 385 |  |  |  |  | P00390 (USD) |  | ✅ Sufficient
102152 | [102152] tf C2 Pneumotach chamber Fron | Xometry |  | 1 |  | 53 | 205 | 258 | 10 | 25.8 | 30 | 70 |  |  |  |  | P01814 (USD) |  | ✅ Sufficient
102242 | [102242] tf C2 Top Shell - VTG | ICO Mold LLC |  | 42 |  | 52 | 58 | 110 | 10 | 11 | 30 | 70 |  |  |  |  | P01865 (USD) |  | ✅ Sufficient
102243 | [102243] tf C2 Front Cap – VTG | ICO Mold LLC |  | 42 |  | 52 | 58 | 110 | 10 | 11 | 30 | 70 |  |  |  |  | P01865 (USD) |  | ✅ Sufficient
102244 | [102244] tf C2 USB-C Cap – VTG | ICO Mold LLC |  | 42 |  | 55 | 55 | 110 | 10 | 11 | 30 | 70 |  |  |  |  | P01865 (USD) |  | ✅ Sufficient
102245 | [102245] tf C2 Custom Display Assembly | OSD Displays, Christ |  | 1 |  | 0 | 100 | 100 | 10 | 10 | 30 | 70 |  |  |  |  | P01866 (USD) |  | ✅ Sufficient

## 🏭 By Supplier
Component PO Plan — Grouped by Supplier
Rate: 101485×5 101524×10 101761×25 101762×25 101769×5 101711×40 102239×5 102240×5 101963×15 101969×1 102002×1 102003×10 102005×1 102036×100 102181×25 102585×125 /mo ¦ Target: 7mo ¦ Reorder at: 3mo ¦ Generated: 2026-03-02 23:24 UTC
Ref | Component Name | Supplier | Sup Code | Lead Days | Min Qty | Stock Avail | Open Incoming | Total Avail | Monthly Req | Coverage Now(mo) | Reorder Point | Target Qty(7mo) | ORDER QTY | Coverage After | Latest Safe Order Date | Buffer (days) | Price Source | Est Value (USD) | Status
🏭 Custom Sheet Metal Products (CSTM) — 2 parts ¦ 2 to order ¦ Est. $99,643
100359 | [100359] TremoFlo C-100 CU Metal Enclo | Custom Sheet Metal P | 100359 | 70 |  | 226 | 300 | 526 | 243 | 2.2 | 729 | 1701 | 1200 | 7.1 | 2026-03-02 | -4 | P01840 (CAD) | 99583.68 | 🔴 CRITICAL — stock out in 65d, lead 70d — ORDER TODAY
101706 | [101706] tf C2 - Exhaust Mesh Frame | Custom Sheet Metal P |  | 70 |  | 337 | 0 | 337 | 55 | 6.1 | 165 | 385 | 50 | 7 | 2026-06-26 | 116 | P00754 (CAD) | 59.01 | 🟢 Order by 2026-06-26 — 116d buffer (lead 70d)
🏭 Alloy Concepts — 22 parts ¦ 20 to order ¦ Est. $401,773
100641 | [100641] tF C100 Test Load Body | Alloy Concepts |  | 56 |  | 23 | 0 | 23 | 125 | 0.2 | 375 | 875 | 900 | 7.4 | 2026-03-02 | -50 | P01034 (CAD) | 23420.34 | 🔴 CRITICAL — stock out in 5d, lead 56d — ORDER TODAY
100642 | [100642] tF C100 Test Load Spacer | Alloy Concepts |  | 56 |  | 0 | 0 | 0 | 250 | 0 | 750 | 1750 | 1750 | 7 | 2026-03-02 | -56 | P01034 (CAD) | 19665.45 | 🔴 CRITICAL — stock out in 0d, lead 56d — ORDER TODAY
100978 | [100978] tF C100 PFT Filter Interface | Alloy Concepts |  | 56 |  | 0 | 2 | 2 | 5 | 0.4 | 15 | 35 | 50 | 10.4 | 2026-03-02 | -43 | P01883 (CAD) | 4123.3 | 🔴 CRITICAL — stock out in 12d, lead 56d — ORDER TODAY
101109 | [101109] Test Load Adaptor - Suregard | Alloy Concepts |  | 56 |  | 9 | 0 | 9 | 5 | 1.8 | 15 | 35 | 50 | 11.8 | 2026-03-02 | -1 | P00220 (CAD) | 1109.81 | 🔴 CRITICAL — stock out in 54d, lead 56d — ORDER TODAY
100643 | [100643] tF C100 Test Load Cap | Alloy Concepts |  | 5 |  | 23 | 0 | 23 | 125 | 0.2 | 375 | 875 | 900 | 7.4 | 2026-03-02 | 0 | P01034 (CAD) | 22015.08 | 🟠 Order NOW — only 0d buffer
100348 | [100348] TremoFlo C-100 Motor Piston M | Alloy Concepts | 100348 | 56 |  | 136 | 750 | 886 | 243 | 3.6 | 729 | 1701 | 850 | 7.1 | 2026-04-25 | 54 | P01745 (CAD) | 19639.33 | 🟢 Order by 2026-04-25 — 54d buffer (lead 56d)
100326 | [100326] TremoFlo C-100 Motor Piston O | Alloy Concepts | 100326 | 56 |  | 234 | 750 | 984 | 243 | 4 | 729 | 1701 | 750 | 7.1 | 2026-05-08 | 67 | P01745 (CAD) | 6448.8 | 🟢 Order by 2026-05-08 — 67d buffer (lead 56d)
101541 | [101541] tF C-100 Pneumotach Heater Ri | Alloy Concepts | 101541 | 56 |  | 249 | 750 | 999 | 243 | 4.1 | 729 | 1701 | 750 | 7.2 | 2026-05-10 | 69 | P01745 (CAD) | 24767.25 | 🟢 Order by 2026-05-10 — 69d buffer (lead 56d)
100318 | [100318] TremoFlo C-100 Motor Bobbin | Alloy Concepts | 100318 | 56 |  | 111 | 900 | 1011 | 243 | 4.2 | 729 | 1701 | 700 | 7 | 2026-05-11 | 70 | P01745 (CAD) | 84080.08 | 🟢 Order by 2026-05-11 — 70d buffer (lead 56d)
101540 | [101540] tF C-100 Pneumotach Main Body | Alloy Concepts | 101540 | 56 |  | 118 | 928 | 1046 | 243 | 4.3 | 729 | 1701 | 700 | 7.2 | 2026-05-16 | 75 | P01745 (CAD) | 44944.27 | 🟢 Order by 2026-05-16 — 75d buffer (lead 56d)
101595 | [101595] tF C100 Test Load Adapter - C | Alloy Concepts |  | 56 |  | 249 | 459 | 708 | 163 | 4.3 | 489 | 1141 | 450 | 7.1 | 2026-05-17 | 76 | P01828 (CAD) | 9895.91 | 🟢 Order by 2026-05-17 — 76d buffer (lead 56d)
100975 | [100975] tF C100 Pneumotach Inner Mesh | Alloy Concepts | 100975 | 56 |  | 169 | 900 | 1069 | 243 | 4.4 | 729 | 1701 | 650 | 7.1 | 2026-05-18 | 77 | P01745 (CAD) | 10549.04 | 🟢 Order by 2026-05-18 — 77d buffer (lead 56d)
100977 | [100977] tF C100 Pneumotach Knob | Alloy Concepts | 100977 | 56 |  | 450 | 634 | 1084 | 243 | 4.5 | 729 | 1701 | 650 | 7.1 | 2026-05-20 | 79 | P01745 (CAD) | 14346.48 | 🟢 Order by 2026-05-20 — 79d buffer (lead 56d)
100321 | [100321] TremoFlo C-100 Motor Shaft | Alloy Concepts |  | 56 |  | 576 | 1611 | 2187 | 486 | 4.5 | 1458 | 3402 | 1250 | 7.1 | 2026-05-21 | 80 | P01745 (CAD) | 12489 | 🟢 Order by 2026-05-21 — 80d buffer (lead 56d)
100976 | [100976] tF C100 Pneumotach Outer Mesh | Alloy Concepts | 100976 | 56 |  | 197 | 900 | 1097 | 243 | 4.5 | 729 | 1701 | 650 | 7.2 | 2026-05-22 | 81 | P01745 (CAD) | 13584.16 | 🟢 Order by 2026-05-22 — 81d buffer (lead 56d)
101719 | [101719] tf C2 Piston CNC | Alloy Concepts |  | 56 |  | 248 | 5 | 253 | 55 | 4.6 | 165 | 385 | 150 | 7.3 | 2026-05-25 | 84 | P01635 (USD) | 8769 | 🟢 Order by 2026-05-25 — 84d buffer (lead 56d)
101255 | [101255] tF C-100 Light Motor Back Pla | Alloy Concepts | 101255 | 56 |  | 457 | 696 | 1153 | 243 | 4.7 | 729 | 1701 | 550 | 7 | 2026-05-29 | 88 | P01745 (CAD) | 22238.7 | 🟢 Order by 2026-05-29 — 88d buffer (lead 56d)
100328 | [100328] TremoFlo C-100 Motor Piston I | Alloy Concepts | 100328 | 56 |  | 379 | 842 | 1221 | 243 | 5 | 729 | 1701 | 500 | 7.1 | 2026-06-06 | 96 | P01745 (CAD) | 3771.45 | 🟢 Order by 2026-06-06 — 96d buffer (lead 56d)
100322 | [100322] TremoFlo C-100 Hall Sensor Br | Alloy Concepts | 100322 | 56 |  | 765 | 475 | 1240 | 243 | 5.1 | 729 | 1701 | 500 | 7.2 | 2026-06-09 | 99 | P01745 (CAD) | 9012.6 | 🟢 Order by 2026-06-09 — 99d buffer (lead 56d)
101254 | [101254] tF C-100 Light Piston | Alloy Concepts |  | 56 |  | 245 | 1005 | 1250 | 243 | 5.1 | 729 | 1701 | 500 | 7.2 | 2026-06-10 | 100 | P01745 (CAD) | 46902.95 | 🟢 Order by 2026-06-10 — 100d buffer (lead 56d)
101385 | [101385] tF C-100 PFT Filter Interface | Alloy Concepts | 101385 | 56 |  | 357 | 800 | 1157 | 163 | 7.1 | 489 | 1141 |  |  |  |  | P01745 (CAD) |  | ✅ Sufficient
101680 | [101680] tf C2 Motor Rod | Alloy Concepts |  | 63 |  | 534 | 400 | 934 | 110 | 8.5 | 330 | 770 |  |  |  |  | P01381 (CAD) |  | ✅ Sufficient
🏭 Lovepac — 4 parts ¦ 3 to order ¦ Est. $12,068
101610 | [101610] tF Power Supply & Cord Box - | Lovepac |  | 42 |  | 0 | 0 | 0 | 168 | 0 | 504 | 1176 | 1200 | 7.1 | 2026-03-02 | -42 | pricelist | 1476 | 🔴 CRITICAL — stock out in 0d, lead 42d — ORDER TODAY
101793 | [101793] tf Shipper Box - Vitalograph | Lovepac |  | 42 |  | 121 | 0 | 121 | 25 | 4.8 | 75 | 175 | 100 | 8.8 | 2026-06-15 | 105 | P01613 (CAD) | 2731.27 | 🟢 Order by 2026-06-15 — 105d buffer (lead 42d)
101612 | [101612] tF C-100 Shipper Box Carton o | Lovepac |  | 42 |  | 265 | 610 | 875 | 168 | 5.2 | 504 | 1176 | 350 | 7.3 | 2026-06-26 | 116 | P01842 (CAD) | 7861 | 🟢 Order by 2026-06-26 — 116d buffer (lead 42d)
101609 | [101609] Reference Load Shipper box wi | Lovepac |  | 0 |  | 206 | 960 | 1166 | 125 | 9.3 | 375 | 875 |  |  |  |  | P01871 (CAD) |  | ⚠ CHECK LEAD TIME — ✅ Sufficient
🏭 ICO Mold LLC — 28 parts ¦ 21 to order ¦ Est. $79,070
101744 | [101744] tf C-100 HHU LOOVER PLATE - V | ICO Mold LLC |  | 42 |  | 63 | 0 | 63 | 75 | 0.8 | 225 | 525 | 500 | 7.5 | 2026-03-02 | -16 | P01432 (USD) | 6240 | 🔴 CRITICAL — stock out in 25d, lead 42d — ORDER TODAY
101745 | [101745] tf C-100 HHU FRONT CAP - Vita | ICO Mold LLC |  | 42 |  | 61 | 0 | 61 | 75 | 0.8 | 225 | 525 | 500 | 7.5 | 2026-03-02 | -17 | P01432 (USD) | 6300 | 🔴 CRITICAL — stock out in 24d, lead 42d — ORDER TODAY
101746 | [101746] tf C-100 HHU_NAME PLATE - Vit | ICO Mold LLC |  | 42 |  | 54 | 0 | 54 | 75 | 0.7 | 225 | 525 | 500 | 7.4 | 2026-03-02 | -20 | P01432 (USD) | 6240 | 🔴 CRITICAL — stock out in 21d, lead 42d — ORDER TODAY
101747 | [101747] tf C-100 CCU Enclosure Holder | ICO Mold LLC |  | 42 |  | 61 | 0 | 61 | 75 | 0.8 | 225 | 525 | 500 | 7.5 | 2026-03-02 | -17 | P01432 (USD) | 7150 | 🔴 CRITICAL — stock out in 24d, lead 42d — ORDER TODAY
101748 | [101748] tf C-100 CCU Enclosure front | ICO Mold LLC |  | 42 |  | 62 | 0 | 62 | 75 | 0.8 | 225 | 525 | 500 | 7.5 | 2026-03-02 | -16 | P01432 (USD) | 9630 | 🔴 CRITICAL — stock out in 25d, lead 42d — ORDER TODAY
101749 | [101749] tf C-100 HHU BACK SHELL - Vit | ICO Mold LLC |  | 42 |  | 59 | 0 | 59 | 75 | 0.8 | 225 | 525 | 500 | 7.5 | 2026-03-02 | -18 | P01432 (USD) | 11740 | 🔴 CRITICAL — stock out in 23d, lead 42d — ORDER TODAY
101750 | [101750] tf C-100 CCU Enclosure Top - | ICO Mold LLC |  | 42 |  | 162 | 0 | 162 | 75 | 2.2 | 225 | 525 | 400 | 7.5 | 2026-03-25 | 23 | P01432 (USD) | 8896 | 🟡 Order by 2026-03-25 — 23d buffer (lead 42d)
100790 | [100790] tF C-100 HHU_STRAIN RELIEF In | ICO Mold LLC | 030-100790-00 | 42 |  | 383 | 1700 | 2083 | 486 | 4.3 | 1458 | 3402 | 1350 | 7.1 | 2026-05-29 | 88 | P01844 (USD) | 1498.5 | 🟢 Order by 2026-05-29 — 88d buffer (lead 42d)
100783 | [100783] tF C-100 HHU_LENS LIGHT PIPE | ICO Mold LLC | 100783 | 42 |  | 714 | 400 | 1114 | 243 | 4.6 | 729 | 1701 | 600 | 7.1 | 2026-06-07 | 97 | P01844 (USD) | 1548 | 🟢 Order by 2026-06-07 — 97d buffer (lead 42d)
100797 | [100797] tF C-100 CCU Enclosure Interf | ICO Mold LLC | 100797 | 42 |  | 511 | 700 | 1211 | 243 | 5 | 729 | 1701 | 500 | 7 | 2026-06-19 | 109 | P01844 (USD) | 710 | 🟢 Order by 2026-06-19 — 109d buffer (lead 42d)
100785 | [100785] tF C-100 HHU_LEFT BUTTON Inj. | ICO Mold LLC | 030-100785-00 | 42 |  | 521 | 700 | 1221 | 243 | 5 | 729 | 1701 | 500 | 7.1 | 2026-06-20 | 110 | P01844 (USD) | 555 | 🟢 Order by 2026-06-20 — 110d buffer (lead 42d)
100786 | [100786] tF C100 HHU RIGHT BUTTON Inj. | ICO Mold LLC | 030-100786-00 | 42 |  | 543 | 700 | 1243 | 243 | 5.1 | 729 | 1701 | 500 | 7.2 | 2026-06-23 | 113 | P01844 (USD) | 555 | 🟢 Order by 2026-06-23 — 113d buffer (lead 42d)
100795 | [100795] tF C-100 CCU Enclosure BOTTOM | ICO Mold LLC | 030-100795-00 | 42 |  | 153 | 1100 | 1253 | 243 | 5.2 | 729 | 1701 | 450 | 7 | 2026-06-24 | 114 | P01844 (USD) | 3213 | 🟢 Order by 2026-06-24 — 114d buffer (lead 42d)
100794 | [100794] tF C-100 CCU Enclosure Holder | ICO Mold LLC | 030-100794-00 | 42 |  | 410 | 464 | 874 | 168 | 5.2 | 504 | 1176 | 350 | 7.3 | 2026-06-26 | 116 | P01844 (USD) | 1424.5 | 🟢 Order by 2026-06-26 — 116d buffer (lead 42d)
100793 | [100793] tF C-100 CCU Enclosure Top In | ICO Mold LLC | 030-100793-00 | 42 |  | 493 | 400 | 893 | 168 | 5.3 | 504 | 1176 | 300 | 7.1 | 2026-06-29 | 119 | P01844 (USD) | 4332 | 🟢 Order by 2026-06-29 — 119d buffer (lead 42d)
100781 | [100781] tF C-100 HHU Front Shell Inj. | ICO Mold LLC | 030-100781-00 | 42 |  | 197 | 1100 | 1297 | 243 | 5.3 | 729 | 1701 | 450 | 7.2 | 2026-06-30 | 120 | P01844 (USD) | 4725 | 🟢 Order by 2026-06-30 — 120d buffer (lead 42d)
100782 | [100782] tF C-100 HHU BACK SHELL Inj. | ICO Mold LLC | 030-100782-00 | 42 |  | 578 | 400 | 978 | 168 | 5.8 | 504 | 1176 | 200 | 7 | 2026-07-15 | 135 | P01844 (USD) | 3434 | 🟢 Order by 2026-07-15 — 135d buffer (lead 42d)
100784 | [100784] tF C-100 HHU_LOOVER REAR PLAT | ICO Mold LLC | 030-100784-00 | 42 |  | 650 | 400 | 1050 | 168 | 6.2 | 504 | 1176 | 150 | 7.1 | 2026-07-28 | 148 | P01844 (USD) | 288 | 🟢 Order by 2026-07-28 — 148d buffer (lead 42d)
100791 | [100791] tF C-100 HHU_NAME PLATE Inj. | ICO Mold LLC | 030-100791-00 | 42 |  | 653 | 400 | 1053 | 168 | 6.3 | 504 | 1176 | 150 | 7.2 | 2026-07-28 | 148 | P01844 (USD) | 279 | 🟢 Order by 2026-07-28 — 148d buffer (lead 42d)
100789 | [100789] tF C-100 HHU_FRONT CAP Inj. | ICO Mold LLC | 030-100789-00 | 42 |  | 702 | 400 | 1102 | 168 | 6.6 | 504 | 1176 | 100 | 7.2 | 2026-08-06 | 157 | P01844 (USD) | 254 | 🟢 Order by 2026-08-06 — 157d buffer (lead 42d)
101681 | [101681] tf C2 Sensor Module Cover | ICO Mold LLC |  | 42 |  | 380 | 0 | 380 | 55 | 6.9 | 165 | 385 | 50 | 7.8 | 2026-08-17 | 168 | P00741 (USD) | 58 | 🟢 Order by 2026-08-17 — 168d buffer (lead 42d)
100792 | [100792] tF C-100 CCU Enclosure front | ICO Mold LLC | 030-100792-00 | 42 |  | 196 | 1100 | 1296 | 168 | 7.7 | 504 | 1176 |  |  |  |  | P01844 (USD) |  | ✅ Sufficient
100796 | [100796] tF C-100 CCU Enclosure Power | ICO Mold LLC | 030-100796-00 | 42 |  | 1943 | 700 | 2643 | 243 | 10.9 | 729 | 1701 |  |  |  |  | P01844 (USD) |  | ✅ Sufficient
101667 | [101667] tf C2 Top Shell | ICO Mold LLC |  | 42 |  | 212 | 500 | 712 | 45 | 15.8 | 135 | 315 |  |  |  |  | P01826 (USD) |  | ✅ Sufficient
101671 | [101671] tf C2 Shoe Mount Cover | ICO Mold LLC |  | 42 |  | 403 | 0 | 403 | 55 | 7.3 | 165 | 385 |  |  |  |  | P00741 (USD) |  | ✅ Sufficient
102242 | [102242] tf C2 Top Shell - VTG | ICO Mold LLC |  | 42 |  | 52 | 58 | 110 | 10 | 11 | 30 | 70 |  |  |  |  | P01865 (USD) |  | ✅ Sufficient
102243 | [102243] tf C2 Front Cap – VTG | ICO Mold LLC |  | 42 |  | 52 | 58 | 110 | 10 | 11 | 30 | 70 |  |  |  |  | P01865 (USD) |  | ✅ Sufficient
102244 | [102244] tf C2 USB-C Cap – VTG | ICO Mold LLC |  | 42 |  | 55 | 55 | 110 | 10 | 11 | 30 | 70 |  |  |  |  | P01865 (USD) |  | ✅ Sufficient
🏭 ULINE, Sales ULINE — 1 parts ¦ 1 to order ¦ Est. $0
102020 | [102020] Wafer Seal Sticker 1.5in | ULINE, Sales ULINE |  | 1 |  | 0 | 0 | 0 | 200 | 0 | 600 | 1400 | 1400 | 7 | 2026-03-02 | -1 | pricelist |  | 🔴 CRITICAL — stock out in 0d, lead 1d — ORDER TODAY
🏭 Globtek Inc. — 2 parts ¦ 2 to order ¦ Est. $6,132
101694 | [101694] USB Cable Type C to A - 2 Fe | Globtek Inc. |  | 1 |  | 91 | 0 | 91 | 100 | 0.9 | 300 | 700 | 650 | 7.4 | 2026-03-28 | 26 | P00730 (USD) | 5486 | 🟡 Order by 2026-03-28 — 26d buffer (lead 1d)
101663 | [101663] tf C2 Power Supply | Globtek Inc. |  | 0 |  | 659 | 0 | 659 | 100 | 6.6 | 300 | 700 | 50 | 7.1 | 2026-09-18 | 200 | P00730 (USD) | 645.5 | ⚠ CHECK LEAD TIME — 🟢 Order by 2026-09-18 — 200d buffer (lead 0d)
🏭 Sinpro Electronics — 1 parts ¦ 1 to order ¦ Est. $18,938
101557 | [101557] Medical Grade Power Supply fo | Sinpro Electronics |  | 84 |  | 494 | 500 | 994 | 243 | 4.1 | 729 | 1701 | 750 | 7.2 | 2026-04-11 | 40 | P01845 (USD) | 18937.5 | 🟡 Order by 2026-04-11 — 40d buffer (lead 84d)
🏭 SMT Hautes Technologies — 11 parts ¦ 7 to order ¦ Est. $239,916
101106 | [101106] TremoFlo C100 Custom made cab | SMT Hautes Technolog | 101106 | 112 |  | 278 | 1002 | 1280 | 243 | 5.3 | 729 | 1701 | 450 | 7.1 | 2026-04-19 | 48 | P01838 (CAD) | 25557.84 | 🟢 Order by 2026-04-19 — 48d buffer (lead 112d)
100481 | [100481] TremoFlo C-100 Handheld Ring | SMT Hautes Technolog |  | 119 |  | 87 | 1299 | 1386 | 243 | 5.7 | 729 | 1701 | 350 | 7.1 | 2026-04-25 | 54 | P01746 (USD) | 32872 | 🟢 Order by 2026-04-25 — 54d buffer (lead 119d)
100479 | [100479] TremoFlo C-100 Handheld Main | SMT Hautes Technolog |  | 119 |  | 61 | 1438 | 1499 | 243 | 6.2 | 729 | 1701 | 250 | 7.2 | 2026-05-09 | 68 | P01746 (USD) | 23480 | 🟢 Order by 2026-05-09 — 68d buffer (lead 119d)
100480 | [100480] TremoFlo C-100 Handheld Posit | SMT Hautes Technolog |  | 119 |  | 175 | 1481 | 1656 | 243 | 6.8 | 729 | 1701 | 50 | 7 | 2026-05-29 | 88 | P01746 (USD) | 4696 | 🟢 Order by 2026-05-29 — 88d buffer (lead 119d)
101535 | [101535] PCBA tF C-100 Connector Board | SMT Hautes Technolog | 101535 | 70 |  | 44 | 1265 | 1309 | 243 | 5.4 | 729 | 1701 | 400 | 7 | 2026-06-03 | 93 | P01746 (USD) | 74180 | 🟢 Order by 2026-06-03 — 93d buffer (lead 70d)
100477 | [100477] tremoFlo C-100 Mezzanine PCBA | SMT Hautes Technolog | 100477 | 70 |  | 79 | 1340 | 1419 | 243 | 5.8 | 729 | 1701 | 300 | 7.1 | 2026-06-17 | 107 | P01746 (USD) | 30450 | 🟢 Order by 2026-06-17 — 107d buffer (lead 70d)
101532 | [101532] PCBA TFC100 NB-SBC | SMT Hautes Technolog | 101532 | 70 |  | 97 | 1404 | 1501 | 243 | 6.2 | 729 | 1701 | 200 | 7 | 2026-06-28 | 118 | P01746 (USD) | 48680 | 🟢 Order by 2026-06-28 — 118d buffer (lead 70d)
101677 | [101677] tf C2 Main Board PCBA | SMT Hautes Technolog |  | 180 |  | 273 | 772 | 1045 | 55 | 19 | 165 | 385 |  |  |  |  | P01894 (USD) |  | ✅ Sufficient
101678 | [101678] tf C2 Button Board PCBA | SMT Hautes Technolog |  | 180 |  | 582 | 743 | 1325 | 110 | 12 | 330 | 770 |  |  |  |  | P01816 (USD) |  | ✅ Sufficient
101679 | [101679] tf C2 USB Board PCBA | SMT Hautes Technolog |  | 0 |  | 278 | 799 | 1077 | 55 | 19.6 | 165 | 385 |  |  |  |  | P01816 (USD) |  | ⚠ CHECK LEAD TIME — ✅ Sufficient
101687 | [101687] tf C2 Sensor Board PCBA | SMT Hautes Technolog |  | 180 |  | 327 | 789 | 1116 | 55 | 20.3 | 165 | 385 |  |  |  |  | P01816 (USD) |  | ✅ Sufficient
🏭 Xometry, Ethan Beum — 2 parts ¦ 2 to order ¦ Est. $29,105
101753 | [101753] tf C-100 Test Load adapter Vi | Xometry, Ethan Beum |  | 1 |  | 124 | 0 | 124 | 75 | 1.7 | 225 | 525 | 450 | 7.7 | 2026-04-20 | 49 | P01405 (CAD) | 10878.89 | 🟢 Order by 2026-04-20 — 49d buffer (lead 1d)
101755 | [101755] tf C-100 Filter interface Vit | Xometry, Ethan Beum |  | 1 |  | 125 | 0 | 125 | 75 | 1.7 | 225 | 525 | 400 | 7 | 2026-04-20 | 49 | P01405 (CAD) | 18226.08 | 🟢 Order by 2026-04-20 — 49d buffer (lead 1d)
🏭 Atlas Gaskets — 4 parts ¦ 3 to order ¦ Est. $2,681
101683 | [101683] tf C2 - Pneumotach Mesh | Atlas Gaskets |  | 28 |  | 143 | 0 | 143 | 55 | 2.6 | 165 | 385 | 250 | 7.1 | 2026-04-22 | 51 | P01559 (USD) | 2362.5 | 🟢 Order by 2026-04-22 — 51d buffer (lead 28d)
101675 | [101675] tf C2 - Battery Strap | Atlas Gaskets |  | 28 |  | 256 | 0 | 256 | 55 | 4.7 | 165 | 385 | 150 | 7.4 | 2026-06-23 | 113 | P00729 (USD) | 259.5 | 🟢 Order by 2026-06-23 — 113d buffer (lead 28d)
101682 | [101682] tf C2 - Sensor Module Foam Ga | Atlas Gaskets |  | 28 |  | 298 | 0 | 298 | 55 | 5.4 | 165 | 385 | 100 | 7.2 | 2026-07-16 | 136 | P00729 (USD) | 59 | 🟢 Order by 2026-07-16 — 136d buffer (lead 28d)
101707 | [101707] tf C2 - Exhaust Mesh Standard | Atlas Gaskets |  | 28 |  | 567 | 0 | 567 | 55 | 10.3 | 165 | 385 |  |  |  |  | P01559 (USD) |  | ✅ Sufficient
🏭 Net Burner — 1 parts ¦ 1 to order ¦ Est. $130,900
100159 | [100159] NetBurner Ethernet Core Modul | Net Burner | MOD5234-200IR | 21 |  | 323 | 300 | 623 | 243 | 2.6 | 729 | 1701 | 1100 | 7.1 | 2026-04-28 | 57 | P01841 (USD) | 130900 | 🟢 Order by 2026-04-28 — 57d buffer (lead 21d)
🏭 Infinite Cables — 5 parts ¦ 3 to order ¦ Est. $5,497
101322 | [101322] CABLE, ETHERNET CAT5E, WHITE, | Infinite Cables | CAT5E-07WH | 7 |  | 524 | 0 | 524 | 243 | 2.2 | 729 | 1701 | 1200 | 7.1 | 2026-04-29 | 58 | P01629 (CAD) | 2823.6 | 🟢 Order by 2026-04-29 — 58d buffer (lead 7d)
101073 | [101073] Medical Grade Power Cord PWL- | Infinite Cables |  | 7 |  | 279 | 560 | 839 | 161 | 5.2 | 483 | 1127 | 300 | 7.1 | 2026-07-31 | 151 | P01888 (CAD) | 2465.19 | 🟢 Order by 2026-07-31 — 151d buffer (lead 7d)
101113 | [101113] Power Cord, Type I (AS/NZS 31 | Infinite Cables |  | 7 |  | 26 | 0 | 26 | 5 | 5.2 | 15 | 35 | 50 | 15.2 | 2026-07-31 | 151 | P01538 (CAD) | 207.81 | 🟢 Order by 2026-07-31 — 151d buffer (lead 7d)
101110 | [101110] Power Cord, Type E/F (CEE 7/7 | Infinite Cables |  | 7 |  | 515 | 560 | 1075 | 136 | 7.9 | 408 | 952 |  |  |  |  | P01888 (CAD) |  | ✅ Sufficient
101111 | [101111] Power Cord 2.5M, 1.0mm^2 H05V | Infinite Cables |  | 7 |  | 11 | 0 | 11 | 1 | 11 | 3 | 7 |  |  |  |  | P01303 (CAD) |  | ✅ Sufficient
🏭 Graphiscan — 3 parts ¦ 2 to order ¦ Est. $2,212
102128 | [102128] C2 USB Power Supply Box Sleev | Graphiscan |  | 0 |  | 197 | 0 | 197 | 100 | 2 | 300 | 700 | 550 | 7.5 | 2026-04-30 | 59 | P01554 (CAD) | 911.13 | ⚠ CHECK LEAD TIME — 🟢 Order by 2026-04-30 — 59d buffer (lead 0d)
101648 | [101648] tremoFlo C-100 User Manual, E | Graphiscan |  | 28 |  | 139 | 10 | 149 | 33 | 4.5 | 99 | 231 | 100 | 7.5 | 2026-06-19 | 109 | P01859 (CAD) | 1301.13 | 🟢 Order by 2026-06-19 — 109d buffer (lead 28d)
101653 | [101653] tremoFlo C-100 User Manual, U | Graphiscan |  | 28 |  | 240 | 0 | 240 | 10 | 24 | 30 | 70 |  |  |  |  | P01859 (CAD) |  | ✅ Sufficient
🏭 Atlas Gaskets, Rebecca Lopez — 1 parts ¦ 1 to order ¦ Est. $40
101699 | [101699] tf C2 - Pneumotach Neck Foam | Atlas Gaskets, Rebec |  | 50 |  | 204 | 0 | 204 | 55 | 3.7 | 165 | 385 | 200 | 7.3 | 2026-05-03 | 62 | P00729 (USD) | 40 | 🟢 Order by 2026-05-03 — 62d buffer (lead 50d)
🏭 Minco — 1 parts ¦ 1 to order ¦ Est. $24,210
100346 | [100346] TremoFlo C-100 Pneumotach RTD | Minco | S100725PFYT24B | 42 |  | 443 | 400 | 843 | 243 | 3.5 | 729 | 1701 | 900 | 7.2 | 2026-05-04 | 63 | P01886 (USD) | 24210 | 🟢 Order by 2026-05-04 — 63d buffer (lead 42d)
🏭 Moticont — 1 parts ¦ 1 to order ¦ Est. $256,116
101278 | [101278] tf C100 Motor Assembly VCA | Moticont | LVCM-016-019-01 | 28 |  | 531 | 400 | 931 | 298 | 3.1 | 894 | 2086 | 1200 | 7.2 | 2026-05-08 | 67 | P01885 (USD) | 256116 | 🟢 Order by 2026-05-08 — 67d buffer (lead 28d)
🏭 NEL Technologies — 1 parts ¦ 1 to order ¦ Est. $22,066
100345 | [100345] TremoFlo C-100 Pneumotach Hea | NEL Technologies | NEL-2018-1743-HA | 42 |  | 490 | 400 | 890 | 243 | 3.7 | 729 | 1701 | 850 | 7.2 | 2026-05-10 | 69 | P01886 (USD) | 22066 | 🟢 Order by 2026-05-10 — 69d buffer (lead 42d)
🏭 Alloy Concepts, Perry MacIssaac — 1 parts ¦ 1 to order ¦ Est. $19,096
101718 | [101718] tf C2 - Main Body CNC | Alloy Concepts, Perr |  | 56 |  | 228 | 5 | 233 | 55 | 4.2 | 165 | 385 | 200 | 7.9 | 2026-05-13 | 72 | P01635 (USD) | 19096 | 🟢 Order by 2026-05-13 — 72d buffer (lead 56d)
🏭 E-Sonic — 2 parts ¦ 2 to order ¦ Est. $18,151
100866 | [100866] THERMOSTAT 50 DEG NC TO-220 A | E-Sonic | 67L050 | 14 |  | 337 | 400 | 737 | 243 | 3 | 729 | 1701 | 1000 | 7.1 | 2026-05-19 | 78 | P01595 (CAD) | 7293.7 | 🟢 Order by 2026-05-19 — 78d buffer (lead 14d)
101393 | [101393] MOTOR THERMAL SWITCH [O53GAB1 | E-Sonic | O53GAB140A-125Y | 14 |  | 620 | 400 | 1020 | 243 | 4.2 | 729 | 1701 | 700 | 7.1 | 2026-06-23 | 113 | P01873 (CAD) | 10857.63 | 🟢 Order by 2026-06-23 — 113d buffer (lead 14d)
🏭 Laiju Bag — 1 parts ¦ 1 to order ¦ Est. $760
102195 | [102195] tf C100 Dust Cover | Laiju Bag |  | 1 |  | 46 | 0 | 46 | 15 | 3.1 | 45 | 105 | 100 | 9.7 | 2026-06-02 | 92 | P01422 (USD) | 760 | 🟢 Order by 2026-06-02 — 92d buffer (lead 1d)
🏭 Quail Electronics — 1 parts ¦ 1 to order ¦ Est. $340
101604 | [101604] Power Cord 2.0M Black, IS 653 | Quail Electronics | 9840.079 | 28 |  | 61 | 0 | 61 | 15 | 4.1 | 45 | 105 | 50 | 7.4 | 2026-06-05 | 95 | P00878 (CAD) | 339.76 | 🟢 Order by 2026-06-05 — 95d buffer (lead 28d)
🏭 Radicom — 1 parts ¦ 1 to order ¦ Est. $29,321
102584 | [102584] USB to Ethernet Adapter (incl | Radicom |  | 28 |  | 156 | 353 | 509 | 125 | 4.1 | 375 | 875 | 400 | 7.3 | 2026-06-05 | 95 | P01880 (CAD) | 29321.2 | 🟢 Order by 2026-06-05 — 95d buffer (lead 28d)
🏭 GEB General Electronics Battery Co. Ltd — 1 parts ¦ 1 to order ¦ Est. $802
101658 | [101658] tf C2 Battery Pack | GEB General Electro |  | 42 |  | 79 | 200 | 279 | 55 | 5.1 | 165 | 385 | 150 | 7.8 | 2026-06-22 | 112 | P01790 (USD) | 802.5 | 🟢 Order by 2026-06-22 — 112d buffer (lead 42d)
🏭 OSD Displays — 1 parts ¦ 1 to order ¦ Est. $1,440
101672 | [101672] tf C2 - Custom Display Assemb | OSD Displays |  | 60 |  | 298 | 0 | 298 | 45 | 6.6 | 135 | 315 | 50 | 7.7 | 2026-07-21 | 141 | P00326 (USD) | 1440 | 🟢 Order by 2026-07-21 — 141d buffer (lead 60d)
🏭 ICO Mold LLC, Brian Bay — 6 parts ¦ 1 to order ¦ Est. $63
101685 | [101685] tf C2 Pneumotach Main Part | ICO Mold LLC, Brian |  | 42 |  | 352 | 0 | 352 | 55 | 6.4 | 165 | 385 | 50 | 7.3 | 2026-08-01 | 152 | P00741 (USD) | 63 | 🟢 Order by 2026-08-01 — 152d buffer (lead 42d)
101668 | [101668] tf C2 Bottom Shell | ICO Mold LLC, Brian |  | 42 |  | 569 | 0 | 569 | 55 | 10.3 | 165 | 385 |  |  |  |  | P01148 (USD) |  | ✅ Sufficient
101669 | [101669] tf C2 USB-C Cap | ICO Mold LLC, Brian |  | 42 |  | 345 | 0 | 345 | 45 | 7.7 | 135 | 315 |  |  |  |  | P00741 (USD) |  | ✅ Sufficient
101670 | [101670] tf C2 Front Cap | ICO Mold LLC, Brian |  | 42 |  | 356 | 0 | 356 | 45 | 7.9 | 135 | 315 |  |  |  |  | P00741 (USD) |  | ✅ Sufficient
101700 | [101700] tf C2 Pneumotach chamber Back | ICO Mold LLC, Brian |  | 42 |  | 283 | 250 | 533 | 55 | 9.7 | 165 | 385 |  |  |  |  | P01826 (USD) |  | ✅ Sufficient
101701 | [101701] tf C2 Pneumotach chamber Fron | ICO Mold LLC, Brian |  | 42 |  | 213 | 250 | 463 | 45 | 10.3 | 135 | 315 |  |  |  |  | P01826 (USD) |  | ✅ Sufficient
🏭 Bogen Magnetics GmbH Magnetics — 1 parts ¦ 1 to order ¦ Est. $1,701
101498 | [101498] Magnetic strip 24mm | Bogen Magnetics GmbH |  | 1 |  | 1756 | 0 | 1756 | 298 | 5.9 | 894 | 2086 | 350 | 7.1 | 2026-08-27 | 178 | P01674 (USD) | 1701 | 🟢 Order by 2026-08-27 — 178d buffer (lead 1d)
🏭 FrontierPC — 1 parts ¦ 0 to order ¦ Est. $0
101405 | [101405] Zebra 5095 High Performance B | FrontierPC |  | 1 |  | 0 | 25 | 25 |  | ∞ | 0 | 0 |  |  |  |  | P01747 (CAD) |  | ✅ Sufficient
🏭 The ZPS Store — 1 parts ¦ 0 to order ¦ Est. $0
101520 | [101520] 2.5 x 4 in. polyester Label r | The ZPS Store |  | 0 |  | 0 | 6 | 6 |  | ∞ | 0 | 0 |  |  |  |  | P01610 (CAD) |  | ⚠ CHECK LEAD TIME — ✅ Sufficient
🏭 Barcodes Inc. — 1 parts ¦ 0 to order ¦ Est. $0
101641 | [101641] 2 x 1 in Zebra label roll | Barcodes Inc. |  | 1 |  | 0 | 2 | 2 |  | ∞ | 0 | 0 |  |  |  |  | P01747 (CAD) |  | ✅ Sufficient
🏭 SEKI — 2 parts ¦ 0 to order ¦ Est. $0
101708 | [101708] Thermal fuse/switch 55C | SEKI |  | 28 |  | 741 | 0 | 741 | 55 | 13.5 | 165 | 385 |  |  |  |  | P00390 (USD) |  | ✅ Sufficient
101715 | [101715] Thermal switch mouting bracke | SEKI |  | 14 |  | 784 | 0 | 784 | 55 | 14.3 | 165 | 385 |  |  |  |  | P00390 (USD) |  | ✅ Sufficient
🏭 Xometry — 1 parts ¦ 0 to order ¦ Est. $0
102152 | [102152] tf C2 Pneumotach chamber Fron | Xometry |  | 1 |  | 53 | 205 | 258 | 10 | 25.8 | 30 | 70 |  |  |  |  | P01814 (USD) |  | ✅ Sufficient
🏭 OSD Displays, Christopher Geisler — 1 parts ¦ 0 to order ¦ Est. $0
102245 | [102245] tf C2 Custom Display Assembly | OSD Displays, Christ |  | 1 |  | 0 | 100 | 100 | 10 | 10 | 30 | 70 |  |  |  |  | P01866 (USD) |  | ✅ Sufficient

## 🔧 Buildable Units
Buildable Units — How Many Devices Can We Build Right Now?
Stock Only = physical stock now ¦ +Incoming = stock + all open PO receipts expected
Ref | Finished Product | Monthly Plan | Max Build (Stock Only) | Months Coverage | Max Build (+Incoming) | Months Coverage | Limiting Component (Stock Only) | Limiting Component (+Incoming)
101485 | tremoflo C-100 Airwave Oscillometry Syst | 5 | 0 | 0.0 mo | 0 | 0.0 mo | 100978 — [100978] tF C100 PFT Filter Inte (0 avail / 1.000/unit = 0 units) | 101610 — [101610] tF Power Supply & Cord (0 avail / 1.000/unit = 0 units)
101524 | tremoflo C-100 Airwave Oscillometry Syst | 10 | 0 | 0.0 mo | 0 | 0.0 mo | 101610 — [101610] tF Power Supply & Cord (0 avail / 1.000/unit = 0 units) | 101610 — [101610] tF Power Supply & Cord (0 avail / 1.000/unit = 0 units)
101761 | tf C-100 Kit Vitalograph - Clinical Tria | 25 | 44 | 1.8 mo | 54 | 2.2 mo | 101535 — [101535] PCBA tF C-100 Connector (44 avail / 1.000/unit = 44 units) | 101746 — [101746] tf C-100 HHU_NAME PLATE (54 avail / 1.000/unit = 54 units)
101762 | tf C-100 Kit Vitalograph - Healthcare Ed | 25 | 44 | 1.8 mo | 54 | 2.2 mo | 101535 — [101535] PCBA tF C-100 Connector (44 avail / 1.000/unit = 44 units) | 101746 — [101746] tf C-100 HHU_NAME PLATE (54 avail / 1.000/unit = 54 units)
101769 | tremoflo C2 Device - Bird - Purple | 5 | 79 | 15.8 mo | 143 | 28.6 mo | 101658 — [101658] tf C2 Battery Pack (79 avail / 1.000/unit = 79 units) | 101683 — [101683] tf C2 - Pneumotach Mesh (143 avail / 1.000/unit = 143 units)
101711 | tremoflo C2 Device - clearflo | 40 | 79 | 2.0 mo | 143 | 3.6 mo | 101658 — [101658] tf C2 Battery Pack (79 avail / 1.000/unit = 79 units) | 101683 — [101683] tf C2 - Pneumotach Mesh (143 avail / 1.000/unit = 143 units)
102239 | tf C2 Device - Blue - VTG 28501 | 5 | 0 | 0.0 mo | 100 | 20.0 mo | 102245 — [102245] tf C2 Custom Display As (0 avail / 1.000/unit = 0 units) | 102245 — [102245] tf C2 Custom Display As (100 avail / 1.000/unit = 100 units)
102240 | tf C2 Device - Blue - VTG 28554 | 5 | 0 | 0.0 mo | 100 | 20.0 mo | 102245 — [102245] tf C2 Custom Display As (0 avail / 1.000/unit = 0 units) | 102245 — [102245] tf C2 Custom Display As (100 avail / 1.000/unit = 100 units)
101963 | tremoflo C-100 Airwave Oscillometry Syst | 15 | 0 | 0.0 mo | 0 | 0.0 mo | 101610 — [101610] tF Power Supply & Cord (0 avail / 1.000/unit = 0 units) | 101610 — [101610] tF Power Supply & Cord (0 avail / 1.000/unit = 0 units)
101969 | tremoflo C-100 Airwave Oscillometry Syst | 1 | 0 | 0.0 mo | 0 | 0.0 mo | 101610 — [101610] tF Power Supply & Cord (0 avail / 1.000/unit = 0 units) | 101610 — [101610] tF Power Supply & Cord (0 avail / 1.000/unit = 0 units)
102002 | tremoflo C-100 Airwave Oscillometry Syst | 1 | 0 | 0.0 mo | 0 | 0.0 mo | 101610 — [101610] tF Power Supply & Cord (0 avail / 1.000/unit = 0 units) | 101610 — [101610] tF Power Supply & Cord (0 avail / 1.000/unit = 0 units)
102003 | tremoflo C-100 Airwave Oscillometry Syst | 10 | 0 | 0.0 mo | 0 | 0.0 mo | 101610 — [101610] tF Power Supply & Cord (0 avail / 1.000/unit = 0 units) | 101610 — [101610] tF Power Supply & Cord (0 avail / 1.000/unit = 0 units)
102005 | tremoflo C-100 Airwave Oscillometry Syst | 1 | 0 | 0.0 mo | 0 | 0.0 mo | 101610 — [101610] tF Power Supply & Cord (0 avail / 1.000/unit = 0 units) | 101610 — [101610] tF Power Supply & Cord (0 avail / 1.000/unit = 0 units)
102036 | tremoflo C2 Airwave Oscillometry System | 100 | 0 | 0.0 mo | 0 | 0.0 mo | 102020 — [102020] Wafer Seal Sticker 1.5i (0 avail / 2.000/unit = 0 units) | 102020 — [102020] Wafer Seal Sticker 1.5i (0 avail / 2.000/unit = 0 units)
102181 | tf C-100 Kit Vitalograph - Healthcare US | 25 | 44 | 1.8 mo | 54 | 2.2 mo | 101535 — [101535] PCBA tF C-100 Connector (44 avail / 1.000/unit = 44 units) | 101746 — [101746] tf C-100 HHU_NAME PLATE (54 avail / 1.000/unit = 54 units)
102585 | tremoflo C-100 Airwave Oscillometry Syst | 125 | 0 | 0.0 mo | 0 | 0.0 mo | 100642 — [100642] tF C100 Test Load Space (0 avail / 2.000/unit = 0 units) | 100642 — [100642] tF C100 Test Load Space (0 avail / 2.000/unit = 0 units)
101485 — tremoflo C-100 Airwave Oscillometry Sy ¦ Monthly: 5 ¦ Max buildable (stock): 0 ¦ Max buildable (+incoming): 2
Ref | Component | Qty/Unit | Stock | Incoming | Total | Build(Stock) | Build(+Inc)
100978 | [100978] tF C100 PFT Filter Interface | 1 | 0 | 2 | 2 | 0 | 2
101610 | [101610] tF Power Supply & Cord Box - | 1 | 0 | 0 | 0 | 0 | 0
101109 | [101109] Test Load Adaptor - Suregard | 1 | 9 | 0 | 9 | 9 | 9
101113 | [101113] Power Cord, Type I (AS/NZS 31 | 1 | 26 | 0 | 26 | 26 | 26
101535 | [101535] PCBA tF C-100 Connector Board | 1 | 44 | 1265 | 1309 | 44 | 1309
100479 | [100479] TremoFlo C-100 Handheld Main | 1 | 61 | 1438 | 1499 | 61 | 1499
100477 | [100477] tremoFlo C-100 Mezzanine PCBA | 1 | 79 | 1340 | 1419 | 79 | 1419
100481 | [100481] TremoFlo C-100 Handheld Ring | 1 | 87 | 1299 | 1386 | 87 | 1386
101532 | [101532] PCBA TFC100 NB-SBC | 1 | 97 | 1404 | 1501 | 97 | 1501
100318 | [100318] TremoFlo C-100 Motor Bobbin | 1 | 111 | 900 | 1011 | 111 | 1011
101540 | [101540] tF C-100 Pneumotach Main Body | 1 | 118 | 928 | 1046 | 118 | 1046
100348 | [100348] TremoFlo C-100 Motor Piston M | 1 | 136 | 750 | 886 | 136 | 886
101648 | [101648] tremoFlo C-100 User Manual, E | 1 | 139 | 10 | 149 | 139 | 149
100795 | [100795] tF C-100 CCU Enclosure BOTTOM | 1 | 153 | 1100 | 1253 | 153 | 1253
100975 | [100975] tF C100 Pneumotach Inner Mesh | 1 | 169 | 900 | 1069 | 169 | 1069
101524 — tremoflo C-100 Airwave Oscillometry Sy ¦ Monthly: 10 ¦ Max buildable (stock): 0 ¦ Max buildable (+incoming): 0
Ref | Component | Qty/Unit | Stock | Incoming | Total | Build(Stock) | Build(+Inc)
101610 | [101610] tF Power Supply & Cord Box - | 1 | 0 | 0 | 0 | 0 | 0
101535 | [101535] PCBA tF C-100 Connector Board | 1 | 44 | 1265 | 1309 | 44 | 1309
100479 | [100479] TremoFlo C-100 Handheld Main | 1 | 61 | 1438 | 1499 | 61 | 1499
100477 | [100477] tremoFlo C-100 Mezzanine PCBA | 1 | 79 | 1340 | 1419 | 79 | 1419
100481 | [100481] TremoFlo C-100 Handheld Ring | 1 | 87 | 1299 | 1386 | 87 | 1386
101532 | [101532] PCBA TFC100 NB-SBC | 1 | 97 | 1404 | 1501 | 97 | 1501
100318 | [100318] TremoFlo C-100 Motor Bobbin | 1 | 111 | 900 | 1011 | 111 | 1011
101540 | [101540] tF C-100 Pneumotach Main Body | 1 | 118 | 928 | 1046 | 118 | 1046
100348 | [100348] TremoFlo C-100 Motor Piston M | 1 | 136 | 750 | 886 | 136 | 886
100795 | [100795] tF C-100 CCU Enclosure BOTTOM | 1 | 153 | 1100 | 1253 | 153 | 1253
100975 | [100975] tF C100 Pneumotach Inner Mesh | 1 | 169 | 900 | 1069 | 169 | 1069
100480 | [100480] TremoFlo C-100 Handheld Posit | 1 | 175 | 1481 | 1656 | 175 | 1656
100790 | [100790] tF C-100 HHU_STRAIN RELIEF In | 2 | 383 | 1700 | 2083 | 191 | 1041
100792 | [100792] tF C-100 CCU Enclosure front | 1 | 196 | 1100 | 1296 | 196 | 1296
100781 | [100781] tF C-100 HHU Front Shell Inj. | 1 | 197 | 1100 | 1297 | 197 | 1297
101761 — tf C-100 Kit Vitalograph - Clinical Tr ¦ Monthly: 25 ¦ Max buildable (stock): 44 ¦ Max buildable (+incoming): 1309
Ref | Component | Qty/Unit | Stock | Incoming | Total | Build(Stock) | Build(+Inc)
101535 | [101535] PCBA tF C-100 Connector Board | 1 | 44 | 1265 | 1309 | 44 | 1309
101746 | [101746] tf C-100 HHU_NAME PLATE - Vit | 1 | 54 | 0 | 54 | 54 | 54
101749 | [101749] tf C-100 HHU BACK SHELL - Vit | 1 | 59 | 0 | 59 | 59 | 59
101745 | [101745] tf C-100 HHU FRONT CAP - Vita | 1 | 61 | 0 | 61 | 61 | 61
101747 | [101747] tf C-100 CCU Enclosure Holder | 1 | 61 | 0 | 61 | 61 | 61
100479 | [100479] TremoFlo C-100 Handheld Main | 1 | 61 | 1438 | 1499 | 61 | 1499
101748 | [101748] tf C-100 CCU Enclosure front | 1 | 62 | 0 | 62 | 62 | 62
101744 | [101744] tf C-100 HHU LOOVER PLATE - V | 1 | 63 | 0 | 63 | 63 | 63
100477 | [100477] tremoFlo C-100 Mezzanine PCBA | 1 | 79 | 1340 | 1419 | 79 | 1419
100481 | [100481] TremoFlo C-100 Handheld Ring | 1 | 87 | 1299 | 1386 | 87 | 1386
101532 | [101532] PCBA TFC100 NB-SBC | 1 | 97 | 1404 | 1501 | 97 | 1501
100318 | [100318] TremoFlo C-100 Motor Bobbin | 1 | 111 | 900 | 1011 | 111 | 1011
101540 | [101540] tF C-100 Pneumotach Main Body | 1 | 118 | 928 | 1046 | 118 | 1046
101793 | [101793] tf Shipper Box - Vitalograph | 1 | 121 | 0 | 121 | 121 | 121
101753 | [101753] tf C-100 Test Load adapter Vi | 1 | 124 | 0 | 124 | 124 | 124
101762 — tf C-100 Kit Vitalograph - Healthcare ¦ Monthly: 25 ¦ Max buildable (stock): 44 ¦ Max buildable (+incoming): 1309
Ref | Component | Qty/Unit | Stock | Incoming | Total | Build(Stock) | Build(+Inc)
101535 | [101535] PCBA tF C-100 Connector Board | 1 | 44 | 1265 | 1309 | 44 | 1309
101746 | [101746] tf C-100 HHU_NAME PLATE - Vit | 1 | 54 | 0 | 54 | 54 | 54
101749 | [101749] tf C-100 HHU BACK SHELL - Vit | 1 | 59 | 0 | 59 | 59 | 59
101745 | [101745] tf C-100 HHU FRONT CAP - Vita | 1 | 61 | 0 | 61 | 61 | 61
101747 | [101747] tf C-100 CCU Enclosure Holder | 1 | 61 | 0 | 61 | 61 | 61
100479 | [100479] TremoFlo C-100 Handheld Main | 1 | 61 | 1438 | 1499 | 61 | 1499
101748 | [101748] tf C-100 CCU Enclosure front | 1 | 62 | 0 | 62 | 62 | 62
101744 | [101744] tf C-100 HHU LOOVER PLATE - V | 1 | 63 | 0 | 63 | 63 | 63
100477 | [100477] tremoFlo C-100 Mezzanine PCBA | 1 | 79 | 1340 | 1419 | 79 | 1419
100481 | [100481] TremoFlo C-100 Handheld Ring | 1 | 87 | 1299 | 1386 | 87 | 1386
101532 | [101532] PCBA TFC100 NB-SBC | 1 | 97 | 1404 | 1501 | 97 | 1501
100318 | [100318] TremoFlo C-100 Motor Bobbin | 1 | 111 | 900 | 1011 | 111 | 1011
101540 | [101540] tF C-100 Pneumotach Main Body | 1 | 118 | 928 | 1046 | 118 | 1046
101753 | [101753] tf C-100 Test Load adapter Vi | 1 | 124 | 0 | 124 | 124 | 124
101755 | [101755] tf C-100 Filter interface Vit | 1 | 125 | 0 | 125 | 125 | 125
101769 — tremoflo C2 Device - Bird - Purple ¦ Monthly: 5 ¦ Max buildable (stock): 79 ¦ Max buildable (+incoming): 279
Ref | Component | Qty/Unit | Stock | Incoming | Total | Build(Stock) | Build(+Inc)
101658 | [101658] tf C2 Battery Pack | 1 | 79 | 200 | 279 | 79 | 279
101683 | [101683] tf C2 - Pneumotach Mesh | 1 | 143 | 0 | 143 | 143 | 143
101699 | [101699] tf C2 - Pneumotach Neck Foam | 1 | 204 | 0 | 204 | 204 | 204
101667 | [101667] tf C2 Top Shell | 1 | 212 | 500 | 712 | 212 | 712
101701 | [101701] tf C2 Pneumotach chamber Fron | 1 | 213 | 250 | 463 | 213 | 463
101718 | [101718] tf C2 - Main Body CNC | 1 | 228 | 5 | 233 | 228 | 233
101719 | [101719] tf C2 Piston CNC | 1 | 248 | 5 | 253 | 248 | 253
101675 | [101675] tf C2 - Battery Strap | 1 | 256 | 0 | 256 | 256 | 256
101680 | [101680] tf C2 Motor Rod | 2 | 534 | 400 | 934 | 267 | 467
101677 | [101677] tf C2 Main Board PCBA | 1 | 273 | 772 | 1045 | 273 | 1045
101679 | [101679] tf C2 USB Board PCBA | 1 | 278 | 799 | 1077 | 278 | 1077
101700 | [101700] tf C2 Pneumotach chamber Back | 1 | 283 | 250 | 533 | 283 | 533
101678 | [101678] tf C2 Button Board PCBA | 2 | 582 | 743 | 1325 | 291 | 662
101672 | [101672] tf C2 - Custom Display Assemb | 1 | 298 | 0 | 298 | 298 | 298
101682 | [101682] tf C2 - Sensor Module Foam Ga | 1 | 298 | 0 | 298 | 298 | 298
101711 — tremoflo C2 Device - clearflo ¦ Monthly: 40 ¦ Max buildable (stock): 79 ¦ Max buildable (+incoming): 279
Ref | Component | Qty/Unit | Stock | Incoming | Total | Build(Stock) | Build(+Inc)
101658 | [101658] tf C2 Battery Pack | 1 | 79 | 200 | 279 | 79 | 279
101683 | [101683] tf C2 - Pneumotach Mesh | 1 | 143 | 0 | 143 | 143 | 143
101699 | [101699] tf C2 - Pneumotach Neck Foam | 1 | 204 | 0 | 204 | 204 | 204
101667 | [101667] tf C2 Top Shell | 1 | 212 | 500 | 712 | 212 | 712
101701 | [101701] tf C2 Pneumotach chamber Fron | 1 | 213 | 250 | 463 | 213 | 463
101718 | [101718] tf C2 - Main Body CNC | 1 | 228 | 5 | 233 | 228 | 233
101719 | [101719] tf C2 Piston CNC | 1 | 248 | 5 | 253 | 248 | 253
101675 | [101675] tf C2 - Battery Strap | 1 | 256 | 0 | 256 | 256 | 256
101680 | [101680] tf C2 Motor Rod | 2 | 534 | 400 | 934 | 267 | 467
101677 | [101677] tf C2 Main Board PCBA | 1 | 273 | 772 | 1045 | 273 | 1045
101679 | [101679] tf C2 USB Board PCBA | 1 | 278 | 799 | 1077 | 278 | 1077
101700 | [101700] tf C2 Pneumotach chamber Back | 1 | 283 | 250 | 533 | 283 | 533
101678 | [101678] tf C2 Button Board PCBA | 2 | 582 | 743 | 1325 | 291 | 662
101672 | [101672] tf C2 - Custom Display Assemb | 1 | 298 | 0 | 298 | 298 | 298
101682 | [101682] tf C2 - Sensor Module Foam Ga | 1 | 298 | 0 | 298 | 298 | 298
102239 — tf C2 Device - Blue - VTG 28501 ¦ Monthly: 5 ¦ Max buildable (stock): 0 ¦ Max buildable (+incoming): 100
Ref | Component | Qty/Unit | Stock | Incoming | Total | Build(Stock) | Build(+Inc)
102245 | [102245] tf C2 Custom Display Assembly | 1 | 0 | 100 | 100 | 0 | 100
102242 | [102242] tf C2 Top Shell - VTG | 1 | 52 | 58 | 110 | 52 | 110
102243 | [102243] tf C2 Front Cap – VTG | 1 | 52 | 58 | 110 | 52 | 110
102152 | [102152] tf C2 Pneumotach chamber Fron | 1 | 53 | 205 | 258 | 53 | 258
102244 | [102244] tf C2 USB-C Cap – VTG | 1 | 55 | 55 | 110 | 55 | 110
101658 | [101658] tf C2 Battery Pack | 1 | 79 | 200 | 279 | 79 | 279
101683 | [101683] tf C2 - Pneumotach Mesh | 1 | 143 | 0 | 143 | 143 | 143
101699 | [101699] tf C2 - Pneumotach Neck Foam | 1 | 204 | 0 | 204 | 204 | 204
101718 | [101718] tf C2 - Main Body CNC | 1 | 228 | 5 | 233 | 228 | 233
101719 | [101719] tf C2 Piston CNC | 1 | 248 | 5 | 253 | 248 | 253
101675 | [101675] tf C2 - Battery Strap | 1 | 256 | 0 | 256 | 256 | 256
101680 | [101680] tf C2 Motor Rod | 2 | 534 | 400 | 934 | 267 | 467
101677 | [101677] tf C2 Main Board PCBA | 1 | 273 | 772 | 1045 | 273 | 1045
101679 | [101679] tf C2 USB Board PCBA | 1 | 278 | 799 | 1077 | 278 | 1077
101700 | [101700] tf C2 Pneumotach chamber Back | 1 | 283 | 250 | 533 | 283 | 533
102240 — tf C2 Device - Blue - VTG 28554 ¦ Monthly: 5 ¦ Max buildable (stock): 0 ¦ Max buildable (+incoming): 100
Ref | Component | Qty/Unit | Stock | Incoming | Total | Build(Stock) | Build(+Inc)
102245 | [102245] tf C2 Custom Display Assembly | 1 | 0 | 100 | 100 | 0 | 100
102242 | [102242] tf C2 Top Shell - VTG | 1 | 52 | 58 | 110 | 52 | 110
102243 | [102243] tf C2 Front Cap – VTG | 1 | 52 | 58 | 110 | 52 | 110
102152 | [102152] tf C2 Pneumotach chamber Fron | 1 | 53 | 205 | 258 | 53 | 258
102244 | [102244] tf C2 USB-C Cap – VTG | 1 | 55 | 55 | 110 | 55 | 110
101658 | [101658] tf C2 Battery Pack | 1 | 79 | 200 | 279 | 79 | 279
101683 | [101683] tf C2 - Pneumotach Mesh | 1 | 143 | 0 | 143 | 143 | 143
101699 | [101699] tf C2 - Pneumotach Neck Foam | 1 | 204 | 0 | 204 | 204 | 204
101718 | [101718] tf C2 - Main Body CNC | 1 | 228 | 5 | 233 | 228 | 233
101719 | [101719] tf C2 Piston CNC | 1 | 248 | 5 | 253 | 248 | 253
101675 | [101675] tf C2 - Battery Strap | 1 | 256 | 0 | 256 | 256 | 256
101680 | [101680] tf C2 Motor Rod | 2 | 534 | 400 | 934 | 267 | 467
101677 | [101677] tf C2 Main Board PCBA | 1 | 273 | 772 | 1045 | 273 | 1045
101679 | [101679] tf C2 USB Board PCBA | 1 | 278 | 799 | 1077 | 278 | 1077
101700 | [101700] tf C2 Pneumotach chamber Back | 1 | 283 | 250 | 533 | 283 | 533
101963 — tremoflo C-100 Airwave Oscillometry Sy ¦ Monthly: 15 ¦ Max buildable (stock): 0 ¦ Max buildable (+incoming): 0
Ref | Component | Qty/Unit | Stock | Incoming | Total | Build(Stock) | Build(+Inc)
101610 | [101610] tF Power Supply & Cord Box - | 1 | 0 | 0 | 0 | 0 | 0
101535 | [101535] PCBA tF C-100 Connector Board | 1 | 44 | 1265 | 1309 | 44 | 1309
102195 | [102195] tf C100 Dust Cover | 1 | 46 | 0 | 46 | 46 | 46
101604 | [101604] Power Cord 2.0M Black, IS 653 | 1 | 61 | 0 | 61 | 61 | 61
100479 | [100479] TremoFlo C-100 Handheld Main | 1 | 61 | 1438 | 1499 | 61 | 1499
100477 | [100477] tremoFlo C-100 Mezzanine PCBA | 1 | 79 | 1340 | 1419 | 79 | 1419
100481 | [100481] TremoFlo C-100 Handheld Ring | 1 | 87 | 1299 | 1386 | 87 | 1386
101532 | [101532] PCBA TFC100 NB-SBC | 1 | 97 | 1404 | 1501 | 97 | 1501
100318 | [100318] TremoFlo C-100 Motor Bobbin | 1 | 111 | 900 | 1011 | 111 | 1011
101540 | [101540] tF C-100 Pneumotach Main Body | 1 | 118 | 928 | 1046 | 118 | 1046
100348 | [100348] TremoFlo C-100 Motor Piston M | 1 | 136 | 750 | 886 | 136 | 886
101648 | [101648] tremoFlo C-100 User Manual, E | 1 | 139 | 10 | 149 | 139 | 149
100795 | [100795] tF C-100 CCU Enclosure BOTTOM | 1 | 153 | 1100 | 1253 | 153 | 1253
100975 | [100975] tF C100 Pneumotach Inner Mesh | 1 | 169 | 900 | 1069 | 169 | 1069
100480 | [100480] TremoFlo C-100 Handheld Posit | 1 | 175 | 1481 | 1656 | 175 | 1656
101969 — tremoflo C-100 Airwave Oscillometry Sy ¦ Monthly: 1 ¦ Max buildable (stock): 0 ¦ Max buildable (+incoming): 0
Ref | Component | Qty/Unit | Stock | Incoming | Total | Build(Stock) | Build(+Inc)
101610 | [101610] tF Power Supply & Cord Box - | 1 | 0 | 0 | 0 | 0 | 0
101535 | [101535] PCBA tF C-100 Connector Board | 1 | 44 | 1265 | 1309 | 44 | 1309
100479 | [100479] TremoFlo C-100 Handheld Main | 1 | 61 | 1438 | 1499 | 61 | 1499
100477 | [100477] tremoFlo C-100 Mezzanine PCBA | 1 | 79 | 1340 | 1419 | 79 | 1419
100481 | [100481] TremoFlo C-100 Handheld Ring | 1 | 87 | 1299 | 1386 | 87 | 1386
101532 | [101532] PCBA TFC100 NB-SBC | 1 | 97 | 1404 | 1501 | 97 | 1501
100318 | [100318] TremoFlo C-100 Motor Bobbin | 1 | 111 | 900 | 1011 | 111 | 1011
101540 | [101540] tF C-100 Pneumotach Main Body | 1 | 118 | 928 | 1046 | 118 | 1046
100348 | [100348] TremoFlo C-100 Motor Piston M | 1 | 136 | 750 | 886 | 136 | 886
101648 | [101648] tremoFlo C-100 User Manual, E | 1 | 139 | 10 | 149 | 139 | 149
100795 | [100795] tF C-100 CCU Enclosure BOTTOM | 1 | 153 | 1100 | 1253 | 153 | 1253
100975 | [100975] tF C100 Pneumotach Inner Mesh | 1 | 169 | 900 | 1069 | 169 | 1069
100480 | [100480] TremoFlo C-100 Handheld Posit | 1 | 175 | 1481 | 1656 | 175 | 1656
100790 | [100790] tF C-100 HHU_STRAIN RELIEF In | 2 | 383 | 1700 | 2083 | 191 | 1041
100792 | [100792] tF C-100 CCU Enclosure front | 1 | 196 | 1100 | 1296 | 196 | 1296
102002 — tremoflo C-100 Airwave Oscillometry Sy ¦ Monthly: 1 ¦ Max buildable (stock): 0 ¦ Max buildable (+incoming): 0
Ref | Component | Qty/Unit | Stock | Incoming | Total | Build(Stock) | Build(+Inc)
101610 | [101610] tF Power Supply & Cord Box - | 1 | 0 | 0 | 0 | 0 | 0
101111 | [101111] Power Cord 2.5M, 1.0mm^2 H05V | 1 | 11 | 0 | 11 | 11 | 11
101535 | [101535] PCBA tF C-100 Connector Board | 1 | 44 | 1265 | 1309 | 44 | 1309
100479 | [100479] TremoFlo C-100 Handheld Main | 1 | 61 | 1438 | 1499 | 61 | 1499
100477 | [100477] tremoFlo C-100 Mezzanine PCBA | 1 | 79 | 1340 | 1419 | 79 | 1419
100481 | [100481] TremoFlo C-100 Handheld Ring | 1 | 87 | 1299 | 1386 | 87 | 1386
101532 | [101532] PCBA TFC100 NB-SBC | 1 | 97 | 1404 | 1501 | 97 | 1501
100318 | [100318] TremoFlo C-100 Motor Bobbin | 1 | 111 | 900 | 1011 | 111 | 1011
101540 | [101540] tF C-100 Pneumotach Main Body | 1 | 118 | 928 | 1046 | 118 | 1046
100348 | [100348] TremoFlo C-100 Motor Piston M | 1 | 136 | 750 | 886 | 136 | 886
101648 | [101648] tremoFlo C-100 User Manual, E | 1 | 139 | 10 | 149 | 139 | 149
100795 | [100795] tF C-100 CCU Enclosure BOTTOM | 1 | 153 | 1100 | 1253 | 153 | 1253
100975 | [100975] tF C100 Pneumotach Inner Mesh | 1 | 169 | 900 | 1069 | 169 | 1069
100480 | [100480] TremoFlo C-100 Handheld Posit | 1 | 175 | 1481 | 1656 | 175 | 1656
100790 | [100790] tF C-100 HHU_STRAIN RELIEF In | 2 | 383 | 1700 | 2083 | 191 | 1041
102003 — tremoflo C-100 Airwave Oscillometry Sy ¦ Monthly: 10 ¦ Max buildable (stock): 0 ¦ Max buildable (+incoming): 0
Ref | Component | Qty/Unit | Stock | Incoming | Total | Build(Stock) | Build(+Inc)
101610 | [101610] tF Power Supply & Cord Box - | 1 | 0 | 0 | 0 | 0 | 0
101535 | [101535] PCBA tF C-100 Connector Board | 1 | 44 | 1265 | 1309 | 44 | 1309
100479 | [100479] TremoFlo C-100 Handheld Main | 1 | 61 | 1438 | 1499 | 61 | 1499
100477 | [100477] tremoFlo C-100 Mezzanine PCBA | 1 | 79 | 1340 | 1419 | 79 | 1419
100481 | [100481] TremoFlo C-100 Handheld Ring | 1 | 87 | 1299 | 1386 | 87 | 1386
101532 | [101532] PCBA TFC100 NB-SBC | 1 | 97 | 1404 | 1501 | 97 | 1501
100318 | [100318] TremoFlo C-100 Motor Bobbin | 1 | 111 | 900 | 1011 | 111 | 1011
101540 | [101540] tF C-100 Pneumotach Main Body | 1 | 118 | 928 | 1046 | 118 | 1046
100348 | [100348] TremoFlo C-100 Motor Piston M | 1 | 136 | 750 | 886 | 136 | 886
101648 | [101648] tremoFlo C-100 User Manual, E | 1 | 139 | 10 | 149 | 139 | 149
100795 | [100795] tF C-100 CCU Enclosure BOTTOM | 1 | 153 | 1100 | 1253 | 153 | 1253
100975 | [100975] tF C100 Pneumotach Inner Mesh | 1 | 169 | 900 | 1069 | 169 | 1069
100480 | [100480] TremoFlo C-100 Handheld Posit | 1 | 175 | 1481 | 1656 | 175 | 1656
100790 | [100790] tF C-100 HHU_STRAIN RELIEF In | 2 | 383 | 1700 | 2083 | 191 | 1041
100792 | [100792] tF C-100 CCU Enclosure front | 1 | 196 | 1100 | 1296 | 196 | 1296
102005 — tremoflo C-100 Airwave Oscillometry Sy ¦ Monthly: 1 ¦ Max buildable (stock): 0 ¦ Max buildable (+incoming): 0
Ref | Component | Qty/Unit | Stock | Incoming | Total | Build(Stock) | Build(+Inc)
101610 | [101610] tF Power Supply & Cord Box - | 1 | 0 | 0 | 0 | 0 | 0
101535 | [101535] PCBA tF C-100 Connector Board | 1 | 44 | 1265 | 1309 | 44 | 1309
100479 | [100479] TremoFlo C-100 Handheld Main | 1 | 61 | 1438 | 1499 | 61 | 1499
100477 | [100477] tremoFlo C-100 Mezzanine PCBA | 1 | 79 | 1340 | 1419 | 79 | 1419
100481 | [100481] TremoFlo C-100 Handheld Ring | 1 | 87 | 1299 | 1386 | 87 | 1386
101532 | [101532] PCBA TFC100 NB-SBC | 1 | 97 | 1404 | 1501 | 97 | 1501
100318 | [100318] TremoFlo C-100 Motor Bobbin | 1 | 111 | 900 | 1011 | 111 | 1011
101540 | [101540] tF C-100 Pneumotach Main Body | 1 | 118 | 928 | 1046 | 118 | 1046
100348 | [100348] TremoFlo C-100 Motor Piston M | 1 | 136 | 750 | 886 | 136 | 886
101648 | [101648] tremoFlo C-100 User Manual, E | 1 | 139 | 10 | 149 | 139 | 149
100795 | [100795] tF C-100 CCU Enclosure BOTTOM | 1 | 153 | 1100 | 1253 | 153 | 1253
100975 | [100975] tF C100 Pneumotach Inner Mesh | 1 | 169 | 900 | 1069 | 169 | 1069
100480 | [100480] TremoFlo C-100 Handheld Posit | 1 | 175 | 1481 | 1656 | 175 | 1656
100790 | [100790] tF C-100 HHU_STRAIN RELIEF In | 2 | 383 | 1700 | 2083 | 191 | 1041
100792 | [100792] tF C-100 CCU Enclosure front | 1 | 196 | 1100 | 1296 | 196 | 1296
102036 — tremoflo C2 Airwave Oscillometry Syste ¦ Monthly: 100 ¦ Max buildable (stock): 0 ¦ Max buildable (+incoming): 0
Ref | Component | Qty/Unit | Stock | Incoming | Total | Build(Stock) | Build(+Inc)
102020 | [102020] Wafer Seal Sticker 1.5in | 2 | 0 | 0 | 0 | 0 | 0
101694 | [101694] USB Cable Type C to A - 2 Fe | 1 | 91 | 0 | 91 | 91 | 91
102128 | [102128] C2 USB Power Supply Box Sleev | 1 | 197 | 0 | 197 | 197 | 197
101663 | [101663] tf C2 Power Supply | 1 | 659 | 0 | 659 | 659 | 659
102181 — tf C-100 Kit Vitalograph - Healthcare ¦ Monthly: 25 ¦ Max buildable (stock): 44 ¦ Max buildable (+incoming): 1309
Ref | Component | Qty/Unit | Stock | Incoming | Total | Build(Stock) | Build(+Inc)
101535 | [101535] PCBA tF C-100 Connector Board | 1 | 44 | 1265 | 1309 | 44 | 1309
101746 | [101746] tf C-100 HHU_NAME PLATE - Vit | 1 | 54 | 0 | 54 | 54 | 54
101749 | [101749] tf C-100 HHU BACK SHELL - Vit | 1 | 59 | 0 | 59 | 59 | 59
101745 | [101745] tf C-100 HHU FRONT CAP - Vita | 1 | 61 | 0 | 61 | 61 | 61
101747 | [101747] tf C-100 CCU Enclosure Holder | 1 | 61 | 0 | 61 | 61 | 61
100479 | [100479] TremoFlo C-100 Handheld Main | 1 | 61 | 1438 | 1499 | 61 | 1499
101748 | [101748] tf C-100 CCU Enclosure front | 1 | 62 | 0 | 62 | 62 | 62
101744 | [101744] tf C-100 HHU LOOVER PLATE - V | 1 | 63 | 0 | 63 | 63 | 63
100477 | [100477] tremoFlo C-100 Mezzanine PCBA | 1 | 79 | 1340 | 1419 | 79 | 1419
100481 | [100481] TremoFlo C-100 Handheld Ring | 1 | 87 | 1299 | 1386 | 87 | 1386
101532 | [101532] PCBA TFC100 NB-SBC | 1 | 97 | 1404 | 1501 | 97 | 1501
100318 | [100318] TremoFlo C-100 Motor Bobbin | 1 | 111 | 900 | 1011 | 111 | 1011
101540 | [101540] tF C-100 Pneumotach Main Body | 1 | 118 | 928 | 1046 | 118 | 1046
101753 | [101753] tf C-100 Test Load adapter Vi | 1 | 124 | 0 | 124 | 124 | 124
101755 | [101755] tf C-100 Filter interface Vit | 1 | 125 | 0 | 125 | 125 | 125
102585 — tremoflo C-100 Airwave Oscillometry Sy ¦ Monthly: 125 ¦ Max buildable (stock): 0 ¦ Max buildable (+incoming): 0
Ref | Component | Qty/Unit | Stock | Incoming | Total | Build(Stock) | Build(+Inc)
100642 | [100642] tF C100 Test Load Spacer | 2 | 0 | 0 | 0 | 0 | 0
101610 | [101610] tF Power Supply & Cord Box - | 1 | 0 | 0 | 0 | 0 | 0
100641 | [100641] tF C100 Test Load Body | 1 | 23 | 0 | 23 | 23 | 23
100643 | [100643] tF C100 Test Load Cap | 1 | 23 | 0 | 23 | 23 | 23
101535 | [101535] PCBA tF C-100 Connector Board | 1 | 44 | 1265 | 1309 | 44 | 1309
100479 | [100479] TremoFlo C-100 Handheld Main | 1 | 61 | 1438 | 1499 | 61 | 1499
100477 | [100477] tremoFlo C-100 Mezzanine PCBA | 1 | 79 | 1340 | 1419 | 79 | 1419
100481 | [100481] TremoFlo C-100 Handheld Ring | 1 | 87 | 1299 | 1386 | 87 | 1386
101532 | [101532] PCBA TFC100 NB-SBC | 1 | 97 | 1404 | 1501 | 97 | 1501
100318 | [100318] TremoFlo C-100 Motor Bobbin | 1 | 111 | 900 | 1011 | 111 | 1011
101540 | [101540] tF C-100 Pneumotach Main Body | 1 | 118 | 928 | 1046 | 118 | 1046
100348 | [100348] TremoFlo C-100 Motor Piston M | 1 | 136 | 750 | 886 | 136 | 886
100795 | [100795] tF C-100 CCU Enclosure BOTTOM | 1 | 153 | 1100 | 1253 | 153 | 1253
102584 | [102584] USB to Ethernet Adapter (incl | 1 | 156 | 353 | 509 | 156 | 509
100975 | [100975] tF C100 Pneumotach Inner Mesh | 1 | 169 | 900 | 1069 | 169 | 1069